## QL SBZ REL Projects Tracking
|  | Radu G. | [7 empty] | CA 1014449-A13-01
QL SBZ REL Projects Tracking
| ●● | ● | ● | ● | ● | ● | ● | ● | ● |  | ● | ● | ● | ● | ● | ● | ● | ● | ●● | ●● | ●● | ●●● | ●● | ●● | ●● | ●● | ●● | ●● | ●● | ●● | ●● | ●● | ●● | ●● | ●● | ●● | ●● | ●●
| QT Info (VAL-REL) | Input Date (dd.mm.yyyy) | Location | Area | OEM | BA | Unique Identification No. | Column1 | Project | Link/ Path | Phase | DT/PO/IO/CC | Planned START (Year) | Planned START (CW) | Planned END (YEAR) | Planned END (CW) | Project Team Responsible | QL VAL Test Responsible | QL REL Test Responsible | Actual START (CW) | Actual END (CW) | QT Status | Status of Test Reports | Last Update (CW)
| Received | 9.06.2021 | Continental-External | Continental-TSR |  | HMI | 963 | R01148 | DAG_BR464 | QL REL Timisoara - 06_ID01148_DAG_BR464IC_PV - All Documents (sharepoint.com) | PV | PO | 2021 | 43 | 2022 | 6 | Herzog Christian | Oana L. | Nick S. | 44 | 9 | Done | Status of Test Reports | Last Update (CW) | External Tests Tracking CA 1013201-F11-02 | DUT's Tracking List CA 1013201-F05-03 |  | Test Tracking CA 1013201-F07-02 | Test Orders (Completed) CA 1013201-F04 | 01_Feasibility Check CA 1013201-F03 | 02_Test Data | 03_Test Profiles and Archives | 04_Annexs (or email) with Pass or Fail | 05_Test Reports | 06_Test Orders (Scanned) | 07_Project Incident Report | 08_Customer Satisfaction Survey CA 1013201-F09-02 | Last Update (CW)
| Received | 01.11.2021 | Continental-Internal | Continental-ING |  | AM |  | R02019 | SVS220vW1_CP04 | SVS220vW1_CP04 | dPV | PO | 2022 | 6 | 2022 | 21 | Rehberger Andreas | Roxana M. | Cosmin R. | 6 | TBD | Ongoing
| New | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 597 | R02021 | SCCU EHNR MB W213 | EHNR | dPV 04 | PO | 2021 | 48 | 2021 | 50 | Anghel Adrian | Carmen B. | Radu G. | 48 | 4 | Done
| New | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 595 | R02022 | DCC3 | DCC3 | dPV | PO | 2021 | 48 | 2021 | 49 | Hategan Ion | Carmen B. | Radu G. | 47 | 50 | Done
| Received | 15.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 600 | R02023 | PNEU SCU - MB_213_D5_PSCM_MJ + PTL | PNEU SCU - MB_213_D5_PSCM_MJ | dPV | PO | 2022 | 41 | 2022 | 22 | Robert Rujan | Oana L. | Iulia T. | 44 | 13 | Done | All Sent | 20 | N.A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Incomplete | Completed | Completed | 21
| New | 19.02.2020 | Continental-External | Continental-ING |  | SAM-VED | 625 | R02024 | MiniMAB TVS N289 ReDesign | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Electronic_Brake_System/MiniMAB/01_ReDesign/03_R02024_QUALIFICATION_TVS%20N289(ID625)(SBZ)?csf=1&web=1&e=YRDsek | PV | PO | 2022 | 26 | 2022 | 50 | Schmailzl S. | Anca M. | Gabriel V. | TBD | TBD | Canceled | All Sent | 22 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| New | 04.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 806 | R02025 | DCC4 | DCC4 | DV | TBD | 2021 | 47 | 2022 | 12 | Ghise S. | Carmen B. | Radu G. | 47 | 13 | Done | All Sent | 26 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| New | 25.01.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED | 816 | R02026 | VED_CAIRS_PWR |  | Pre-Comp. | DT | 2022 | TBD | 2022 | TBD | Dumitriu Vasile | Oana L. | TBD. | TBD | TBD | Done
| New | 27.01.2021 | TBD | TBD |  | N.A | 818 | R02027 | Renar |  |  | N.A | 2022 | TBD | 2022 | TBD | N.A |  | TBD. | TBD | TBD | Done | All Sent | 35 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| Received | 1.02.2021 | Continental-External | Continental-TSR |  | QL | 830 | R02028 | MFC525 Camera | 03_R02028_MFC 525_Pre-compliance | Pre-Comp. | PO | 2022 | 2 | 2022 | 29 | Mardare Adrian | Anca M. | Radu I. | 2 | TBD | Ongoing | All Sent | 40 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| New | 2.02.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 839 | R02029 | MakeValves_dPV65 | MakeValves_dPV65 | dPV | PO | 2022 | 23 | 2022 | 47 | Ciobanu Aurelian | Oana L. | Iulia T. | TBD | TBD | Canceled | All Sent | 35 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| New | 2.02.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 840 | R02030 | MakeValves_dPV33 | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\VNI-CE\MakeValves\AUDI&Daimler\04_R02030_ReQualification_dPV33 | PWR | PO | 2022 | 13 | 2022 | 26 | Ciobanu Aurelian | Oana L. | TBD. | TBD | TBD | Canceled | All Sent | 37 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| New | 2.02.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 841 | R02031 | MakeValves_dPV44 | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\VNI-CE\MakeValves\AUDI&Daimler\05_R02031_ReQualification_dPV44 | PWR | PO | 2022 | 13 | 2022 | 26 | Ciobanu Aurelian | Oana L. | TBD. | TBD | TBD | Canceled
| New | 2.02.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 842 | R02032 | MakeValves_dPV45 | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\VNI-CE\MakeValves\AUDI&Daimler\06_R02032_ReQualification_dPV45 | PWR | PO | 2022 | 13 | 2022 | 26 | Ciobanu Aurelian | Oana L. | TBD. | TBD | TBD | Canceled
| New | 2.02.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 843 | R02033 | MakeValves_Dpv51 | Continental AG\Projects data\04_Project_Divisions\VNI-CE\MakeValves\AUDI&Daimler\07_R02033_ReQualification_dPV51 | PWR | PO | 2022 | 13 | 2022 | 26 | Ciobanu Aurelian | Oana L. | TBD. | TBD | TBD | Canceled | All Done | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| New | 3.02.2021 | Non-Continental | External-Schaffler |  | N.A | 848 | R02034 | Schaeffler_05TSwithsplash |  | Pre-Comp. | PO | 2022 | TBD | 2022 | TBD | Calburean Oliver-Gheorghe | Oana L. |  |  |  | Canceled | All Done | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| New | 3.02.2021 | Non-Continental | External-Schaffler |  | N.A | 850 | R02035 | Schaeffler_07MS | old process | Pre-Comp. | PO | 2022 | 44 | 2022 | 44 | Calburean Oliver-Gheorghe | Oana L. | Tiberiu B. | 46 | TBD | Done | All Sent | 46 | N.A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Incomplete | Completed | Completed | 22
| Received | 9.02.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 858 | R02036 | VW_MQB_23_GW-Baseline | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\VNI-CE\VW_MQB_23_GW\Baseline\03_R02036_DV | DV | Dsin | 2022 | 9 | 2022 | 50 | Costel Cojocaru | Roxana M. | Iulia T. | 9 | TBD | Ongoing | Not Started | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| Received | 15.02.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 865 | R02037 | EFP2V2K _PV 2021 | EFP2V2K | PV | PO | 2022 | 4 | 2022 | 20 | Salcianu Mihai | Carmen B. | Radu G. | 4 | 21 | Done | Not Started | 1
| New | 19.03.2021 | Non-Continental | External-VITESCO |  | N.A | 897 | R02038 | EXT_VT_IWS_Dpv | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\VITESCO\VT_HEV\BMW\01_BMW_DCDC\05_R02038_ReQualification_IWS(SBZ) | dPV | PO | 2022 | 14 | 2022 | 17 | Larion Catalin | Oana L. | Nick S. | 14 | 17 | Done | In Work | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| New | 22.03.2021 | Non-Continental | External-VITESCO |  | N.A | 900 | R02039 | VT_HV_DCDC22 | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\VITESCO\VT_HEV\BMW\01_BMW_DCDC\06_R02039_HV_DV(SBZ) | DV | PO | 2022 | 18 | 2022 | 5 | Chiriac Radu | Oana L. | Robert T. | TBD | TBD | Canceled | All Sent | 30 | N.A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Incomplete | Completed | Completed | 30
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 907 | R02040 | EFP3k+ | EFP3k+ | dPV | PO | 2022 | 2 | 2022 | 8 | Hategan I. | Carmen B. | Radu G. | TBD | TBD | Canceled | All Sent | 40 | N.A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Incomplete | Completed | Completed | 40
| Received | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 908 | R02041 | ICMV 2022 | ICMV 2022 | dPV | PO | 2022 | 5 | 2022 | 11 | Hategan I. | Carmen B. | Radu G. | 5 | 11 | Done | All Sent | 20 | N.A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Incomplete | Completed | Completed | 21
| Received | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 909 | R02042 | EFP 3K+ | EFP 3K+ | dPV | PO | 2022 | 8 | 2022 | 14 | Hategan I. | Carmen B. | Radu G. | 8 | 16 | Done | N.A
| Received | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 910 | R02043 | VOLVO | Volvo | dPV | PO | 2022 | 12 | 2022 | 27 | Hategan I. | Carmen B. | Radu G. | 12 | TBD | Ongoing | All Sent | 40 | N.A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Incomplete | Completed | N.A | 40
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 911 | R02044 | CHCM 1.25 | CHCM 1.25 | dPV | PO | 2022 | 14 | 2022 | 20 | Hategan I. | Carmen B. | Radu G. | TBD | TBD | Canceled
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 912 | R02045 | SCCU LF MB W213 SPC+ | SCCU LF MB W213 SPC | dPV | PO | 2022 | 16 | 2022 | 18 | Hategan I. | Carmen B. | Radu G. | 16 | 19 | Done | All Sent | 30 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 913 | R02046 | VDP_LOW | VDP LOW | dPV | PO | 2022 | 19 | 2022 | 22 | Hategan I. | Carmen B. | Radu G. | 19 | 24 | Done | All Sent | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| Received | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 914 | R02047 | EFP 2.0 | EFP 2.0 | dPV | PO | 2022 | 21 | 2022 | 26 | Hategan I. | Carmen B. | Radu G. | 21 | TBD | Ongoing | All Done | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 915 | R02048 | CHCM1.25 DTC | CHCM 1.25 DTC | dPV | PO | 2022 | 24 | 2022 | 28 | Hategan I. | Carmen B. | Radu G. | TBD | TBD | Canceled
| Received | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 916 | R02049 | EFP1.3 | EFP 1.3 | dPV | PO | 2022 | 26 | 2022 | 31 | Hategan I. | Carmen B. | Marius B.. | TBD | TBD | Next
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 917 | R02050 | SSD | SSD | dPV | PO | 2022 | 28 | 2022 | 33 | Hategan I. | Carmen B. | Marius B.. | TBD | TBD | Canceled | All Sent | 20 | N.A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Incomplete | Completed | Completed | 21
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 918 | R02051 | VDP_HIGH | VDP HIGH | dPV | PO | 2022 | 30 | 2022 | 36 | Hategan I. | Carmen B. | Marius B.. | TBD. | TBD. | Next | All Sent | 26 | N.A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Incomplete | Completed | Completed | 40
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 919 | R02052 | EFP3K | EFP3K | dPV | PO | 2022 | 32 | 2022 | 38 | Hategan I. | Carmen B. | Marius B.. | TBD | TBD | Next | All Sent | 28 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 920 | R02053 | SCCM | SCCM | dPV | PO | 2022 | 35 | 2022 | 41 | Hategan I. | Carmen B. | Marius B.. | TBD. | TBD. | Next
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 921 | R02054 | EFP1.3 | EFP1.3 | dPV | PO | 2022 | 38 | 2022 | 44 | Hategan I. | Carmen B. | TBD. | TBD | TBD | Next | All Sent | 50 | N.A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Incomplete | Completed | Completed | 50
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 922 | R02055 | EFP2.0 | EFP2.0 | dPV | PO | 2022 | 40 | 2022 | 46 | Hategan I. | Carmen B. | TBD. | TBD | TBD | Next | All Sent | 35 | N.A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Incomplete | Completed | Completed | 35
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 923 | R02056 | CHCM | CHCM | dPV | PO | 2022 | 42 | 2022 | 48 | Hategan I. | Carmen B. | TBD. | TBD | TBD | Next | All Sent | 40 | N.A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Incomplete | Completed | N.A | 40
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 924 | R02057 | SPC+ | SPC+ | dPV | PO | 2022 | 43 | 2022 | 49 | Hategan I. | Carmen B. | TBD. | TBD | TBD | Next | All Done | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 925 | R02058 | VADA | VADA | dPV | PO | 2022 | 45 | 2022 | 51 | Hategan I. | Carmen B. | TBD. | TBD | TBD | Next | All Done | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| New | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 926 | R02059 | EHNR | EHNR | dPV | PO | 2022 | 48 | 2023 | 4 | Hategan I. | Carmen B. | TBD. | TBD | TBD | Next | All Sent | 46 | N.A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Incomplete | Completed | Completed | 50
| Received | 10.05.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 942 | R02060 | BMW PDM TU3 |  | PV | DSIN | 2022 | 45 | 2022 | 6 | Arsene Ionela | Anca M. | Cosmin R. | 46 | 7 | Done | All Done | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| Received | 10.05.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED | 943 | R02061 | BMW G2x MY'19 MK 100 HP-HP | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Electronic_Brake_System/BMW/03_G2x%20MY19/03_R02061_QUALIFICATION_MK100%20HP-HP(ID943)(SBZ)/01_TEST%20ORDERS?csf=1&web=1&e=n9kuKF | PV | PO | 2022 | 5 | 2022 | 26 | Dallmeir Wolfgang | Anca M. | Catalin S. | 6 | TBD | Ongoing | All Sent | 51 | N.A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | N.A | Completed | Incomplete | Completed | Completed | 50
| Received | 11.05.2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 945 | R02062 | CVC_LOW | CVC_LOW | DV | PO | 2021 | 49 | 2022 | 26 | Stuparu C. | Carmen B. | Radu G. | 49 | 23 | Done | All Sent | 46 | N.A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Incomplete | Completed | Completed | 50
| New | 8.06.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 959 | R02064 | BMW I20 IGC PDLC | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/VNI-CE/ICG/03_R02064_QUALIFICATION_BMW%20I20%20IGC%20PDLC(ID959)(SBZ)?csf=1&web=1&e=kKdADV | dPV | PO | 2022 | 6 | 2022 | 11 | Tutui Daniel | Anca M. | Radu I. | TBD | TBD | Canceled | Not Started | 1 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| Received | 28.07.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED | 998 | R02066 | BMW_CAirS_CB1_MY18 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Cairs/BMW/03_R02066_QUALIFICATION_CB1_MY18(SBZ)?csf=1&web=1&e=85WGSk | PV | eSign | 2022 | 9 | 2022 | 27 | Andreas Goetz | Anca M. | Gabriel V. | 10 | TBD | Ongoing
| Received | 30.07.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1003 | R02067 | RAM_DT_CAirS_CK1_MY21 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Cairs/Stellantis%20DT/03_R02067_QUALIFICATION_RAM_DT_CAirS_CK1_MY21(SBZ)?csf=1&web=1&e=zDvKof | PV | PO | 2021 | 49 | 2022 | 23 | Andreas Goetz | Anca M. | Dan V. | 50 | 15 | Done | N.A
| Received | 2.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1004 | R02068 | Mercedes_Benz_eSPC_BR223 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Cairs/Mercedes/03_R02068_QUALIFICATION_eSPC_BR223?csf=1&web=1&e=whm9f9 | PV | PO | 2021 | 49 | 2022 | 28 | Andreas Goetz | Anca M. | Dan V. | 50 | TBD | Ongoing
| Received | 2.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1005 | R02069 | MRA2_CM4_MY22.75_GLV_BR254 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Cairs/Mercedes/04_R02069_QUALIFICATION_MRA2_CM4_MY22.75_GLV_BR254(ID1005)(SBZ)?csf=1&web=1&e=AMx6ER | PV | PO | 2021 | 49 | 2022 | 28 | Andreas Goetz | Anca M. | Dan V. | 50 | TBD | Ongoing
| Received | 2.08.2021 | Continental-Internal | Continental-ING |  | SAM-VED | 1007 | R02070 | ER100 PSA CMP ECO MY23.50_IPB High | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Electronic_Brake_System/PSA%20Group/03_R02070_QUALIFICATION_ER100%20PSA%20CMP%20ECO%20MY23.50_IPB%20High(SBZ)?csf=1&web=1&e=aaJ9h8 | PV | PO | 2022 | 19 | 2022 | 34 | Dallmeir Wolfgang | Stefania B. | Gabriel V. | 19 | TBD | Ongoing
| Received | 2.08.2021 | Continental-Internal | Continental-ING |  | SAM-VED | 1008 | R02071 | ER100 PSA CMP ECO MY23.50_IPB Base | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Electronic_Brake_System/PSA%20Group/05_R02071_QUALIFICATION_ER100%20PSA%20CMP%20ECO%20MY23.50_IPB%20Base(SBZ)?csf=1&web=1&e=nntzU0 | PV | PO | 2022 | 19 | 2022 | 34 | Dallmeir Wolfgang | Stefania B. | Gabriel V. | 19 | TBD | Ongoing
| Received | 2.08.2021 | Continental-Internal | Continental-ING |  | SAM-VED | 1009 | R02072 | ER100 PSA CMP ECO MY23.50_ESC Base | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Electronic_Brake_System/PSA%20Group/04_R02072_QUALIFICATION_ER100%20PSA%20CMP%20ECO%20MY23.50_ESC%20Base(SBZ)?csf=1&web=1&e=HEECMP | PV | PO | 2022 | 19 | 2022 | 34 | Dallmeir Wolfgang | Stefania B. | Gabriel V. | 19 | TBD | Ongoing
| Received | 2.08.2021 | Continental-Internal | Continental-ING |  | VED | 1011 | R02073 | Nissan_QX80_CAirS_MY23.75 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Cairs/Nissan/QX80_MY23.75/03_R02073_QUALIFICATION_Nissan_QX80_CAirS_MY23.75(ID1011)(SBZ)?csf=1&web=1&e=6rMHrO | DV | DSIN | 2021 | 44 | 2022 | 28 | Andreas Goetz | Anca M. | Dan V. | 45 | TBD | Ongoing
| New | 24.08.2021 | Continental-External | Continental-TSR |  | VNI | 1030 | R02074 | CCN_VolvoSPA22_2_TCM | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\VNI-CCN\TCM\Volvo\SPA22_2_TCM\03_R02074_QUALIFICATION(SBZ) | PV | PO | 2022 | 13 | 2022 | 30 | Arsene Ionela | Roxana M. | Radu I. | 14 | TBD | Ongoing
| Received | 31.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1039 | R02075 | ER100 Hyundai B_MPV | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Electronic_Brake_System/Hyundai/ER100_B-MPV/03_R02075_QUALIFICATION_B-MPV(ID1039)(SBZ)?csf=1&web=1&e=X1T9Ii | PV | PO | 2021 | 50 | 2022 | 9 | Stefan Schmailzl | Anca M. | Dan V. | 50 | 11 | Done
| New | 6.09.2021 | Non-Continental | External-Schaffler |  | N.A | 1044 | R02076 | P-085496-02-06-55_pre-comp_TS | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\EXTERNAL\Schaeffler\03_R02076_QUALIFICATION_TS | Pre-Comp. | PO | 2022 | 47 | 2022 | 48 | Calburean Oliver-Gheorghe | Oana L. | Radu I. | 47 | 48 | Done
| New | 6.09.2021 | Non-Continental | External-Schaffler |  | N.A | 1045 | R02077 | P-085496-02-06-55_pre-comp_VIB+Res+MS | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\EXTERNAL\Schaeffler\04_R02077_QUALIFICATION_VIB+RES+MS | Pre-Comp. | PO | 2022 | 2 | 2022 | 4 | Calburean Oliver-Gheorghe | Oana L. | Ion C. | TBD | TBD | Canceled
| New | 6.09.2021 | Non-Continental | External-Schaffler |  | N.A | 1046 | R02078 | P-085496-02-06-55_pre-comp_heathumid | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\EXTERNAL\Schaeffler\05_R02078_QUALIFICATION_heathumid | Pre-Comp. | PO | 2022 | 6 | 2022 | 7 | Calburean Oliver-Gheorghe | Oana L. | Robert T. | TBD | TBD | Canceled
| New | 6.09.2021 | Non-Continental | External-Schaffler |  | N.A | 1047 | R02079 | P-085496-02-06-55_pre-comp_low temp storage | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\EXTERNAL\Schaeffler\05_R02079_QUALIFICATION_low temp storage | Pre-Comp. | PO | 2022 | 9 | 2022 | 9 | Calburean Oliver-Gheorghe | Oana L. | TBD. | TBD | TBD | Canceled
| New | 7.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED | 1051 | R02080 | DAI_BR167 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Cairs/Mercedes/05_R02080_Pre-compliance_DAI_BR167?csf=1&web=1&e=VEwLsr | Pre-Comp. | DSIN | 2022 | 16 | 2022 | 17 | Slavu Alexandru | Anca M. | TBD. | TBD | TBD | Canceled
| New | 7.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED | 1052 | R02081 | DAI_BR223 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Cairs/Mercedes/06_R02081_Pre-compliance_DAI_BR223?csf=1&web=1&e=zlIBaD | Pre-Comp. | DSIN | 2022 | 19 | 2022 | 20 | Slavu Alexandru | Anca M. | TBD. | TBD | TBD | Canceled
| New | 7.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1053 | R02082 | GWM | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Cairs/GWM/03_R02053_Pre-compliance_GWM_VIB%26MS?csf=1&web=1&e=nZqaRf | Pre-Comp. | DSIN | 2022 | 45 | 2023 | 2 | Slavu Alexandru | Anca M. | TBD. | TBD | TBD | Next
| New | 7.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED | 1054 | R02083 | SAIC_S11L | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/AMS-VED/Cairs/SAIC/03_R02083_Pre-compliance_SAIC_S11L?csf=1&web=1&e=Z6QQy3 | Pre-Comp. | DSIN | 2022 | 37 | 2022 | 38 | Slavu Alexandru | Anca M. | TBD. | TBD | TBD | Next
| New | 7.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED | 1055 | R02084 | NISSAN_QX80 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Cairs/Nissan/QX80_MY23.75/04_R02084_Pre-compliance_Nissan_QX80(ID1055)(SBZ)?csf=1&web=1&e=aeDeWl | Pre-Comp. | DSIN | 2022 | 45 | 2022 | 46 | Slavu Alexandru | Anca M. | TBD. | TBD | TBD | Next
| Received | 7.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1056 | R02085 | MK100 MIB EVO BMW KRx | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/AMS-VED/Electronic_Brake_System/BMW/02_MK100_MIB_EVO_KRx/03_R02085_Pre-compliance(ID1056)(SBZ)?csf=1&web=1&e=AAbYMP | Pre-Comp. | PO | 2021 | 50 | 2022 | 2 | Dallmeir Wolfgang | Anca M. | Dan V. | 51 | 4 | Done
| New | 28.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED | 1085 | R02086 | ER100_Chrysler_MPMY21_Base | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/AMS-VED/Electronic_Brake_System/Chrysler/03_R02086_QUALIFICATION_ER100_Chrysler_MPMY21_Base(ID1085)(SBZ)?csf=1&web=1&e=DzUxNc | PV | PO | 2022 | 6 | 2022 | 16 | Stefan Schmailzl | Anca M. | TBD. | TBD | TBD | Canceled
| Received | 28.09.2021 | Continental-External | Continental-TSR |  | SAM-PSS | 1086 | R02087 | AMS PSS_Honda gSAT | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-PSS/SAT/Honda/03_SAT_HONDA_HRS8_gSAT/04_R02087_PV_compound%20endurance(ID1086)(SBZ)?csf=1&web=1&e=cVJPcQ | PV | PO | 2022 | 4 | 2022 | 7 | Nania Chariss | Anca M. | Tibi B. | 5 | 7 | Done
| Received | 4.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1092 | R02089 | MK100 HIGH PHASE 1 FAMILY LasColinas | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Cairs/Chrysler/01_MK100%20High%20Phase%201%20Family%20Las%20Colinas/03_R02089_QUALIFICATION_Chrysler%20JT(ID1092)(SBZ)?csf=1&web=1&e=43Ovio | PV | PO | 2021 | 48 | 2022 | 10 | Schmailzl S. | Anca M. | Dan V. | 49 | 10 | Done
| New | 4.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1094 | R02090 | PNEU SCU - MB_213_D5_PSCM_MJ | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\VNI-CE\PNEU SCU - MB_213_D5_PSCM_MJ\Daimler\04_R02090_ReQualification | dPV | PO | 2022 | 22 | 2022 | 35 | Ciobanu Aurelian | Roxana M. | Iulia T. | TBD | TBD | Canceled | N.A
| New | 4.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1095 | R02091 | PNEU SCU - MB_213_D5_PSCM_MJ | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\VNI-CE\PNEU SCU - MB_213_D5_PSCM_MJ\Daimler\05_R02091_ReQualification | dPV | PO | 2022 | 22 | 2022 | 35 | Ciobanu Aurelian | Roxana M. | Iulia T. | TBD | TBD | Canceled
| New | 4.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1096 | R02092 | MakeValves_dPV81 _dPV82 | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\VNI-CE\MakeValves\AUDI&Daimler\08_R02092_ReQualification_dPV81&dPV82 | dPV | PO | 2022 | 2 | 2022 | 14 | Ciobanu Aurelian | Oana L. | Iulia T. | TBD | TBD | Canceled
| New | 4.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1097 | R02093 | MakeValves_dPV64 | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\VNI-CE\MakeValves\AUDI&Daimler\09_R02093_ReQualification_dPV64 | dPV | PO | 2022 | 9 | 2022 | 14 | Ciobanu Aurelian | Oana L. | Cosmin R. | TBD | TBD | Canceled
| New | 4.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1098 | R02094 | MakeValves_dPV66 | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\VNI-CE\MakeValves\AUDI&Daimler\10_R02094_ReQualification_dPV66 | dPV | PO | 2022 | 36 | 2022 | 44 | Ciobanu Aurelian | Roxana M. | Cosmin R. | TBD | TBD | Next
| New | 4.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1099 | R02095 | MakeValves_dPV33_dPV44_dPV45_dPV51 | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\VNI-CE\MakeValves\AUDI&Daimler\11_R02095_ReQualification_dPV33_dPV44_dPV45_dPV51 | dPV | PO | 2022 | 18 | 2022 | 26 | Ciobanu Aurelian | Roxana M. | Iulia T. | 18 | TBD | Ongoing
| New | 6.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1104 | R02096 | CCN_VW_MQB_19_GW_LOW | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/VNI-CE/Gateway/VW/MQB/LOW/03_R02096_ReQUALIFICATION?csf=1&web=1&e=ME3wFp | dPV | PO | 2022 | 49 | 2022 | 6 | Costel Cojocaru | Oana L. | Iulia T. | 50 | 13 | Done | Not Started | 1
| New | 6.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1105 | R02097 | CCN_VW_MQB_19_FCM | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\VNI-CE\VW_MQB_23_GW\FCM\03_R02097_ReQUALIFICATION | dPV | PO | 2022 | 2 | 2022 | 9 | Costel Cojocaru | Oana L. | Iulia T. | 3 | 13 | Done | Not Started | 1
| New | 12.11.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI |  | R02098 | SVC220 | SVC220 | Pre-Comp. | Esign | 2021 | 46 | 2021 | 46 | Florin Prioteasa | Carmen B. | Carmen B. | 46 | 46 | Done
| Received | 13.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED | 1111 | R02099 | ER100 Honda 30AA MY23 ESC Base IPB HEV | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Electronic_Brake_System/Honda/01_ER100%20Honda%2030AA/03_R02099_QUALIFICATION_My23%20ESC%20Base%20IPB%20HEV(ID1111)(SBZ)?csf=1&web=1&e=0zaRvA | PV | PO | 2022 | 11 | 2022 | 23 | Dallmeir Wolfgang | Anca M. | Catalin S. | 11 | TBD | Canceled
| New | 13.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1112 | R02100 | AUD_XXXX_16_PNEU_BK |  | dPV | PO | 2022 | 47 | 2022 | 48 | Flencana Adelin | Oana L. | Iulia T. | TBD | TBD | Canceled
| New | 12.11.2021 | Non-Continental | External-VITESCO |  | VITESCO |  | R02101 | DB35 | DB35 | Pre-Comp. | PO | 2021 | 48 | 2021 | 48 | Tudor Pojar | Carmen B. | Carmen B. |  |  | Done
| Received | 19.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1118 | R02102 | Trial |  | Pre-Comp. | PO | 2021 | TBD | 2022 | TBD | Andreas Goetz | Anca M. | Gabriel V. | TBD | TBD | Done
| New | 22.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | AM | 1122 | R02103 | SVC221 | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\AMS-ADAS\CAMERA\Daimler\02_SVC221\03_R02103_ReQualification | dPV | PO | 2022 | 44 | 2022 | 47 | Zeljko Majstoro | Oana L. | Iulia T. | 46 | 51 | Done
| Received | 25.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 1123 | R02104 | EFP 3K | EFP3K | dPV | PO | 2022 | 2 | 2022 | 7 | Ion Hategan | Carmen B. | Radu G. | 2 | 9 | Done
| New | 26.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1124 | R02105 | Daimler | Daimler | Pre-Comp. | PO | 2021 | 46 | 2021 | 46 | Munteanu Cristian | Carmen B. | Carmen B. | 46 | 46 | Done
| New | 27.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 1128 | R02106 | BMW CVC LOW | CVC LOW | Pre-Comp. |  | 2021 | 47 | 2021 | 47 | Stuparu Catalin | Carmen B. | Radu G. | 47 | 47 | Done
| New | 28.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 1130 | R02108 | OSC12 | OSC12 | dPV | PO | 2022 | 19 | 2022 | 29 | Salcianu Mihai | Carmen B. | TBD. | TBD | TBD | Canceled
| New | 29.10.2021 | Non-Continental | External-OSRAM |  | N.A | 1131 | R02109 | VolvoHCM | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\OSRAM\VNI-CCN\ECU\Volvo-Geely\01_Volvo_HCM\03_R02109_Requalification (SBZ) | dPV | PO | 2022 | 8 | 2022 | 13 | Adina Zaharov | Oana L. | Radu I. | 8 | 14 | Done
| New | 29.10.2021 | Non-Continental | External-OSRAM |  | N.A | 1132 | R02110 | VolvoHCM | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\OSRAM\VNI-CCN\ECU\Volvo-Geely\01_Volvo_HCM\04_R02110_Requalification (SBZ) | dPV | PO | 2022 | 27 | 2022 | 28 | Adina Zaharov | Oana L. | TBD. | TBD | TBD | Next
| New | 05.11.2021 | Continental-Internal | Continental-SBZ (Plant) |  | ADAS |  | R02111 | SVC220 Daimler | C:\Users\balanc\OneDrive - Continental AG\Projects data\04_Project_Divisions\AMS-ADAS\CAMERA\Daimler\01_SVC220\03_R02111_SVC220_pre-compliance(SBZ) | Pre-Comp. | ESign | 2021 | 45 | 2021 | 45 | Buteata Andrei | Carmen B. | Carmen B. | 45 | 45 | Done
| Received | 05.11.2021 | Continental-Internal | Continental-ING |  | VED |  | R02112 | ChangAn_EPA2_HBE | https://continental.sharepoint.com/teams/cs_11010264/Projects%20data/Forms/AllItems.aspx?RootFolder=%2Fteams%2Fcs%5F11010264%2FProjects%20data%2F04%5FProject%5FDivisions%2FAMS%2DVED%2FChangAn%2F01%5FEPA2%20MK100%20HBE%2F04%5FR02112%5FPre%2Dcompliance%5FInsulation%26Dielectric%20tests%28SBZ%29&FolderCTID=0x01200070D1D7DF295EBC45887D7E6D0C83A766 | Pre-Comp. | DSIN | 2021 | 49 | 2021 | 49 | Dallmeir Wolfgang | Anca M. | Dan V. | TBD | TBD | Done
| Received | 05.11.2022 | Continental-Internal | Continental-ING |  | VED |  | R02113 | Roewe_Architecture | https://continental.sharepoint.com/teams/cs_11010264/Projects%20data/Forms/AllItems.aspx?RootFolder=%2Fteams%2Fcs%5F11010264%2FProjects%20data%2F04%5FProject%5FDivisions%2FAMS%2DVED%2FRoewe%2F01%5FRoewe%5FArhitecture%2F03%5FR02113%5FPre%2Dcompliance%5FInsulation%26Dielectric%28SBZ%29&FolderCTID=0x01200070D1D7DF295EBC45887D7E6D0C83A766 | Pre-Comp. | DSIN | 2021 | 49 | 2021 | 49 | Dallmeir Wolfgang | Anca M. | Dan V. | TBD | TBD | Done
| Received | 10.11.2021 | Continental-Internal | Continental-TSR |  | SAM-PSS |  | R02114 | Honda gSAT delta Product Validation | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-PSS/SAT/Honda/03_SAT_HONDA_HRS8_gSAT/03_R02114_dPV_compound%20endurance(SBZ)?csf=1&web=1&e=YNI3q0 | dPV | PO | 2022 | 4 | 2022 | 7 | Nania Chariss | Anca M. | Tibi B. | 5 | 7 | Done
| Received | 11.11.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED |  | R02115 | Mk100 Staking Validation_Panasonic Cl 2.0 Resin shortage | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/AMS-VED/Cairs/Panasonic?csf=1&web=1&e=z9Jyzl | Pre-Comp. | PO | 2021 | 47 | 2021 | 50 | Tudor Bozan | Anca M. | Tibi B. | 47 | 1 | Done
| Received | 15.11.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED |  | R02116 | Ford CD4.2 MCR | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/AMS-VED/Electronic_Brake_System/Ford?csf=1&web=1&e=IgsFwk | Pre-Comp. | DSIN | 2021 | 46 | 2021 | 46 | Vornicu Iulian | Anca M. | Gabriel V. | 46 | 46 | Done
| Received | 16.11.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02117 | VW_MQB19_GW_High | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/he%5Ba%5Dt-CE/Gateway/VW/MQB/HIGH/03_R02117_QUALIFICATION_VW_MQB19_GW(SBZ)?csf=1&web=1&e=ShiPcg | dPV | Dsin | 2022 | 11 | 2022 | 31 | Cojocariu Costel | Roxana M. | Iulia T. | 12 | TBD | Ongoing
| New | 16.11.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02118 | VW_MQB19_GW_Low | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/he%5Ba%5Dt-CE/Gateway/VW/MQB/LOW/04_R02118_ReQUALIFICATION_VW_MQB19_GW(SBZ)?csf=1&web=1&e=LSXZdY | dPV | PO | 2022 | 9 | 2022 | 17 | Cojocariu Costel | Anca M. | Iulia T. | TBD | TBD | Canceled
| New | 16.11.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI |  | R02119 | EZS PAG BASIS | ESZ PAG BASIS | Pre-Comp. | eSign | 2021 | 46 | 2021 | 46 | George Mosteanu | Carmen B. | Carmen B. | 46 | 46 | Done
| New | 16.11.2021 | Continental-Internal | Continental-SBZ (Plant) |  | ADAS |  | R02120 | SVC216 TVL | SVC216 TVL | Pre-Comp. | eSign | 2021 | 46 | 2021 | 46 | Bogdan Dobra | Carmen B. | Carmen B. | 46 | 46 | Done
| New | 17.11.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI |  | R02121 | BMW SP21 LIN HSZ | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/AN/ECU/BMW/03_BMW%20SP21%20LIN%20HSZ/03_R02121_REQUALIFICATION?csf=1&web=1&e=8GpEeq | dPV | eSign | 2022 | 4 | 2022 | 8 | Burdulea Ionel | Oana L. | Cosmin R. | 4 | TBD | Done
| New | 17.11.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI |  | R02122 | MPS6 | MPS6 | Pre-Comp. | eSign | 2021 | 47 | 2021 | 47 | Ganea Constantin | Carmen B. | Carmen B. | 47 | 47 | Done
| New | 19.11.2021 | Continental-Internal | Continental-ING |  | AM |  | R02123 | MFC431TA | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/AMS-ADAS/CAMERA/Toyota/01_MFC431TA20/04_R02123_Qualification_DSPComponent%20Shortage%20DDE?csf=1&web=1&e=g9Yvdc | PV | PO | 2022 |  | 2022 | [6 empty] | Canceled
| New | 22.11.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED |  | R02124 | Volvo SPA2 | Volvo SPA2 | Pre-Comp. | DSIN | 2021 | 47 | 2021 | 47 | Nicu Stefanoaia | Carmen B. | Carmen B. | 47 | 47 | Done
| New | 18.11.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 557 | R02125 | JTEK 144P | JTEKT | DV | PO | 2021 | 40 | 2022 | 19 | Slatineanu I. | Carmen B. | Radu G. | 40 | 19 | Done
| New | 25.11.2021 | Continental-Internal |  |  | VNI |  | R02126 | Magna CTS SRM | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/VNI-CE/SUNROOF/Toyota%26FIAT/MAGNA/CTS%20SRM/03_R02126_REQUALIFICATION?csf=1&web=1&e=iH2efm | dPV | PO | 2022 | 17 | 2022 | 24 | Davidescu Madalina | Oana L. | Nick S. | 17 | 25 | Ongoing
| New | 25.11.2021 | Continental-Internal | Continental-SBZ (Plant) |  | ADAS |  | R02127 | SVC216TVL | SVC216 TVL | Pre-Comp. | Esign | 2021 | 49 | 2021 | 49 | Bogdan Dobra | Carmen B. | Carmen B. | 49 | 49 | Done
| New | 26.11.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02128 | AUD_PPE21_SCU | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/VNI-CCN/SUNROOF/VAG_(VW-Audi-Skoda-Porsche-Lamborghini-Bugatti)/02_AUD_PPE21%20(SBZ)/03_R02128_REQUALIFICATION_SCU?csf=1&web=1&e=7e4j7x | dPV |  | 2022 | 51 | 2022 | 52 | Costel Cojocariu | Oana L. | Iulia T. | 50 | 52 | Done
| New | 9.12.2021 | Continental-Internal | Continental-SBZ (Plant) |  | AM |  | R02129 | SVC210 VW | SVC210VW | Pre-Comp. | eSign | 2022 | 50 | 2022 | 50 | Lapadatu Rares | Carmen B. | Carmen B. | 50 | 50 | Canceled
| New | 13.12.2021 | Continental-Internal | Continental-SBZ (Plant) |  | ADAS |  | R02130 | SVC216TVL | SVC216 TVL | Pre-Comp. | e-Sign | 2021 | 50 | 2021 | 50 | Bogdan Dobra | Carmen B. | Carmen B. | 50 | 50 | Done
| New | 13.12.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02131 | JTEKT143x | JTEKT143x | DV |  | 2022 | 31 | 2023 | 4 | Slatineanu Iulian | Carmen B. | Marius B.. |  |  | Canceled
| New | 13.12.2021 | Continental-External |  |  | AM |  | R02132 | RVS2xxGM | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/AMS-ADAS/CAMERA/GM/01_RVS22xGM12/03_R02132_Qualification_PV?csf=1&web=1&e=bAE9Sb | PV | PO | 2022 | 32 | 2022 | 41 | Santiago Miguel | Oana L. | TBD. | TBD | TBD | Next
| New | 14.12.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02133 | SAIC S11L | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/ESS/SAIC/03_R02133_SAIC%20S11L_pre-compliance?csf=1&web=1&e=1aaAEg | DV | PO | 2022 | 8 | 2022 | 9 | Dragos Roman | Roxana M. | Tibi B. | 8 | 9 | Done
| Received | 17.12.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI |  | R02134 | DQ200 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/VNI-CCN/ECU/VAG_(VW-Audi-Skoda-Porsche-Lamborghini-Bugatti)/05_DQ200?csf=1&web=1&e=7au9Kx | Pre-Comp. | eSign | 2022 | 50 | 2022 | 50 | Ovidiu Capatina | Anca M. | Gabriel V. | TBD | TBD | Done
| New |  | Continental-External | External-OSRAM |  |  |  | R02135 | Volvo HCM Re-Design | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/OSRAM/VNI-CCN/ECU/Volvo-Geely/01_Volvo_HCM/05_R02135_Requalification%20(SBZ)?csf=1&web=1&e=2dfPpn | dPV | PO | 2022 | 19 | 2022 | 20 | Adina Zaharov | Oana L. | Radu I. | TBD | TBD | Canceled
| New | 04.01.2022 | Continental-Internal | External-OSRAM |  | AN |  | R02136 | Volvo HCM1 Swing lines Changchun | Volvo HCM1 Swing lines Changchun | dPV | PO | 2022 | 18 | 2022 | 30 | Adina Zaharov | Roxana M. | Radu I. | TBD | TBD | Canceled
| Received | 12.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS | 1110 | R02137 | JTEKT 144P dDV | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-PSS/ECC/Peugeot/JTEKT/05_R02137_JTEKT%20144P(SBZ)?csf=1&web=1&e=CqRmg9 | dDV | PO | 2022 | 23 | 2022 | 39 | Anghel Adrian | Carmen B. | Radu G. | 23 | TBD | Ongoing
| New | 5.01.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02138 | DCC4 | DCC4 | PV |  | 2022 | 38 | 2023 | 1 | Ghise Sorin | Carmen B. | TBD. | TBD. | TBD. | Next
| New | 07.01.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02139 | FCM Baseline | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/he%5Ba%5Dt-CE/Gateway/VW/MQB/Baseline/04_R02139_FCM%20Baseline_PV?csf=1&web=1&e=cinupk | PV | PO | 2022 | 30 | 2022 | 41 | Cojocariu Costel | Anca M. | Cosmin R. | TBD | TBD | Next
| New | 07.01.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02140 | GW Baseline | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/he%5Ba%5Dt-CE/Gateway/VW/MQB/Baseline/05_R02140_GW%20Baseline_PV?csf=1&web=1&e=aMnOfK | PV | PO | 2022 | 32 | 2022 |  | David Cristina | Roxana M. | TBD. |  |  | Next
| Received | 07.01.2021 | Continental-Internal | Continental-ING |  | SAM-VED |  | R02141 | ER100 Chrysler MP MY21 Base Pace 6 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Electronic_Brake_System/Chrysler/04_R02141_ER100%20Chrysler%20MP%20MY21%20Base%20Pace%206_PV?csf=1&web=1&e=ciWaI1 | PV | PO | 2022 | 14 | 2022 | 26 | Stefan Schmailzl | Stefania B. | Catalin S. | 16 | 26 | Done
| New | 7.01.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02142 | Jtekt 144P | Jtekt 144P | PV |  | 2022 | 39 | 2023 | 12 | Anghel Adrian | Carmen B. | TBD. |  |  | Next
| New | 10.01.2021 | Continental-External | External-VITESCO |  |  |  | R02143 |  |  |  |  | 2022 |  | 2022 | [6 empty] | Canceled
| New | 11.01.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02144 | AUD_MQB_21_DCU_DIS | AUD_MQB_21_DCU_DIS: DV | DV | PO | 2022 | 8 | 2022 | 16 | Costin Cristina-Elena | Roxana M. | Iulia T. | 9 | 15 | Done
| Received | 11.01.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02145 | Nissan QX80 Cairs | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Cairs/Nissan/QX80_MY23.75/05_R02145_QUALIFICATION_QX80_PV?csf=1&web=1&e=ihGoni | PV | PO | 2022 | 25 | 2022 | 51 | Radu Bogdan | Stefania B. | Gabriel V. | 25 | TBD | Ongoing
| New | 12.01.2022 | Continental-Internal | Continental-SBZ (Plant) |  | VNI |  | R02146 | MPS6 | MPS6 | Pre-Comp. | eSign | 2022 | 2 | 2022 | 2 | Craciuna Dalia | Carmen B. | Carmen B. | 2 | 2 | Done
| Received | 13.01.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02147 | Volvo VGM | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/he%5Ba%5Dt-CE/Gateway/Volvo/03_R02147_QUALIFICATION_VGM%20dPV?csf=1&web=1&e=JPhrWP | dPV | PO | 2022 | 11 | 2022 | 22 | Tutui Daniel | Roxana M. | Cosmin R. | 11 | 24 | Done
| New | 13.01.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02148 | FCM Baseline CCQ | FCM Baseline CCQ | PV | PO | 2023 | 17 | 2022 |  | David Cristina | Roxana M. | TBD. | TBD. | TBD | Next
| New | 14.12.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02149 | RAM DT CAIRS MY2024 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/AMS-VED/Cairs/Stellantis%20DT/04_R02149_Pre-compliance_RAM%20DT_CAIRS_%20MY2023?csf=1&web=1&e=CdRw3j | Pre-Comp. | DSIN | 2022 | 6 | 2022 | 7 | Dragos Roman | Roxana M. | Tibi B. | 7 | 7 | Done
| Received | 14.01.2021 | Continental-Internal | Continental-ING |  | SAM-VED |  | R02150 | ER100 Nissan L21B High Plus | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Electronic_Brake_System/Nissan/03_R02150_QUALIFICATION_L21B%20High%20Plus_dPV?csf=1&web=1&e=bGTJFu | dPV | PO | 2022 | 16 | 2022 | 29 | Stefan Schmalzl | Stefania B. | Gabriel V. | 16 | TBD | Ongoing
| New | 14.01.2022 | Non-Continental | External-VITESCO |  | VITESCO |  | R02151 | HVE_DCDC_MB_800V_EVA2 | HVE_DCDC_MB_800V_EVA2 | Pre-Comp. | PO | 2022 | 26 | 2022 | 37 | Pricop Florentina | Oana L. | Nicolae S. | TBD | TBD | Next
| New | 17.01.2022 | Non-Continental |  |  |  |  | R02152 | Kendrion_pre-compliance x-ray | Kendrion | Pre-Comp. | PO | 2022 | 3 | 2022 | 3 | Herciu Adrian | Carmen B. | Carmen B. | 3 | 3 | Done
| New | 21.01 | Continental-External | Continental-SBA |  | AM |  | R02153 | RVSGM PV01 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/AMS-ADAS/CAMERA/GM/01_RVS22xGM12/04_R2153_PVmoved%20from%20SCH?csf=1&web=1&e=loE9UU | PV | PO | 2022 | 13 | 2022 | 18 | Santiago Miguel | Oana L. | Cosmin R. | 15 | 20 | Done
| New | 20.01.2022 | Non-Continental |  |  |  |  | R02154 | Kendrion_pre-compliance x-ray | Kendrion | Pre-Comp. | PO | 2022 | 4 | 2022 | 4 | Cosmin Stanciu | Carmen B. | Carmen B. | 5 | 5 | Done
| Received | 25.01.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02155 | SCCU VDP BMW Mid | VDP BMW Mid | dPV |  | 2022 | 7 | 2022 | 8 | Hategan Ion | Carmen B. | Radu G. | 7 | 9 | Done
| Received | 25.01.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02156 | SCCU VDP BMW High | VDP BMW High | dPV | PO | 2022 | 8 | 2022 | 9 | Hategan Ion | Carmen B. | Radu G. | 8 | 10 | Done
| New | 25.01.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02157 | MK100 | MK100 | Pre-Comp. | DSIN | 2022 | 4 | 2022 | 4 | Aurel Neamtu | Carmen B. | Carmen B. | 4 | 4 | Done
| New | 26.01.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02158 | MakeValves | MakeValves | dPV | eSign | 2022 | 5 | 2022 | 6 | Ciobanu Aurelian | Roxana M. | Iulia T. | 5 | 6 | Done
| New | 26.01.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02159 | MakeValves | MakeValves | dPV | sSign | 2022 | 5 | 2022 | 5 | Ciobanu Aurelian | Roxana M. | Iulia T. | TBD. |  | Canceled
| Received | 17.12.2021 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02160 | MKC1 Renault XDD |  | DV | DSIN-069120 | 2022 | 5 | 2022 | 6 | Spatar Alexandru | Anca M. | Dan V. | 5 | TBD | Done
| New | 26.01.2022 | Continental-External | Continental-ING |  | SAM-VED |  | R02161 | ER100 Las Colinas Family Phase 2 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Cairs/Chrysler/02_MK100%20High%20Phase%202%20Family%20Las%20Colinas/03_R02161_QUALIFICATION_PV?csf=1&web=1&e=r9qTIY | PV | PO | 2022 | 40 | 2022 | 52 | Schmailzl S. | Anca M. | TBD. | TBD. | TBD. | Next
| New | 03.02.2022 | Continental-Internal | Continental-SBZ (Plant) |  | AM |  | R02162 | MFC431 | MFC431 | Pre-Comp. | Esign | 2022 | 6 | 2022 | 11 | Puscas Anca | Roxana M. | Radu I. | 5 | 11 | Done
| New | 03.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02163 | BMW IP-Fahren B0 Samples | BMW IP-Fahren B0 Samples | Pre-Comp. |  | 2022 | 35 | 2022 | 2 | Catalin Stuparu | Carmen B. | Marius B.. | TBD | TBD. | Canceled
| New | 07.02.2022 | Continental-Internal | Continental-TSR |  | VNI |  | R02164 | Vol_SPA2_22_TCM_TRM | Vol_SPA2_22_TCM_TRM | Pre-Comp. | PO | 2022 | 19 | 2022 | 23 | Arsene Catalina | Roxana M. | Radu I. | 19 | 22 | Done
| New | 07.02.2022 | Continental-Internal | Continental-TSR |  | VNI |  | R02165 | REN_EZ1_23_IVS_PCU | REN_EZ1_23_IVS_PCU | DV | PO | 2022 | 21 | 2022 | 38 | Davidescu Madalina | Roxana M. | Nick S. | 21 | TBD | Ongoing
| Received | 07.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02166 | VW - Investiation | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Electronic_Brake_System/Volkswagen/03_R02166_QUALIFICATION_Pre-compliance?csf=1&web=1&e=XtEogI | Pre-Comp. | DSIN | 2022 | 6 | 2022 | 6 | Pal Alexandru | Anca M. | Radu I. | 6 | 6 | Done
| New | 08.02.2022 | Continental-Internal | Continental-ING |  | AM |  | R02167 | MFC431TA20 | MFC431TA20 | dPV | PO | 2022 |  | 2022 |  | Sawai Kunihiko | Roxana M. | TBD. | TBD. |  | Canceled
| New | 08.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02168 | AUDI_XXXX_16_PNEU_BK | AUDI_XXXX_16_PNEU_BK | dPV | PO | 2022 | 21 | 2022 | 22 | Cojocariu Costel | Roxana M. | Iulia T. | 20 | 22 | Done
| New | 8.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02169 | CVC LOW | CVC LOW | PV |  | 2022 | 30 | 2023 | 4 | Stuparu Catalin | Carmen B. | Marius B.. |  |  | Next
| New | 9.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02170 | BMW CVC LOW | BMW CVC LOW | Pre-Comp. |  | 2022 | 9 | 2022 | 10 | Catalin Stuparu | Carmen B. | Carmen B. | 9 | 10 | Done
| New | 9.02.2022 | Non-Continental |  |  |  |  | R02171 | Kendrion_pre-compliance x-ray | Kendrion | Pre-Comp. | PO | 2022 | 7 | 2022 | 7 | Silviu Dascalu | Carmen B. | Carmen B. | 7 | 7 | Done
| Received | 10.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02172 | BMW CVC LOW | BMW CVC LOW | Pre-Comp. |  | 2022 | 13 | 2022 | 14 | Catalin Stuparu | Carmen B. | Radu G. | 12 | 14 | Done
| New | 14.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02173 | IP-Fahren B0 Samples | IP-Fahren B0 Samples | DV | PO | 2022 | TBD | 2022 | TBD | Stuparu Catalin | Carmen B. | TBD. | TBD. | TBD. | Canceled
| New | 14.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02174 | IP-Fahren B0 Samples | IP-Fahren B0 Samples | PV | PO | 2022 | TBD | 2022 | TBD | Stuparu Catalin | Carmen B. | TBD. | TBD. | TBD. | Canceled
| New | 14.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02175 | EFP | Dynamic sensor | Pre-Comp. | DSIN | 2022 | TBD | 2022 | TBD | Alexandru Ciocan | Carmen B. | TBD. | TBD | TBD. | Canceled
| New | 15.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02176 | Make Valves dPV85 | Make Valves dPV85 | dPV | PO | 2022 | 10 | 2022 | 16 | Ciobanu Aurelian | Roxana M. | Cosmin R. | 11 | 15 | Done
| New | 15.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02177 | Make Valves dPV86 | Make Valves dPV86 | dPV | PO | 2022 | 16 | 2022 | 21 | Ciobanu Aurelian | Roxana M. | Cosmin R. | 17 | TBD | Done
| New | 15.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02178 | Make Valves dPV88 | Make Valves dPV88 | dPV | PO | 2022 | 27 | 2022 | 32 | Ciobanu Aurelian | Roxana M. | Cosmin R. | TBD | TBD | Next
| New | 15.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02179 | Make Valves dPV84 | Make Valves dPV84 | dPV | PO | 2022 | 17 | 2022 | 50 | Ciobanu Aurelian | Roxana M. | Cosmin R. | 17 | TBD | Ongoing
| New | 15.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02180 | Make Valves dPV32_52_53 | Make Valves dPV32_52_53 | dPV | PO | 2022 | 30 | 2022 | 40 | Ciobanu Aurelian | Roxana M. | TBD. | TBD | TBD | Next
| New | 15.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02181 | Make Valves dDV76 | Make Valves dDV76 | dDV | PO | 2022 | 42 | 2022 | 50 | Ciobanu Aurelian | Roxana M. | TBD. | TBD | TBD | Next
| New | 15.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02182 | Make Valves PV77 | Make Valves PV77 | PV | PO | 2022 | 48 | 2022 | 9 | Ciobanu Aurelian | Roxana M. | TBD. | TBD | TBD | Next
| Received | 16.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02183 | MK100 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Electronic_Brake_System/Generic_Products/04_MK100/03_R02183_QUALIFICATION_Pre-compliance?csf=1&web=1&e=14i0O2 | Pre-Comp. | DSIN | 2022 | 9 | 2022 | 9 | Buta Viorel | Anca M. | Carmen B. | 9 | 9 | Done
| New | 16.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02184 | PSA MFST 5W | PSA MFST 5W | Pre-Comp. | DSIN | 2022 | 8 | 2022 | 8 | Horatiu Vecerdea | Carmen B. | Carmen B. | 8 | 8 | Done
| New | 17.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02185 | AUDI_XXXX_16_PNEU_BK | AUDI_XXXX_16_PNEU_BK | PV | PO | 2022 | 22 | 2022 | 34 | Cojocariu Costel | Roxana M. | Cosmin R. | 22 | TBD | Ongoing
| New | 17.02.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02186 | Make Valves dDV64 | Make Valves dDV64 | dDV | PO | 2022 | 24 | 2022 | 26 | Ciobanu Aurelian | Roxana M. | Iulia T. | 24 | TBD. | Ongoing
| New | 21.02.2022 | Non-Continental | External-VITESCO |  | VITESCO |  | R02187 | 48V DCDC BMW – C3b – 2nd supplier Mosfets | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/VITESCO/VT_HEV/BMW/01_BMW_DCDC/06_R02187_PreCompliance_C3b%20%E2%80%93%202nd%20supplier%20Mosfets?csf=1&web=1&e=jNfSHk | Pre-Comp. | PO TSR | 2022 | 20 | 2022 | 28 | Larion Catalin | Oana L. | Nick S. | 20 | TBD | Ongoing
R02187 | New | 22.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02188 | AUD_PPE_21_SCU | AUD_PPE_21_SCU | dPV | DSIN | 2022 | 15 | 2022 | 27 | Cojocariu Costel | Roxana M. | Iulia T. | 15 | TBD | Ongoing
| New | 23.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02189 | MB_213_D5_PSCM_MJ | MB_213_D5_PSCM_MJ | PV | PO | 2022 | 21 | 2022 | 36 | Ciobanu Aurelian | Roxana M. | Iulia T. | 20 | TBD. | Ongoing
| New | 24.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02190 | DCC4 | DCC4 | dDV 01 | DSIN-070265 | 2022 | 17 | 2022 | 23 | Ghise Sorin | Carmen B. | Radu G. | 14 | 21 | Done
| Received | 24.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02191 | EFP2V2K | EFP2V2K | dPV | PO | 2022 | 10 | 2022 | 10 | Ciocan Alexandru | Carmen B. | Radu G. | 9 | 10 | Done
| New | 24.02.2022 | Continental-External | TBD |  | VNI |  | R02192 | AUD_MQB_21_DCU_DIS | AUD_MQB_21_DCU_DIS | dPV | PO | 2022 | 16 | 2022 | 21 | Costin Cristina-Elena | Roxana M. | Iulia T. | 15 | 21 | Done
| New | 25.02.2022 | Continental-Internal | External-OSRAM |  | VNI |  | R02193 | Volvo HCM1 | Volvo HCM1 | dPV | PO | 2022 | 34 | 2022 | 43 | Adina Zaharov | Roxana M. | TBD. | TBD. | TBD. | Next
| New | 25.02.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02194 | MK100 | MK100 | Pre-Comp. | DSIN | 2022 | 10 | 2022 | 10 | Vonica Lucian | Carmen B. | Carmen B. | 10 | 10 | Done
| Received | 01.03.2022 | Continental-Internal | Continental-ING |  | SAM-VED |  | R02195 | ER100 Mitsubishi 5F00 Base | 03_R02195_QUALIFICATION_Base_PV | PV | PO | 2022 | 28 | 2022 | 48 | Schmailzl S. | Anca M. | Catalin S. | TBD. | TBD. | Next
| Received | 01.03.2022 | Continental-Internal | Continental-ING |  | SAM-VED |  | R02196 | ER100 Mitsubishi 5F00 High | 04_R02196_QUALIFICATION_High_PV | PV | PO | 2022 | 28 | 2022 | 48 | Schmailzl S. | Anca M. | Catalin S. | TBD. | TBD. | Next
| New | 01.03.2022 | Continental-Internal | Continental-ING |  | SAM-VED |  | R02197 | ER100 ChangAn EPA2 HBE | 05_R02197_QUALIFICATION_XX | PV | PO | 2022 | 28 | 2022 | 38 | Schmailzl S. | Anca M. | Catalin S. | TBD. | TBD. | Next
| New | 04.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02198 | Honda MDX CP22 | 03_R02198_Honda_MDX CP22_XX |  |  | 2022 | 25 | 2022 | 36 | Slavu Alexandru | Anca M. | Catalin S. | TBD. | TBD. | Canceled
| Received | 04.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02199 | BASE CP22 |  | Pre-compliance | DSIN | 2022 | 28 | 2022 | 41 | Slavu Alexandru | Anca M. | Catalin S. | TBD. | TBD. | Next
| New | 4.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02200 | CVC LOW | CVC LOW | Pre-Comp. |  | 2022 | TBD | 2022 | TBD | Stuparu Catalin | Carmen B. | TBD. | TBD. | TBD. | On Hold
| New | 07.03.2022 | Continental-Internal | Continental-ING |  | AM |  | R02201 | MFL420, CP03 TA | MFL420, CP03 TA | dPV | PO | 2022 | 20 | 2022 | 34 | Sawai, Kunihiko | Roxana M. | Cosmin R. | 20 | TBD | Ongoing
| New | 08.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02202 | MB_MRA2_20_PNEU_CCC | MB_MRA2_20_PNEU_CCC | dPV | PO | 2022 | 27 | 2022 | 40 | Adelin Flencana | Roxana M. | TBD. | TBD | TBD | Next
| New | 08.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  |  |  | R02203 | MB_213_D5_PSCM_MJ | MB_213_D5_PSCM_MJ | dPV | PO | 2022 | 22 | 2022 | 25 | Vestemean Marius | Roxana M. | Iulia T. | 21 | TBD. | Ongoing
| New | 08.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02204 | MB_213_D5_PSCM_MJ | MB_213_D5_PSCM_MJ | dPV | PO | 2022 | 31 | 2022 | 33 | Vestemean Marius | Roxana M. | TBD. | TBD. | TBD. | Next
| New | 8.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02205 | Cairs | Cairs | Pre-Comp. | DSIN-017199 | 2022 | 10 | 2022 | 10 | Vasi Dumitriu | Carmen B. | Carmen B. | 10 | 10 | Done
| New | 9.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02206 | MK120 | MK120 | Pre-Comp. | DSIN-060262 | 2022 | 11 | 2022 | 11 | Nistor Ioana | Carmen B. | Carmen B. | 11 | 11 | Done
| New | 9.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02207 | KYB PSA | KYB | PV |  | 2022 | TBD | 2022 | TBD | Stuparu Catalin | Carmen B. | TBD. | TBD | TBD | On Hold
| New | 09.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02208 | AUD_MLBE_D5_DCU | AUD_MLBE_D5_DCU | dPV | PO | 2022 | 11 | 2022 | 14 | Costin Cristina-Elena | Roxana M. | Iulia T. | 11 | 14 | Done
| New | 11.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VED |  | R02209 | MiniMAB TVS N289 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Electronic_Brake_System/MiniMAB/02_TVS/03_R02209_MiniMab%20TVS%20N289_dPV?csf=1&web=1&e=ShgWDl | dPV | PO | 2022 | 31 | 2023 | 2 | Schmailzl S. | Anca M. | TBD. | TBD. | TBD. | Next
| New | 28.03.2022 | Continental-Internal | Continental-ING |  | AM |  | R02210 | SVC22XDP | SVC22XDP | dPV | PO | 2022 | 28 | 2022 | 42 | Zeljko Majstoro | Roxana M. | Iulia T. | TBD | TBD | Next
| Received | 14.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02211 | HIGH PHASE 1 2022 (family) - HTHH | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/Cairs/Chrysler/01_MK100%20High%20Phase%201%20Family%20Las%20Colinas/03_R02089_QUALIFICATION_Chrysler%20JT(ID1092)(SBZ)?csf=1&web=1&e=a7mc78 | dPV | PO | 2022 | 15 | 2022 | 21 | Schmailzl S. | Stefania B. | Catalin S. | 15 | 21 | Done
| New | 10.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02212 | KYB PSA | KYB | Pre-Comp. |  | 2022 | TBD | 2022 | TBD | Stuparu Catalin | Carmen B. | TBD. | TBD | TBD | On Hold
| New | 11.03.2022 | Continental-Internal | Continental-SBZ (Plant) |  | AM |  | R02213 | RVS GM | RVS GM | Pre-Comp. | e-Sign | 2022 | 11 | 2022 | 11 | Jaglea Alexandru | Carmen B. | Carmen B. | 11 | 11 | Done
| New | 15.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02214 | MB_213_D5_PSCM_MJ | MB_213_D5_PSCM_MJ | dPV | PO | 2022 | 21 | 2022 | 35 | Vestemean Marius | Roxana M. | TBD. |  |  | Canceled
| New | 15.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02215 | EPCU JAME 143X | EPCU JAME 143X | dDV |  | 2022 | 44 | 2022 | 3 | Anghel A. | Carmen B. | TBD. |  |  | Next
| Received | 16.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02216 | MK120 |  |  | DSIN-083547-1110 | 2022 | 12 | 2022 | 13 | Pal Alexandru | Anca M. | Tibi B. | 14 | 15 | Done
| New | 16.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02217 | MB_167_22_TRAN_FRE_SIP | MB_167_22_TRAN_FRE_SIP | PV | PO | 2022 | 25 | 2022 | 27 | Radac Emanuel | Roxana M. | Cosmin R. | TBD. | TBD. | Next
| New | 16.03.2022 | Continental-External | External-VITESCO |  | VITESCO |  | R02218 |  | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/VITESCO/VT_EC/Ford/01_DKG250%20Gen1/03_R02218_pre-compliance%20(SBZ)?csf=1&web=1&e=fINur3 | Pre-Comp. | PO | 2022 | 30 | 2022 | 43 | Maxim Loredana | Oana L. | TBD. | TBD. | TBD. | Next
| New | 16.03.2022 | Continental-Internal | Continental-SBZ (Plant) |  | VNI |  | R02219 | GBE K-15a | GBE K-15a | Pre-Comp. | eSign | 2022 | 12 | 2022 | 12 | Malau Ovidiu | Roxana M. | Iulia T. | 12 | 12 | Done
| New | 17.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02220 | Daimler MMA | Daimler MMA | Pre-Comp. |  | 2022 |  | 2022 |  | Stuparu Catalin | Carmen B. | TBD. | TBD | TBD | On Hold
| Received | 18.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02221 | QX80 _Media test - Undercoat (bitumen type) chemical | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/SAM-VED/ESS/Nissan/03_R02221_QUALIFICATION_QX80_DV?csf=1&web=1&e=kh6dzm | DV | DSIN | 2022 | 15 | 2022 | 15 | Dragos Roman | Anca M. | Robert T. | 15 | 15 | Done
| New | 21.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02222 | Daimler MMA | Daimler MMA | Pre-Comp. |  | 2022 |  | 2022 |  | Stuparu Catalin |  | TBD. | TBD. | TBD.
| New | 21.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02223 | Daimler MMA | q | Pre-Comp. |  | 2022 |  | 2022 |  | Stuparu Catalin | Carmen B. | TBD. | TBD. | TBD. | On Hold
| New | 21.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  |  |  | R02224 | Nissan | Nissan | PV | PO | 2022 | 24 | 2022 | 28 | Adina Zaharov | Roxana M. | Radu I. | 24 | TBD. | Ongoing
| New | 21.03.2022 | Non-Continental | External-Schaffler |  |  |  | R02225 | Damp Heat Cyclic | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/EXTERNAL/Schaeffler/06_R02224_dampheatcyclic?csf=1&web=1&e=LD6Cjx | Pre-Comp. |  | 2022 | 15 | 2022 |  | Campean Adnrei Florian | Oana L. | TBD. | TBD. | TBD. | Canceled
| New | 21.03.2022 | Non-Continental | External-Schaffler |  |  |  | R02226 | Damp Heat Constant | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/EXTERNAL/Schaeffler/07_R02225_dampheatconstant?csf=1&web=1&e=acPn68 | Pre-Comp. |  | 2022 | 15 | 2022 |  | Campean Adnrei Florian | Oana L. | TBD. | TBD. | TBD. | Canceled
| New | 21.03.2022 | Non-Continental | External-Schaffler |  |  |  | R02227 | High Low Temp Storage | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/EXTERNAL/Schaeffler/08_R02226_highlowstorage?csf=1&web=1&e=4DkeQq | Pre-Comp. |  | 2022 | 15 | 2022 |  | Campean Adnrei Florian | Oana L. | TBD. | TBD. | TBD. | Canceled
| New | 21.03.2022 | Non-Continental | External-Schaffler |  |  |  | R02228 | TS | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/EXTERNAL/Schaeffler/09_R02227_TS?csf=1&web=1&e=ZCLMyt | Pre-Comp. |  | 2022 | 15 | 2022 |  | Campean Adnrei Florian | Oana L. | TBD. | TBD. | TBD. | Canceled
| New | 24.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02229 | KYB PSA | KYB PSA | Pre-Comp. |  | 2022 |  | 2022 |  | Stuparu Catalin | Carmen B. | TBD. |  |  | On Hold
| New | 24.03.2022 | Non-Continental | External-VITESCO |  | VITESCO |  | R02230 | DB35 | DB35 | Pre-Comp. | PO | 2022 | 13 | 2022 | 13 | Tudor Pojar | Carmen B. | Carmen B. | 13 |  | Done
| New | 29.03.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02231 | VW MQB23 GW BSL | VW MQB23 GW BSL | Pre-Comp. | Dsin | 2022 | 13 | 2022 | 13 | David Cristina | Roxana M. | Iulia T. | 13 | 13 | Done
| New | 30.03.2022 | Continental-Internal | Continental-SBZ (Plant) |  | SAM-PSS |  | R02232 | CHCM | CHCM | Pre-Comp. |  | 2022 |  | 2022 |  | Hategan Ion | Carmen B. | TBD. | TBD. | TBD. | On Hold
| New | 12.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02233 | MB_213_D5_PSCM_MJ | MB_213_D5_PSCM_MJ | dPV | PO | 2022 | 39 | 2022 | 40 | Vestemean Marius | Roxana M. | TBD. | TBD. | TBD. | Next
| New |  | Non-Continental | External-Schaffler |  |  |  | R02234 |  |  |  |  | 2022 | 15 | 2022 | 20 | Campean Adnrei Florian | Oana L. | TBD. | TBD. | TBD. | Canceled
| New | 1.04.2022 | Continental-Internal | Continental-BNG |  | SAM-PSS |  | R02235 | EVPRD Honda | EVPRD HONDA | PV | PO | 2022 | 22 | 2022 | 26 | Rohan Kharvi | Carmen B. | Tiberiu B. | TBD. | TBD. | Canceled
| New |  | Non-Continental | External-Schaffler |  |  |  | R02236 |  |  |  |  | 2022 |  | 2022 |  | Campean Adnrei Florian | Oana L. | TBD. | TBD. | TBD. | Next
| New | 05.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02237 | MB_213_D5_PSCM_MJ | MB_213_D5_PSCM_MJ | dPV | PO | 2022 | 41 | 2022 | 42 | Vestemean Marius | Roxana M. | TBD.
| New | 5.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02238 | Cairs | Cairs | Pre-Comp. | DSIN | 2022 | 14 | 2022 | 14 | Lorand Horvath | Carmen B. | Carmen B. | 14 | 14 | Done
| New | 5.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02239 | Geely Lotus | Geely Lotus | Pre-Comp. | DSIN | 2022 | 14 | 2022 | 14 | Nicu Stefanoaia | Carmen B. | Carmen B. | 14 | 14 | Done
| New | 06.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02240 | Thermal shock immersion |  | TBD |  | 2022 | 35 | 2022 | 36 | Cosmin Bratu | Anca M. | TBD. | TBD. | TBD. | Canceled
| New | 06.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02241 | GWM DE30 |  | DV |  | 2022 | 18 | 2022 | 19 | Dragos Roman | Anca M. | Ion C. | TBD. | TBD. | Canceled
| New | 7.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02242 | SCCU SAF BMW K50 |  | Pre-Comp. |  | 2022 |  | 2022 |  | Hategan Ion | Carmen B. | TBD. |  |  | On Hold
| New | 7.04.2022 | Continental-Internal | Continental-SBZ (Plant) |  | SAM-PSS |  | R02243 | SVC22x |  | Pre-Comp. |  | 2022 | 15 | 2022 | 16 | Buteata Marian | Carmen B. | Gabriel V. | 16 | 17 | Done
| New | 8.04.2022 | Continental-Internal | Continental-SBZ (Plant) |  | AM |  | R02244 | FSC23x |  | Pre-Comp. |  | 2022 | 15 | 2022 | 15 | Praporgescu Cristian | Carmen B. | Carmen B. | 15 | 15 | Done
| New | 08.04.2022 | Continental-Internal |  |  | VNI |  | R02245 | AUD_XXXX_16_PNEU_BK |  | dPV | PO | 2022 | 16 | 2022 | 16 | David Cristina | Oana L. |  |  |  | Canceled
| New | 11.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02245 | AUD_XXXX_16_PNEU_BK | AUD_XXXX_16_PNEU_BK | dPV | PO | 2022 | 40 | 2022 | 41 | David Cristina | Roxana M. | TBD. |  |  | Next
| New | 08.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02246 |  |  |  |  | 2022 | 16 | 2022 | 16 | David Cristina | Oana L. |  |  |  | Canceled
| Received | 11.04.2022 | Continental-External | Continental-ING |  | VED | R02089 | R02247 | HIGH PHASE 1 2022 (family)_PV_neutral reports |  | PV | PO | 2021 | 50 | 2022 | 10 | Schmailzl S. | Anca M. | Dan V. |  |  | Done
| Received | 11.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02248 | Sum of Motor Forces |  | PV | DSIN | 2022 | 15 | 2022 | 15 | Tudor Bozan | Anca M. | Daniel I. | 15 | 16 | Done
| New | 13.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02249 | MK100_Broken knob at customer | MK100 | Pre-Comp. | IO | 2022 | 15 | 2022 | 16 | Lazar Sergiu | Oana L. | Daniel I. | 16 | 16 | Done
| New | 14.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02250 | MK100 EVO Upgrade | MK100 EVO Upgrade | Pre-Comp. |  | 2022 | 15 | 2022 | 16 | Vraciu Marina | Oana L. | Ion C. | 15 | 19 | Done
| Received | 13.04.2022 | Continental-External | Continental-ING |  | SAM-VED | R02211 | R02251 | Neutral Reports VED_HIGH PHASE 1 2022 (family)_dPV |  | dPV | PO | 2022 | 15 | 2022 | 21 | Schmailzl S. | Anca M. | Catalin S. | 15 | 21 | Done
| Received | 13.04.2022 | Continental-External | Continental-ING |  | SAM-VED | R02099 | R02252 | Neutral Reports VED_ER100 Honda 30AA MY23 ESC Base IPB |  | PV | PO | 2022 | 11 | 2022 | 24 | Schmailzl S. | Stefania B. | Catalin S. | 11 | 24 | Done
| Received | 13.04.2022 | Continental-External | Continental-ING |  | SAM-VED | R02066 | R02253 | Neutral Reports VED_BMW_CAirS_CB1_MY18 - Pulse cube |  | PV | eSign | 2022 | 9 | 2022 | 27 | Schmailzl S. | Anca M. | Gabriel V. | 10 | TBD | Ongoing
| Received | 13.04.2022 | Continental-External | Continental-ING |  | VED | R02067 | R02254 | Neutral Reports VED_RAM_DT_CAirS_CK1_MY21 |  | PV | PO | 2021 | 49 | 2021 | 23 | Schmailzl S. | Anca M. | Dan V. | 50 | 15 | Done
| Received | 13.04.2022 | Continental-External | Continental-ING |  | SAM-VED | R02068 | R02255 | Neutral Reports VED_Mercedes Benz CAirS eSPC_BR223 |  | PV | PO | 2022 | 49 | 2022 | 28 | Schmailzl S. | Anca M. | Dan V. | 50 | TBD | Ongoing
| Received | 13.04.2022 | Continental-External | Continental-ING |  | SAM-VED | R02069 | R02256 | Neutral Reports VED_Mercedes Benz CAirS eSPC_BR254 |  | PV | PO | 2022 | 49 | 2022 | 28 | Schmailzl S. | Anca M. | Dan V. | 50 | TBD | Ongoing
| Received | 13.04.2022 | Continental-External | Continental-ING |  | SAM-VED | R02141 | R02257 | Neutral Reports VED_ER100 Chrysler MP MY21 Base Pace6_PV |  | PV | PO | 2022 | 14 | 2022 | 26 | Stefan Schmailzl | Anca M. | Catalin S. | 16 | 26 | Done
| Received | 13.04.2022 | Continental-External | Continental-ING |  | SAM-VED | R02145 | R02258 | Neutral Reports VED_CAirs_Nissan QX80 |  | PV | PO | 2022 | 25 | 2022 | 51 | Schmailzl S. | Stefania B. | Gabriel V. | 25 | TBD | Ongoing
| New | 14.04.2022 | Continental-Internal | Continental-SBZ (Plant) |  | VNI |  | R02259 | DQ200 TCU |  | Pre-Comp. | eSign | 2022 | 18 | 2022 | 19 | Horia Enciu | Carmen B. | Ion C. | 18 | 18 | Done
| Received | 13.04.2022 | Continental-Internal | Continental-SBZ (Plant) |  | VNI |  | R02260 | Ramses |  | Pre-Comp. | DSIN | 2022 | 15 | 2022 | 15 | Flaviu Musat | Carmen B. | Carmen B. | 15 | 15 | Done
| Received | 13.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02261 | REN EZ1 PCU | REN EZ1 PCU | Pre-Comp. |  | 2022 | 16 | 2022 | 16 | Ionica Alexandru | Carmen B. | Carmen B. | 16 | 16 | Done
| New | 18.04.2022 | Continental-Internal | Continental-ING |  | AM |  | R02262 | SRR320MA20 | SRR320MA20 | dPV | PO | 2022 | 31 | 2022 | 50 | Sawai Kunihiko | Roxana M. | TBD. |  |  | Next
| New | 18.04.2022 | Continental-Internal | Continental-ING |  | AM |  | R02263 | SRR320MA20 | SRR320MA20 | dPV | PO | 2022 |  | 2022 |  | Sawai Kunihiko | Roxana M. | TBD. |  |  | Canceled
| Received | 18.04.2022 | Continental-Internal | Continental-ING |  | SAM-VED | R02150 | R02264 | Neutral reports -ER100Nissan =L21B High Plus | Neutral reports -ER100Nissan =L21B High Plus | dPV | PO | 2022 | 16 | 2022 | 29 | Stefan Schmalzl | Stefania B. | Gabriel V. | 16 | TBD | Ongoing
| Received | 18.02.2022 | Continental-Internal | Continental-SBZ (Plant) |  | VNI |  | R02265 | MPS6 | MPS6 | Pre-Comp. | 16 | 2022 | 16 | 2022 | 16 | Craciuna Dalia | Carmen B. | Carmen B. | 16 | 16 | Done
| New | 19.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02266 | Daimler MMA EE | Daimler MMA EE | Pre-Comp. |  | 2022 | 29 | 2023 | 43 | Ciocan Alexandru | Carmen B. | Marius B.. |  |  | Next
| Received | 20.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02267 | ESS_D4_Standardization_SYS_ASU (push-pull) |  | Pre-Comp. |  | 2022 | 20 | 2022 | 20 | Lorand Horvath | Carmen B. | Daniel I. | TBD. | TBD. | Canceled
| Received | 20.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02268 | MK C1-FCA |  | Pre-Comp. | DSIN | 2022 | 16 | 2022 | 16 | Lazar Sergiu | Carmen B. | Carmen B. | 16 | 16 | Done
| New | 27.04.2022 | [5 empty] | R02269 |  |  |  |  | 2022 |  | 2022 |  |  | Oana L. |  | TBD | TBD | Next
| Received | 29.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02270 | ER120 Hyundai SX2 |  | PV | PO | 2022 | 28 | 2022 | 40 | Schmailzl S. | Stefania B. | Gabriel V. | TBD | TBD | Next
| Received | 02.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02271 | Hyundai_B-MPV_MK 100_ESC_MY22.00_Base_KS |  | Pre-Comp. | DSIN | 2022 | 18 | 2022 | 19 | Acatrinei Alina | Stefania B. | Daniel I. | 17 | 20 | Done
| New | 16.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02272 | BMW_35UP_SCU_MYC | BMW_35UP_SCU_MYC | dPV | esign | 2022 | 20 | 2022 | 23 | Vasile Maria Adina | Roxana M. | Iulia T. | 20 | 23 | Done
| New | 2.05.2022 | Continental-External | Continental-TSR |  | AM |  | R02273 | FSC33x |  | Pre-Comp. |  | 2022 | 21 | 2022 | 22 | Plostinaru Roxana | Carmen B. | Carmen B. | 21 | 22 | Done
| Received | 2.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  |  |  | R02274 | MkC2 HAD |  | Pre-Comp. |  | 2022 | 18 | 2022 | 18 | Secu Mihaita | Carmen B. | Carmen B. | 18 | 18 | Done
| New | 5.05.2022 | Continental-Internal | Continental-SBZ (Plant) |  |  |  | R02275 | DQ200 Gen 2 x-ray |  |  | eSign | 2022 | 18 | 2022 | 18 | Marius Maracine | Carmen B. | Carmen B. | 18 | 18 | Canceled
| New | 09.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  |  |  | R02276 |  |  |  |  | 2022 |  | 2023 |  | Vestemean Marius | Roxana M. | TBD. |  |  | Next
| New | 09.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  |  |  | R02277 |  |  |  |  | 2022 |  | 2022 |  | Vestemean Marius | Roxana M. | TBD. |  |  | Next
| New | 06.05.2022 | Continental-Internal | Continental-ING |  | SAM-VED |  | R02278 | Hero_MiniMAB_ABS_MY18.25_ABWB |  | DV | PO | 2022 | 28 | 2022 | 36 | Popescu Claudiu | Stefania B. | Catalin S. | TBD. | TBD. | Next
| New | 06.05.2022 | Continental-Internal | Continental-ING |  | VED |  | R02279 | Neutral Reports MK100_MAB w. new Q-RESON series CSTNE-V-C / new Back-end line |  | PV | DSIN | 2022 | 48 | 2023 | 10 | Popescu Claudiu | Stefania B. | TBD. |  |  | Next
| Received | 9.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02280 | Dryer |  |  | DSIN | 2022 | 19 | 2022 | 19 | Vasi Dumitriu | Carmen B. | Carmen B. | 19 | 19 | Done
| Received | 9.05.2022 | Continental-Internal | Continental-SBZ (Plant) |  | VNI |  | R02282 | DQ200 T-Shock |  | Pre-Comp. | ESign | 2022 | 21 | 2022 | 23 | Capatana Ovidiu | Carmen B. | Radu I. | 21 | 24 | Done
| Received | 9.05.2022 | Non-Continental | External-VITESCO |  | VITESCO |  | R02283 | HTS 8AT Aqxxx |  | Pre-Comp. | PO | 2022 | 26 | 2022 | 26 | Tudor Pojar | Carmen B. | Carmen B. | 20 | 20 | Done
| New | 09.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  |  |  | R02284 |  |  |  |  | 2022 |  | 2022 |  | Vestemean Marius | Roxana M. | TBD. |  |  | Next
| New | 09.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  |  |  | R02285 |  |  |  |  | 2022 |  | 2022 |  | Vestemean Marius | Roxana M. | TBD. |  |  | Next
| New | 10.05.2022 | Continental-External | Continental-TSR |  | AM |  | R02286 | SVC225 |  | Pre-Comp. |  | 2022 | 21 | 2022 | 22 | Plostinaru Roxana | Carmen B. | Carmen B. | 21 | 22 | Done
| Received | 10.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED | R02070 | R02287 | Neutral Reports for ER100 PSA CMP ECO MY23.50_IPB High |  | PV | PO | 2022 | 19 | 2022 | 34 | Dallmeir Wolfgang | Stefania B. | Gabriel V. | 19 | TBD | Ongoing
| Received | 10.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED | R02071 | R02288 | Neutral Reports for ER100 PSA CMP ECO MY23.50_IPB Base |  | PV | PO | 2022 | 19 | 2022 | 34 | Dallmeir Wolfgang | Stefania B. | Gabriel V. | 19 | TBD | Ongoing
| Received | 10.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED | R02072 | R02289 | Neutral Reports for ER100 PSA CMP ECO MY23.50_ESC Base |  | PV | PO | 2022 | 19 | 2022 | 34 | Dallmeir Wolfgang | Stefania B. | Gabriel V. | 19 | TBD | Ongoing
| New | 11.05.2022 | Continental-Internal | Continental-SBZ (Plant) |  | VNI |  | R02290 | REN_EZ1_23_IVS_PCU |  | Pre-Comp. | PO | 2022 | 21 | 2022 | 21 | Davidescu Madalina | Roxana M. | Nicolae S. | 21 | 21 | Done
| Received | 12.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02291 | Hyundai_B-MPV_MK 100_ESC_MY22.00_Base_KS |  | Pre-Comp. |  | 2022 | 21 | 2022 | 22 | Acatrinei Alina | Stefania B. | Ion C. | 20 | 22 | Done
| New | 13.05.2022 | [5 empty] | R02292
| Received | 13.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02293 | B-MPV_MK 100_ESC_MY22.00_Base_KS with SunC |  | dPV | PO | 2022 | 21 | 2022 | 31 | Acatrinei Alina | Stefania B. | Catalin S. | 21 | TBD. | Ongoing
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02294 | EFP 3k+ |  | dPV 04 |  | 2023 | 2 | 2023 | 4 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02295 | SPCh |  | dPV 05 |  | 2023 | 5 | 2023 | 8 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02296 | emARS |  | dPV 10 |  | 2023 | 8 | 2023 | 11 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02297 | VDP MID (1) |  | dPV 02 |  | 2023 | 10 | 2023 | 14 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02298 | CCU37 |  | dPV 04 |  | 2023 | 36 | 2023 | 51 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
44 | New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02299 | SPC+ |  | dPV 09 |  | 2023 | 43 | 2023 | 46 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02300 | DCC3 |  | dPV 04 |  | 2023 | 16 | 2023 | 17 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02301 | VDP LOW |  | dPV 08 |  | 2023 | 18 | 2023 | 22 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02302 | EFP 2.0 |  | dPV 08 |  | 2023 | 40 | 2023 | 43 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02303 | CHCM |  | dPV 06 |  | 2023 | 42 | 2023 | 44 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02304 | SAF |  | dPV11 |  | 2023 | 25 | 2023 | 36 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02305 | SSD |  | dPV 06 |  | 2023 | 27 | 2023 | 29 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02306 | OSC12 |  | dPV 02 |  | 2023 | 28 | 2023 | 36 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02307 | VDP HIGH |  | dPV 06 |  | 2023 | 30 | 2023 | 34 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02308 | EFP 3k |  | dPV 03 |  | 2023 | 32 | 2023 | 37 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02309 | SCCM |  | dPV 06 |  | 2023 | 35 | 2023 | 37 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02310 | VASCO |  | dPV 02 |  | 2023 | 11 | 2023 | 14 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02311 | EFP 1.3 |  | dPV 06 |  | 2023 | 38 | 2023 | 42 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02312 | VDP MID |  | dPV 06 |  | 2023 | 21 | 2023 | 24 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02313 | SAS |  | dPV 03 |  | 2023 | 24 | 2023 | 29 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02314 | AMR |  | dPV 05 |  | 2023 | 14 | 2023 | 17 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02315 | VADA |  | dPV 04 |  | 2023 | 45 | 2023 | 49 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02316 | EHNR |  | dPV 06 |  | 2023 | 48 | 2023 | 50 | Hategan Ion | Carmen B. | TBD. | TBD | TBD | Next
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02317 | BMW GBE | BMW GBE |  | eSign | 2022 | 21 | 2022 | 21 | Popa Roxana | Roxana M. | Radu I. | 22 | 22 | Done
| New | 17.05.2022 | Continental-Internal | Continental-SBZ (R&D) | Continental-ING | SAM-VED | R02278 | R02318 | Neutral reports Hero_MiniMAB_ABS_MY18.25_ABWB |  | DV | PO | 2022 | 28 | 2022 | 36 | Popescu Claudiu | Stefania B. | TBD. | TBD. | TBD. | Next
| Received | 19.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02319 | ESS D5 Cairs |  | Pre-Comp. | DSIN | 2022 | 20 | 2022 | 20 | Gheorghe Urian | Carmen B. | Daniel I. | 20 | 20 | Done
| Received | 19.05.2022 | Continental-Internal | Continental-SBZ (Plant) |  | VNI |  | R02320 | FacEasy PCU |  | Pre-Comp. | DSIN | 2022 | 20 | 2022 | 20 | Flaviu Musat | Carmen B. | Carmen B. | 20 | 20 | Done
| Received | 19.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02321 | Daimler BR167 |  | Pre-Comp. | DSIN | 2022 | 20 | 2022 | 20 | Vasi Dumitriu | Carmen B. | Daniel I. | 20 | 20 | Done
| Received | 24.05.2022 | Continental-Internal | Continental-SBZ (Plant) |  | SAM-PSS |  | R02322 | SPCh |  | dPV | PO | 2022 | 26 | 2022 | 27 | Hategan Ion | Carmen B. | Marius B.. | TBD | TBD | Next
| Received | 24.05.2022 | Continental-Internal | Continental-SBZ (Plant) |  | SAM-PSS |  | R02323 | SAF |  | dPV | PO | 2022 | 25 | 2022 | 26 | Hategan Ion | Carmen B. | Marius B.. | 25 | TBD | Ongoing
| Received | 25.05.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02324 | ER120mP |  | Pre-Comp. | DSIN-060262 | 2022 | 21 | 2022 | 21 | Nistor Ioana | Carmen B. | Carmen B. | 21 | 21 | Done
| New | 20.05.2022 | Continental-Internal | Continental-ING |  | SAM-VED |  | R02325 | New MK120 ECU/HCU gasket (no report needed) |  | Pre-Comp. | DSIN | 2022 | 27 | 2022 | 29 | Spatar Alexandru | Stefania B. | Catalin S. | TBD | TBD | Next
| New | 26.05.2022 | Continental-Internal | Continental-TSR |  | VNI |  | R02326 | DCU SP 21 BMW | DCU SP 21 BMW | dPV | PO | 2022 | 25 | 2022 | 27 | Silvana Popovici | Roxana M. | Iulia T. | TBD. | TBD. | Next
| Received | 30.05.2022 | Continental-Internal | Continental-SBZ (Plant) |  | AM |  | R02327 | SVC220 |  | Pre-Comp. | eSign | 2022 | 24 | 2022 | 26 | Buteata Andrei | Carmen B. | Cosmin R. | 24 | TBD. | Ongoing
| New | 02.06.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02328 | CHCM |  | dPV |  | 2022 | 30 | 2022 | 32 | Ion Hategan | Carmen B. | Marius B.. |  |  | Canceled
| Received | 08.06.2022 |  |  |  | SAM-VED |  | R02329 | CAirS |  | dPV | PO | 2022 | 26 | 2022 | 27 | Radu Bogdan | Stefania B. | Catalin S. | 26 | TBD | Ongoing
| Received | 08.06.2022 |  |  |  | SAM-VED |  | R02330 | MiniMAB |  | Pre-Comp. | DSIN-085726 | 2022 | 23 | 2022 | 24 | Rotaru Vlad | Stefania B. | Gabriel V. | 23 | 24 | Done
| Received | 10.06.2022 |  |  |  | SAM-VED |  | R02331 | MK100 Panasonic CRP Light |  | Pre-Comp. | DSIN-075616 | 2022 | 25 | 2022 | 29 | Tudor Bozan | Stefania B. | Catalin S. | 25 | TBD | Ongoing
| New | 14.06.2022 |  |  |  | SAM-VED |  | R02332 | FLS3.2 |  | dPV |  | 2022 | 33 | 2022 | 41 | Stefan Schmailzl | Stefania B. | TBD. | TBD. | TBD. | Next
| Received | 14.06.2022 |  |  |  | VNI |  | R02333 | VW_TVL |  | Pre-Comp. | eSign | 2022 | 27 | 2022 | 27 | Lupoiu Madalina | Carmen B. | Carmen B. | 24 | 24 | Done
| New | 14.06.2022 |  |  |  | SAM-VED |  | R02334 | 2nd source Eldor XT-Coils |  | dPV | PO | 2022 | 33 | 2022 | 44 | Stefan Schmailzl | Stefania B. | TBD. | TBD. | TBD. | Next
| New | 15.06.2022 | [5 empty] | R02335 | MFC431TA20 | MFC431TA20 | dPV | PO | 2022 | 31 | 2022 | 40 | Sawai Kunihiko | Roxana M. | TBD. |  |  | Next
| New | 15.06.2022 |  |  |  | VNI |  | R02336 | M50 CCU | M50 CCU | dPV |  | 2022 | 29 | 2022 | 33 | Davidescu Madalina | Roxana M. | TBD. |  |  | Next
| New | 16.06.2022 |  | Continental-ING |  | SAM-VED |  | R02337 | INA201 industry grade |  | dPV | PO | 2022 | 31 | 2022 | 41 | Andreas Goetz | Stefania B. | TBD. | TBD | TBD | Next
| New | 16.06.2022 |  | Continental-ING |  | SAM-VED |  | R02338 | INA200 automotive grade with HW change to Shunt of 10mOhm |  | dPV | PO | 2022 | 31 | 2022 | 41 | Andreas Goetz | Stefania B. | TBD. | TBD | TBD | Next
| Received | 17.06.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R02339 | I CMV |  | dPV |  | 2022 | 27 | 2022 | 27 | Bardasu Mihail | Carmen B. | Marius B.. |  |  | Next
| Received | 20.06.2022 | Continental-Internal | Continental-ING |  | VED | R02073 | R02340 | Neutral reports Nissan_QX80_CAirS_MY23.75 |  | DV |  | 2021 | 44 | 2022 | 28 | Andreas Goetz | Stefania B. | Dan V. | 45 | TBD | Ongoing
| Received | 21.06.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02341 | CAG_XXX_D5_PNEU |  | Pre-Comp. |  | 2022 | 25 | 2022 | 26 | Aurelian Ciobanu | Carmen B. | Carmen B. | 25 | 26 | Done
| Received | 21.06.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02342 | Minimab |  | Pre-Comp. | DSIN | 2022 | 25 | 2022 | 25 | Secu Mihaita | Carmen B. | Carmen B. | 25 | 25 | Done
| New | 21.06.2022 | Continental-Internal | Continental-ING |  | VED |  | R02343 | CAirS CB1 BMW DPAK shortage |  | PV | PO | 2022 | TBD. | TBD. | TBD. | Andreas Goetz | Stefania B. | TBD. | TBD. | TBD. | On Hold
| New | 21.06.2022 | Continental-Internal | Continental-ING |  | SAM-VED | R02150 | R02344 | Neutral reports ER100 Nissan L21B High Plus |  | dPV | PO | 2022 | 16 | 2022 | 29 | Stefan Schmalzl | Stefania B. | Gabriel V. | 16 | TBD | Canceled
| Received | 22.06.2022 | Continental-Internal | Continental-ING |  | SAM-VED |  | R02345 | Neutral reports ER100 Mitsubishi 5F00 Base |  | PV | PO | 2022 | 28 | 2022 | 48 | Schmailzl S. | Stefania B. | Catalin S. | TBD. | TBD. | Next
| Received | 22.06.2022 | Continental-Internal | Continental-ING |  | SAM-VED |  | R02346 | Neutral reports ER100 Mitsubishi 5F00 High |  | PV | PO | 2022 | 28 | 2022 | 48 | Schmailzl S. | Stefania B. | Catalin S. | TBD. | TBD. | Next
| New | 23.06.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02347 | VW MQB19 FCM |  | dPV | PO | 2022 | 27 | 2022 | 28 | David Cristina | Roxana M. | TBD. |  |  | Next
| New | 21.06.2022 | Continental-Internal | Continental-ING |  | SAM-VED |  | R02348 | RAM_DT_CAirS_CK1_MY21 |  | PV | PO | 2022 | 29 | 2022 | 36 | Radu Bogdan | Stefania B. | Catalin S. | TBD. | TBD. | Next
| New | 21.06.2022 | Continental-Internal | Continental-ING |  | SAM-VED | R02348 | R02349 | Neutral reports RAM_DT_CAirS_CK1_MY21 |  | PV | PO | 2022 | 29 | 2022 | 36 | Radu Bogdan | Stefania B. | TBD. | TBD. | TBD. | Next
| New | 24.06.2022 | Continental-Internal | Continental-ING |  | AM |  | R02350 |  |  |  |  | 2022 |  | 2022 |  | Zeljko Majstoro | Roxana M. | TBD. |  |  | Next
| New | 24.06.2022 | Continental-Internal | Continental-ING |  | AM |  | R02351 |  |  |  |  | 2022 |  | 2022 |  | Zeljko Majstoro | Roxana M. | TBD. |  |  | Next
| New | 27.06.2022 | Continental-Internal | Continental-SBZ (Plant) |  | VNI |  | R02352 | BMW GBE |  | PV | PO | 2022 |  | 2022 |  | Popa Roxana | Roxana M. |  |  |  | Next
| New | 29.06.2022 | Continental-External | Continental-ING |  | VED |  | R02353 | FLS3.3 |  | PV | PO | 2022 | TBD. | TBD. | TBD. | Stefan Schmailzl | Stefania B. | TBD. | TBD. | TBD. | Next
| New | 30.06.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02354 | VOLVO RE-DESIGN |  | dPV | PO | 2022 | CW36 | 2022 | CW38 | Adina Zaharov | Maracine R. | TBD. |  |  | Next
| New | 30.06.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VED |  | R02355 | Nissan_L21B_MK 100_ESC_6XI_MY19_Base_(NMEX for US,CAN) |  | PV | PO | 2023 | 2 | 2023 | TBD. | Acatrinei Alina | Stefania B. | TBD. | TBD. | TBD. | Next
| New | 1.07.2022 | Continental-Internal | Continental-TSR |  | SAM-PSS |  | R02356 | ACU_RNM_C1AHS_EVO2_MY24_S40 |  | Pre-Comp. | PO | 2022 |  | 2022 |  | Marian Patricia | Carmen B. | Carmen B. |  |  | Next
| New | 01.07.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02357 | DE30 |  | DV | DSIN-078683 | 2022 | 36 | 2022 | 37 | Roman Dragos | Stefania B. | TBD. | TBD | TBD | Next
| New | 04.07.2022 | Continental-Internal | Continental-SBZ (R&D) |  |  |  | R02358
| New | 04.07.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-VED |  | R02359 | Renault ESC |  | Pre-Comp. | NA | 2022 | 27 | 2022 | 27 | Spatar Alexandru | Stefania B. | Catalin S. | TBD | TBD | Next
| New | 04.07.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02360 | MQB19 GW LOW |  | Pre-Comp. | NA | 2022 | 27 | 2022 | 27 | Cojocariu Costel | Roxana M. | Iulia T. | TBD | TBD | Next
| New | 04.07.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02361 | MQB19 GW FCM |  | Pre-Comp. | NA | 2022 | 27 | 2022 | 27 | Cojocariu Costel | Roxana M. | Nick S. | TBD | TBD | Next
| New | 04.07.2022 | Continental-Internal | Continental-SBZ (R&D) | Renault | SAM-VED |  | R02362 | EXT_AUD_REN_IPX9K |  | Pre-Comp. | NA | 2022 | 27 | 2022 | 27 | Andrei Cimpean | Stefania B. | Dan V. | TBD | TBD | Next
| Received | 04.07.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02363 | MQB19 GW LOW |  | Pre-Comp. | NA | 2022 | 27 | 2022 | 27 | Cojocariu Costel | Maracine R. | Radu G. | 27 | 27 | Done
| New | 04.07.2022 | Continental-Internal | Continental-SBZ (R&D) |  |  |  | R02364 |  |  |  | NA | [6 empty] | Nick S. | TBD | TBD | Next
| New | 30.06.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VED | R02355 | R02365 | Neutral reports Nissan_L21B_MK 100_ESC_6XI_MY19_Base_(NMEX for US,CAN) |  | PV | PO | 2023 | 2 | 2023 | TBD. | Acatrinei Alina | Stefania B. | TBD. | TBD. | TBD. | Next
| Received | 04.07.2023 | Continental-Internal | Continental-SBZ (R&D) | GM | AM |  | R02366 | RVS22xGM12 2.1MP |  | Pre-Comp. | NA | 2022 | 21 | 2022 | 21 | Dayana Montenegro | Stefania B. | Dan V. | 21 | 21 | Done
| New | 04.07.2022 | Continental-Internal | Continental-SBZ (R&D) |  |  |  | R02367 | BMW_SP21_22_OTHR_PDM |  | Pre-Comp. | NA | 2022 | 1 | 2022 | 1 |  | Roxana M. | Iulia T. | TBD | TBD | Next
| New | 5.07.2022 | Continental-Internal | Continental-SBZ (R&D) |  | PSS |  | R02368 | KHAT |  | PV | PO | 2023 |  | 2023 |  | Ghise Sorin | Carmen B. |  |  |  | On Hold
| Received | 27.04.2022 | Continental-Internal | Continental-SBZ (R&D) |  | VNI |  | R02369 | Volvo VGM |  | Pre-Comp. | DSIN | 2022 | 18 | 2022 | 18 | Tutui Daniel | Roxana M. | Catalin S. | 18 | 18 | Done
| Received | 08.11.2021 | Continental-Internal | Continental-TSR |  | HMI | 1136 | R03308 | KTM_PJ617 | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/VNI-CVS/INSTRUMENT%20CLUSTER/KTM/01_KTM_PJ617/05_R03308_PV_ReQualification%20(2021)?csf=1&web=1&e=YSW2zq |  |  | 2021 | 50 | 2021 | 50 | Dragoi Emilia | Oana L. | Radu G. | 49 | 51 | Done
| Received | 02.12.2021 | Continental-Internal | Continental-TSR |  | he[a]t-CES |  | R03318 | TOGG_CGU - VIB test | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/he%5Ba%5Dt-CES/TOGG/01_TOGG_CGU/02_R03118_DV?csf=1&web=1&e=SD6sEn | DV | PO | 2022 | 2 | 2022 | 3 | Neff Tobias | Anca M. | Tibi B. | 3 | 4 | Done
| Modified | 10.06.2021 | Continental-External | Continental-TSR |  | ADAS | 969 | R03386 | SRR320FT21 | C:\Users\uia91514\OneDrive - Continental AG\Projects data\04_Project_Divisions\AMS-ADAS\RADAR\Fiat\SRR320FT21\03_R03386_ReQualification | dPV | PO | 2021 | 38 | 2022 | 11 | Marginean Alexandru | Oana L. | Nick S. | 48 | 17 | Done
| New | 7.06.2021 | Non-Continental | External-VITESCO |  | N.A | 957 | R03470 | BMW_DCDC_C3b | https://continental.sharepoint.com/teams/cs_11010264/Projects%20data/Forms/AllItems.aspx?RootFolder=%2Fteams%2Fcs%5F11010264%2FProjects%20data%2F04%5FProject%5FDivisions%2FVITESCO%2FVT%5FHEV%2FBMW%2F01%5FBMW%5FDCDC%2F03%5FR03470%5FPreCompliance%28C3b%5Fsample%29%28SBZ%20ID957%29&FolderCTID=0x01200070D1D7DF295EBC45887D7E6D0C83A766 | PV | PO | 2021 | 46 | 2022 | 10 | Larion Catalin | Oana L. | Robert T. | 49 | 12 | Done
| Received |  | Continental-External | Continental-TSR |  |  |  | R03476 | R03476 - SAT PPS AK1 RQ AK test 7 |  |  | PO | 2022 | 11 | 2022 | 27 | Bodensohn, Ramona | Oana L. | Radu I. | 11 | TBD | Ongoing
| New | 13.01.2022 | Continental-Internal | Continental-SBZ (R&D) |  | SAM-PSS |  | R03476 | SAT_PPS_AK1 | SAT_PPS_AK1 | dPV |  | 2022 |  | 2022 |  |  | Oana L. |  | TBD |  | Next
| New | 28.10.2021 | Continental-External | Continental-TSR |  | VNI | 1129 | R03513 | MFC526TN12 | https://continental.sharepoint.com/teams/cs_11010264/Projects%20data/Forms/AllItems.aspx?FolderCTID=0x01200070D1D7DF295EBC45887D7E6D0C83A766&id=%2Fteams%2Fcs%5F11010264%2FProjects%20data%2F04%5FProject%5FDivisions%2FVNI%2DCVS%2FCAMERA%2FGeneric%5FProducts%2F02%5FMFC526%2F03%5FR03513%5FPre%2Dcompliance%5FMFC526TN12%28ID1129%29%28SBZ%29&viewid=1f54fbe3%2D0ed5%2D47a3%2D88e1%2Da70a7925d86e | Pre-Comp. | PO | 2021 | 47 | 2022 | 3 | Cioroianu Alina | Anca M. | Iulia T. | TBD | TBD | Canceled
| New | 1.10.2021 | Non-Continental | External-VITESCO |  | N.A | 1091 | R03514 | Ford_DCDC_DEB | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/VITESCO/VT_HEV/FORD/01_Ford_DCDC/02_R03514_ReQualification(Leg1)?csf=1&web=1&e=3EhRKY | Pre-Comp. | PO | 2021 | 47 | 2021 | 49 | Larion Mihaela | Oana L. | Nick S. | 48 | 51 | Done
| Received | 08.11.2021 | Non-Continental | External-OSRAM |  |  |  | R03557 | ZKW_ULB | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/OSRAM/VNI-CCN/ECU/ZKW/01_ZKW_ULB_2/03_R03557_QUALIFICATION_Requalification_2022?csf=1&web=1&e=7BrZLB | dPV | PO | 2022 | 3 | 2022 | 12 | Adina Zaharov | Oana L. | Radu I. | 3 | 13 | Done
| New | 25.11.2021 | Continental-Internal | Continental-TSR |  | UX |  | R03562 | DAG BR464 IC | https://continental.sharepoint.com/:f:/r/teams/cs_11010264/Projects%20data/04_Project_Divisions/VNI-HMI/INSTRUMENT_CLUSTER/DAG/09_BR464/05_R03562_DAG_BR464IC_deltaPV_(SBZ)?csf=1&web=1&e=YEouLC | dPV | PO | 2022 | 11 | 2022 | 18 | Herzog Cristian | Oana L. | Nicolae S. | TBD | TBD | Canceled
| New | 20.01.2022 | Continental-Internal | Continental-TSR |  | VNI |  | R03668 | MB_214_22_BLE_UWB_MAU | MB_214_22_BLE_UWB_MAU | dPV | PO | 2022 | 8 | 2022 | 25 | Niculina Radulescu | Roxana M. | Cosmin R. | TBD. | TBD | Canceled
| New | 25.05.2022 | Continental-Internal | Continental-TSR |  | SAM-VED |  | R03830 | SRR620 | SRR620 | Pre-Comp. | Dsin | 2022 | 25 | 2022 | 34 | Mardare Adrian | Roxana M. | Catalin S. | TBD |  | Next
| New | 3.05.2021 | Continental-Internal | Continental-TSR |  |  |  | R03871 | PSA eHUD |  |  | PO | 2022 | 20 | 2022 | 23 | Petru Suveti/Adina Gruber | Oana L. | Radu I. | 19 | 22 | Done
| New | 23.05.2022 | Continental-External |  |  |  |  | R03908 | S&A Nissan |  | Pre-Comp. | PO | 2022 | 24 | 2022 | 34 | Danciu Petru Bogdan | Oana L. | Radu I. | 24 | TBD | Ongoing
| Received | 20.11.2020 | Non-Continental | External-Schaffler |  | N.A | 792 |  | P-073259-02-06-49_200 |  | Pre-Comp. | PO | 2021 | 1 | 2021 | 2 | Soare Ionut Tudor | Oana L. | TBD. | TBD | TBD | Canceled
| Received | 14.12.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 803 |  | CVC |  | Pre-Comp. | PO | 2021 | 2 | 2021 | 3 | Ghise S. | Oana L. | Radu G. | TBD | TBD | Done
| Received | 22.06.2021 | Continental-Internal | Continental-SBZ (R&D) |  | ADAS | 700 |  | ARS510VP12 |  | DV | PO | 2021 | 2 | 2021 | 5 | Preda Eugen | Oana L. | Alex M. | 2 | 9 | Done
| Received | 24.11.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 797 |  | CVC Low |  | dDV | DSIN-055988 | 2021 | 2 | 2021 | 25 | Stuparu C. | Oana L. | Radu G. | 2 | 19 | Done
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 432 |  | EFP 3K+ |  | dPV | PO | 2020 | 3 | 2020 | 7 | Hategan I. | Oana L. | Ovidiu B. | - | - | Canceled
| Received | 15.12.2020 | Non-Continental | External-VITESCO |  | ETCM | 804 |  | Ford_DCDC |  | dPV | PO | 2021 | 3 | 2021 | 11 | Larion Mihaela | Oana L. | Nick S. | 4 | 11 | Done
| Received | 6.01.2021 | TBD | TBD | TBD | TBD | 807 |  | DKG250 G1 DS2011241702 |  | Pre-Comp. | TBD | 2021 | 4 | 2021 | 4 | Salinas Dante | Anca M. |  |  |  | Canceled
| Received | 4.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | BS | 853 |  | MakeValves_dPV50_additional tests |  | dPV | PO | 2021 | 4 | 2021 | 4 | Ciobanu Aurelian | Oana L. | Iulia T. | 5 | 6 | Done
| Received | 20.11.2020 | Non-Continental | External-Schaffler |  | N.A | 793 |  | P-077881-02-06-75_High low |  | Pre-Comp. | PO | 2021 | 4 | 2021 | 5 | Soare Ionut Tudor | Oana L. | TBD. | TBD | TBD | Canceled
| Received | 20.02.2021 | Continental-External | Continental-TSR |  | PSS | 814 |  | PCN0040332 |  | dPV | PO | 2021 | 4 | 2021 | 5 | Hategan Ion | Oana L. | Radu G. | 4 | 6 | Done
| Received | 07.05.2020 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 669 |  | Make Valves dPV55 |  | Pre-Comp. | PO | 2021 | 4 | 2021 | 9 | Aurelian Ciobanu | Oana L. | Iulia T. | 8 | 10 | Done
| Received | 19.01.2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 579 |  | VADA |  | dPV | PO | 2021 | 4 | 2021 | 9 | TBD | Oana L. | Radu G. | 3 | 8 | Done
| Received | 08.10.2020 | Continental-External | Continental-TSR |  | PSS | 764 |  | ACU_RNM_C1AHS_EVO_MY23_S40 |  | Pre-Comp. | PO | 2021 | 5 | 2021 | 6 | Bucnariu Claudia | Anca M. | Radu G. | TBD | TBD | Canceled
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 438 |  | EFP 3K+ |  | dPV | PO | 2020 | 5 | 2020 | 6 | Hategan I. | Oana L. | Ovidiu B. | - | - | Canceled
| Received | 20.11.2020 | Non-Continental | External-Schaffler |  | N.A | 794 |  | P-077881-02-06-75 200_TS |  | Pre-Comp. | PO | 2021 | 5 | 2021 | 6 | Soare Ionut Tudor | Oana L. | TBD. | TBD | TBD | Canceled
| Received | 27.01.2022 | Continental-Internal | Continental-SBZ (R&D) | TBD | VED | 822 |  | Thermal shock |  | Pre-Comp. | DT | 2021 | 5 | 2021 | 6 | Olariu Mircea | Anca M. | Radu I. | 5 | 6 | Done
| Received | 27.01.2021 | Continental-Internal | Continental-SBZ (R&D) | BMW | VED | 819 |  | BMW HBE Investigation |  | Pre-Comp. | DT | 2021 | 5 | 2021 | 10 | Alex Spatar | Anca M. | Dan V. | 5 | 9 | Done
| Received | 11.01.2021 | Continental-External | Continental-TSR | TBD | PSS | 808 |  | gSAT_HKMC_JAPE2 |  | DV | PO | 2021 | 5 | 2021 | 21 | Raveanu Veronica | Anca M. |  |  |  | Canceled
| Received | 11.01.2021 | Continental-External | Continental-TSR | TBD | PSS | 809 |  | pSAT_HKMC_JAPE2 |  | DV | PO | 2021 | 5 | 2021 | 24 | Raveanu Veronica | Anca M. |  |  |  | Canceled
| Modified |  | Continental-Internal | Continental-SBZ (R&D) | TBD | AM | 872 |  | SVS220VW1 |  | PV | PO | 2022 | 6 | 2022 | 9 | Rehberger Andreas | Oana L. | Iulia T. | TBD | TBD | Canceled
| Received | 13.01.2021 | Continental-External | Continental-TSR | TBD | PSS | 811 |  | ACU_FCA226_ |  | dPV | PO | 2021 | 6 | 2021 | 6 | Patan Alexandru | Oana L. | Radu G. | 6 | 6 | Done
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 448 |  | EHNR |  | dPV 03 | PO | 2021 | 6 | 2021 | 9 | Hategan I. | Mihaela C. | Radu G. | 6 | 10 | Done
| Received | 15.01.2021 | Continental-Internal | Continental-SBZ (Plant) | TBD | PSS | 580 |  | SPCh |  | dPV | PO | 2021 | 6 | 2021 | 9 | Hategan I. | Mihaela C. | Radu G. | 6 | 9 | Done
| Received | 11.02.2021 | Non-Continental | External-Schaffler | TBD | N.A | 860 |  | Scheffler_200cyclesTS |  | Pre-Comp. | PO | 2021 | 7 | 2021 | 7 | Ionut Soare | Oana L. | Nick S. | 7 | 8 | Done
| Received | 27.01.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VED | 821 |  | Foil protection |  | Pre-Comp. | DT | 2021 | 7 | 2021 | 8 | Pop Dan | Anca M. | Radu I. | 7 | 9 | Done
| Received | 12.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VED | 863 |  | VED CAirs_Ford U611 |  | Pre-Comp. | PO | 2021 | 7 | 2021 | 8 | Cosmin Bratu | Anca M. | Tiberiu B. | 8 | 10 | Done
| Received | 29.01.2021 | Non-Continental | External-Schaffler | TBD | N.A | 825 |  | Scheffler_VIB |  | Pre-Comp. | PO | 2021 | 8 | 2021 | 8 | Ionut Soare | Oana L. | Tiberiu B. | 8 | 13 | Done
| Received | 1.03.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 879 |  | VED ESS_IWS |  | Pre-Comp. | DSIN-060262 | 2021 | 8 | 2021 | 8 | Vraciu Marina | Anca M. |  |  |  | Canceled
| Received | 16.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VED | 866 |  | MK100 HCU ESC |  | Pre-Comp. | DSIN-060262 | 2021 | 8 | 2021 | 9 | Olariu Mircea | Adriana F. | Radu I. | 8 | 9 | Done
| Received | 28.01.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VNI | 823 |  | CVS_MGN_XXX_SRM_TOY |  | PV | PO | 2021 | 8 | 2021 | 18 | Davidescu Iuliana | Oana L. | Nick S. | 8 | 19 | Done
| Received | 06.11.2020 | Continental-External | Continental-ING |  | VED | 782 |  | ER100 Honda 30AA ESC IPB |  | DV | DT | 2021 | 8 | 2021 | 28 | Schmailzl S. | Anca M. | TBD. | TBD | TBD | Canceled
| Received | 23.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VED | 876 |  | MK120 |  | Pre-Comp. | DSIN-069191 | 2021 | 9 | 2021 | 9 | Pop Dan | Anca M. | Radu I. |  |  | Done
| Received | 22.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VED | 875 |  | VED EBS_garnitura etansare MK100 |  | Pre-Comp. | DSIN-060262 | 2021 | 9 | 2021 | 9 | Pal Alexandru | Anca M. | Tiberiu B. | 9 | 10 | Done
| Received | 12.02.2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 581 |  | EFP 3K+ |  | dPV | PO | 2021 | 9 | 2021 | 15 | Bardasu M. | Mihaela C. | Radu G. | 9 | 19 | Done
| Received | 17.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VED | 867 |  | Hyundai B-MPV |  | Pre-Comp. | PO | 2021 | 9 | 2021 | 15 | Wolfgang D. | Anca M. | Dan V. | 8 | 16 | Done
| Received | 10.07.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 500 |  | TRX_Chrysler |  | PV | PO | 2020 | 9 | 2020 | 16 | Ciocan A. | Oana L. | Ovidiu B. | 9 | 14 | Done
| Received | 06.11.2020 | Continental-External | Continental-ING |  | VED | 781 |  | ER100 Suzuki YXA ESC Base |  | DV | DT | 2021 | 9 | 2021 | 19 | Schmailzl S. | Anca M. | Alex M. | 9 | 23 | Done
| Received | 1.02.2021 | Non-Continental | External-Schaffler | TBD | N.A | 829 |  | Schaeffler_SaltSpray |  | Pre-Comp. | PO | 2021 | 10 | 2021 | 10 | Ionut Soare | Oana L. |  |  |  | Canceled
| Received | 1.02.2021 | Non-Continental | External-Schaffler | TBD | N.A | 827 |  | Schaeffler_TS |  | Pre-Comp. | PO | 2021 | 10 | 2021 | 10 | Ionut Soare | Oana L. |  |  |  | Canceled
| Received | 3.03.2021 | Continental-External | Continental-TSR |  | PSS | 884 |  | SUZYWD_pSat |  | Pre-Comp. | PO | 2021 | 10 | 2021 | 10 | Onut Liliana | Oana L. | Radu G. | 13 | 14 | Done
| Received | 21.12.2020 | Continental-Internal | Continental-SBZ (R&D) | TBD | VNI | 805 |  | AUD_XXXX_16_PNEU_BK |  | dPV | PO | 2021 | 10 | 2021 | 11 | Cojocariu Costel | Anca M. | Iulia T. | 9 | 12 | Done
| Received | 2.02.2021 | Non-Continental | External-Schaffler | TBD | N.A | 836 |  | Schaeffler_chemical-performed in TSR |  | Pre-Comp. | PO | 2021 | 10 | 2021 | 11 | Burlacu Adrian | Oana L. |  |  |  | Canceled
| Received | 1.02.2021 | Non-Continental | External-Schaffler | TBD | N.A | 828 |  | Schaeffler_Head_humid |  | Pre-Comp. | PO | 2021 | 10 | 2021 | 11 | Ionut Soare | Oana L. | Alex M. | TBD | TBD | Canceled
| Received | 11.02.2021 | Non-Continental | External-Schaffler | TBD | N.A | 861 |  | Scheffler_200cyclesTS |  | Pre-Comp. | PO | 2021 | 10 | 2021 | 11 | Ionut Soare | Oana L. |  |  |  | Canceled
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 433 |  | EFP3k+ |  | dPV | PO | 2020 | 10 | 2020 | 16 | Slatineanu I. | Oana L. | Ovidiu B. | 10 | 14 | Done
| Received | 22.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | PSS | 871 |  | CVC_High2 |  | Pre-Comp. | PO | 2021 | 11 | 2021 | 11 | Ghise Sorin | Mihaela C. | Radu G. | TBD | TBD | Canceled
| Received | 9.03.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 888 |  | MK120 ECU |  | Pre-Comp. | DSIN-060262 | 2021 | 11 | 2021 | 11 | Vonica Lucian | Anca M. | Tiberiu B. | 10 | 11 | Done
| Received | 3.02.2021 | Non-Continental | External-Schaffler | TBD | N.A | 844 |  | Schaeffler_01TS |  | Pre-Comp. | PO | 2021 | 11 | 2021 | 11 | Calburean Oliver-Gheorghe | Oana L. |  |  |  | Canceled
| Received | 11.03.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 892 |  | VED CAirs_Honda |  | Pre-Comp. | PO | 2021 | 11 | 2021 | 12 | Bratu Cosmin | Anca M. | Ion C. | 12 | 12 | Done
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 434 |  | emARS_35up |  | dPV | PO | 2020 | 11 | 2020 | 13 | Hategan I. | Oana L. | Dan V. | 12 | 14 | Done
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 582 |  | emARS |  | dPV | PO | 2021 | 11 | 2021 | 15 | Ion Hategan | Mihaela C. | Radu G. | 11 | 19 | Done
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 435 |  | VDP LOW |  | dPV | PO | 2020 | 11 | 2020 | 17 | Hategan I. | Oana L. | Radu G. | 11 | 16 | Done
| Received | 26.11.2020 | Continental-External | Continental-ING |  | VED | 798 |  | BR254 CAirS MRA2 CM4 GLV MY22 75 |  | PV | DT | 2021 | 11 | 2021 | 34 | Andreas Goetz | Anca M. | Radu I. | 11 | 41 | Done
| Received | 16.03,2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 895 |  | VDP HIGH VDC1 qualification 2021 |  | Pre-Comp. | TBD | 2021 | 12 | 2021 | 13 | Bardasu M. | Mihaela C. | Radu G. | 12 | 13 | Done
| Received | 1.02.2021 | Non-Continental | External-OSRAM | TBD | N.A | 834 |  | VolvoHCM |  | Pre-Comp. | PO | 2021 | 12 | 2021 | 13 | Adina Zaharov | Oana L. | Tiberiu B. | 13 | 13 | Done
| Received | 11.03.2021 | Continental-External | Continental-TSR |  | VNI | 893 |  | BW SP 21 MFST_PWR |  | PWR | PO | 2021 | 12 | 2021 | 14 | Deparateanu Claudia | Oana L. | Iulia T. | 12 | 14 | Done
| Received | 1.02.2021 | Continental-External | Continental-TSR | TBD | QL | 832 |  | KB_System MFC525 |  | Pre-Comp. | TBD | 2021 | 12 | 2021 | 16 | Dragoi Emilia | Anca M. | Radu I. | TBD | TBD | Canceled
| Received | 8.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VNI | 856 |  | BS_PPE_21_SCU_V3 |  | dDV | PO | 2021 | 12 | 2021 | 17 | Costel Cojocaru | Oana L. | Iulia T. | 8 | 11 | Done
| Received | 09.06.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 692 |  | MY21 |  | PV | PO | 2021 | 12 | 2021 | 18 | Ciocan A. | Oana L. | Radu G. | 12 | 20 | Done
| Received | 11.03.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 637 |  | CVC HIGH2 |  | dDV | DT | 2020 | 12 | 2020 | 19 | Ghise S. | Oana L. | Ovidiu B. | 12 | 19 | Done
| Received | 17.03.2021 | Continental-External | Continental-TSR |  | N.A | 896 |  | DAIMLER SVC22x_pre-compliance |  | Pre-Comp. | TBD | 2021 | 12 | 2021 | 22 | Dragoi Emilia | Anca M. | Radu G. | TBD | TBD | Canceled
| Received | 9.03.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 887 |  | AMS VED_MK120 Upgrade ECU |  | Pre-Comp. | DSIN | 2021 | 12 | 2021 | 23 | Seybold Matthias | Anca M. | Dan V. | 12 | 21 | Done
| Received | 1.02.2021 | Continental-External | Continental-TSR | TBD | QL | 831 |  | KB_MFC525 |  | PV | PO | 2021 | 12 | 2021 | 24 | Dragoi Emilia | Anca M. | Radu I. | TBD | TBD | Canceled
| Received | 26.02.2021 | Continental-External | Continental-TSR |  | VITESCO | 878 |  | GPA T85 DV vib test reschedule |  | DV | PO | 2021 | 13 | 2021 | 13 | Berechet Radu | Oana L. | Daniel I. | 13 | 13 | Done
| Received | 3.02.2021 | Non-Continental | External-Schaffler | TBD | N.A | 845 |  | Schaeffler_02Vibr |  | Pre-Comp. | PO | 2021 | 13 | 2021 | 14 | Calburean Oliver-Gheorghe | Oana L. | TBD. | TBD | TBD | Canceled
| Received | 19.03.2021 | Non-Continental | External-OSRAM |  | N.A | 899 |  | VolvoHCM |  | Pre-Comp. | PO | 2021 | 13 | 2021 | 18 | Adina Zaharov | Oana L. | Radu I. | 14 | 21 | Done
| Received | 15.01.2021 | Continental-External | Continental-TSR | TBD | VNI | 813 |  | CCN_Honda_MY21 |  | Pre-Comp. | PO | 2021 | 13 | 2021 | 19 | Mioc Lucian | Oana L. |  |  |  | Canceled
| Received | 15.01.2021 | Continental-External | Continental-TSR | TBD | ADAS | 812 |  | Daimler |  | dPV | PO | 2021 | 13 | 2021 | 23 | Zeljko Majstoro | Oana L. | Iulia T. | 13 | 31 | Done
| Received | 22.09.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 747 |  | DCC4 |  | Pre-Comp. | DT | 2021 | 13 | 2021 | 25 | Sorin Ghise | Mihaela C. | TBD. | TBD | TBD | Canceled
| Received | 6.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 906 |  | BMW CVC LOW |  | DV | DSIN-055988 | 2021 | 14 | 2021 | 14 | Stuparu C. | Oana L. | Radu G. | 14 | 14 | Done
| Received | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 927 |  | PE Protection foil |  | Pre-Comp. | DT | 2021 | 14 | 2021 | 17 | Pop Dan | Anca M. | Dan V. | 15 | 18 | Done
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 436 |  | AMR |  | dPV | PO | 2020 | 14 | 2020 | 18 | Hategan I. | Oana L. | Ovidiu B. | - | - | Canceled
| Received | 10.12.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 558 |  | CVC |  | Pre-Comp. | DT | 2020 | 14 | 2020 | 18 | Stuparu C. | Oana L. | Ovidiu B. | 14 | 16 | Done
| Received | 6.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 904 |  | Dacia EVO ESC |  | dPV | PO | 2021 | 14 | 2021 | 21 | Dallmeir Wolfgang | Anca M. | Dan V. | 17 | 23 | Done
| Received | 6.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 905 |  | Dacia EVO IPB |  | dPV | PO | 2021 | 14 | 2021 | 21 | Dallmeir Wolfgang | Anca M. | Dan V. | 17 | 23 | Done
| Received | 23.03.2021 | Continental-External | Continental-TSR |  | PSS | 901 |  | gSat&pSat HRS9 MY23 |  | Pre-Comp. | PO | 2021 | 14 | 2021 | 22 | Traian Novacescu | Anca M. | Radu G. | 14 | 23 | Done
| Received | 14.12.2020 | Non-Continental | External-OSRAM |  | N.A | 802 |  | VOLVO_HCM |  | dPV | PO | 2021 | 14 | 2021 | 24 | Zaharov Adina | Oana L. | Radu I. | 13 | 27 | Done
| Received | 28.07.2020 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 719 |  | Volvo_HCM |  | dPV | PO | 2021 | 14 | 2021 | 28 | Zaharov Adina | Oana L. | TBD. | TBD | TBD | Canceled
| Received | 06.11.2020 | Continental-External | Continental-ING |  | VED | 783 |  | EBS_ER100 EVO SAIC Sigma A AS32 IPB Base |  | PV | DT | 2021 | 14 | 2021 | 33 | Schmailzl S. | Anca M. | Radu I. | 13 | 35 | Done
| Received | 06.11.2020 | Continental-External | Continental-ING |  | VED | 784 |  | ER100 SAIC Sigma A AS32 IPB HighPlus |  | PV | DT | 2021 | 14 | 2021 | 33 | Schmailzl S. | Anca M. | Radu I. | 13 | 35 | Done
| Received | 08.04.2020 | Continental-Internal | Continental-SBZ (R&D) |  | BS | 647 |  | Make Valves |  | dPV50 | PO | 2020 | 15 | 2021 | 1 | Ciobanu Aurelian | Oana L. | Iulia T. | TBD | TBD | Done
| Received | 13.01.2021 | Continental-Internal | Continental-SBZ (R&D) | Dacia | VED | 810 |  | Engineering test - Ice water shock |  | PWR | IO | 2021 | 15 | 2021 | 22 | Alexandru Spatar | Anca M. | Dan V. | 10 | 10 | Done
| Received | 13.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 932 |  | Hyundai OS Leg C CUA |  | dPV | PO | 2021 | 15 | 2021 | 25 | Stefan Schmailzl | Anca M. | Dan V. | 17 | 28 | Done
| Received | 13.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 933 |  | Hyundai OS Leg C SHA |  | dPV | PO | 2021 | 15 | 2021 | 25 | Stefan Schmailzl | Anca M. | Dan V. | 17 | 28 | Done
| Received | 20.07.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 715 |  | EFP2V2K |  | DV | PO | 2021 | 15 | 2021 | 31 | Mihai Salceanu | Carmen B. | Radu G. | 15 | 31 | Done
| Received | 13.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 934 |  | MK120 |  | Pre-Comp. | DSIN | 2021 | 16 | 2021 | 16 | Dan Pop |  | Tiberiu B. | 15 | 16 | Done
| Received | 3.02.2021 | Non-Continental | External-Schaffler | TBD | N.A | 846 |  | Schaeffler_03SaltSpray |  | Pre-Comp. | PO | 2021 | 16 | 2021 | 16 | Calburean Oliver-Gheorghe | Oana L. |  |  |  | Canceled
| Received | 14.04.2021 | Non-Continental | External-Schaffler |  | N.A | 935 |  | Schaeffler_HighLoW |  | Pre-Comp. | PO | 2021 | 16 | 2021 | 16 | Alexandra Bonini | Oana L. | Nick S. | 17 | 17 | Done
| Received | 29.01.2021 | Non-Continental | External-Schaffler | TBD | N.A | 824 |  | Schaeffler_IP |  | Pre-Comp. | PO | 2021 | 16 | 2021 | 16 | Ionut Soare | Oana L. | Nick S. | 17 | 17 | Done
| Received | 11.02.2021 | Continental-External | Continental-TSR | TBD |  | 862 |  | BMW_SP21_19_USM_PDMD |  | dPV | PO | 2021 | 16 | 2021 | 18 | Ionela Catalina Arsene | Oana L. | TBD. | TBD | TBD | Canceled
| Received | 7.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 928 |  | MK100_HCRP_E_CL_F_LPA |  | Pre-Comp. | PO | 2021 | 16 | 2021 | 18 | Birza C. | Anca M. | Dan V. | 17 | 19 | Done
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 584 |  | VDP LOW |  | dPV | PO | 2021 | 16 | 2021 | 20 | Ion Hategan | Mihaela C. | Radu G. | 16 | 21 | Done
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 583 |  | AMR |  | dPV 07 | PO | 2021 | 17 | 2021 | 21 | Anghel A. | Mihaela C. | Radu G. | 17 | 21 | Done
| Received | 8.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VED | 854 |  | ER100 Mitsubishi 4L45W |  | PV | PO | 2021 | 17 | 2021 | 26 | Stefan Schmailzl | Anca M. | Alex M. | 17 | 25 | Done
| Received | 6.04.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 903 |  | SVC_Daimler |  | Pre-Comp. | PO | 2021 | 18 | 2021 | 18 | Andriescu Tudor | Oana L. | Tiberiu B. | 15 | 15 | Done
| Received | 3.02.2021 | Non-Continental | External-Schaffler | TBD | N.A | 847 |  | Schaeffler_04DampHeat |  | Pre-Comp. | PO | 2021 | 18 | 2021 | 19 | Calburean Oliver-Gheorghe | Oana L. |  |  |  | Canceled
| Received | 06.04.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 646 |  | VADA |  | dPV | PO | 2020 | 18 | 2020 | 19 | Bardasu M. | Oana L. | Alex M. | 15 | 15 | Done
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 585 |  | VDP MID |  | dPV | PO | 2021 | 18 | 2021 | 22 | Bardasu M. | Mihaela C. | Radu G. | 17 | 23 | Done
| Received | 31.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 605 |  | emARS |  | dPV | PO | 2020 | 18 | 2020 | 25 | Hategan I. | Oana L. | Ovidiu B. | - | - | Canceled
| Received | 8.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VED | 855 |  | ER100 Hyundai SU2id |  | PV | PO | 2021 | 18 | 2021 | 30 | Stefan Schmailzl | Anca M. | Radu I. | 18 | 33 | Done
| Received | 26.03.2021 | Continental-External | Continental-TSR |  | CES | 902 |  | TSR_L-03 |  | Pre-Comp. | PO | 2021 | 18 | 2021 | 30 | Cockalo Danijel | Anca M. | Nick S. | 20 | 41 | Done
| Received | 11.05.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 946 |  | SVC_Daimler |  | Pre-Comp. | eSign | 2021 | 19 | 2021 | 19 | Andriescu Tudor | Oana L. | Radu G. | 19 | 19 | Done
| Received | 13.05.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 948 |  | VNI CCN_DQ200 |  | Pre-Comp. | DSIN | 2021 | 19 | 2021 | 19 | Ienciu Horia | Anca M. | Dan V. | 19 | 21 | Done
| Received | 31.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 607 |  | CVC |  | dPV | PO | 2020 | 19 | 2020 | 20 | Ghise S. | Oana L. | Ovidiu B. | - | - | Canceled
| Received | 7.05.2021 | Non-Continental | External-OSRAM |  | N.A | 941 |  | VolvoHCM1 |  | Pre-Comp. | PO | 2021 | 19 | 2021 | 21 | Adina Zaharov | Oana L. | Radu I. | 20 | 24 | Done
| Received | 11.03.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 891 |  | MakeValves_dPV73 |  | dPV | PO | 2021 | 19 | 2021 | 22 | Ciobanu Aurelian | Oana L. | Iulia T. | 19 | 22 | Done
| Received | 5.03.2022 | Continental-External | Continental-ING |  | ADAS | 886 |  | TO21-024-MFC320DC-CP05-SCH |  | PV | PO | 2021 | 19 | 2021 | 25 | Wiedrich philipp | Oana L. | Iulia T. | 19 | 25 | Done
| Received | 5.03.2021 | Continental-External | Continental-ING |  | ADAS | 885 |  | TO21-023-MFC3XX-CP05-SCH |  | PV | PO | 2021 | 19 | 2021 | 28 | Wiedrich philipp | Oana L. | Iulia T. | 19 | 29 | Done
| Received | 20.05.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 481 |  | SCCU DCC3 |  | dPV | PO | 2020 | 19 | 2020 | 31 | Slatineanu I. | Oana L. | Ovidiu B. | 19 | 31 | Done
| Received | 1.03.2021 | Continental-External | External-VITESCO |  | N.A | 882 |  | BMW_48V_DCDC |  | dPV | PO | 2021 | 19 | 2021 | 32 | Larion Catalin | Oana L. | Nick S. | 19 | 36 | Done
| Received | 1.03.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 881 |  | VED EBS_ER100 Subaru HM7 IPB High |  | dPV | PO | 2021 | 19 | 2021 | 32 | Stefan Schmailzl | Anca M. | Radu I. | 21 | 35 | Done
| Received | 1.03.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 880 |  | VED EBS_ER100 Subaru HM7-P IPB Base |  | dPV | PO | 2021 | 19 | 2021 | 32 | Stefan Schmailzl | Anca M. | Radu I. | 21 | 35 | Done
| Received | 8.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VED | 857 |  | BMW UKL MK100 ESC MY19.50 High |  | PV | PO | 2021 | 19 | 2021 | 36 | Dallmeir Wolfgang | Anca M. | Dan V. | 19 | 41 | Done
| Received | 03.07.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 495 |  | EFP2K |  | DV | DT | 2020 | 19 | 2020 | 38 | Ghise S. | Oana L. | Ovidiu B. | 19 | 38 | Done
| Received | 10.05.2021 | Non-Continental | External-VITESCO |  | N.A | 944 |  | BMW_48V_DCDC |  | Pre-Comp. | PO | 2021 | 20 | 2021 | 20 | Pap Abel | Oana L. | Nick S. | 20 | 20 | Done
| Received | 13.05.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 949 |  | VW_MQB23_GW_Baseline |  | Pre-Comp. | PO | 2021 | 20 | 2021 | 20 | Costel Cojocaru | Oana L. | Daniel I. | 20 | 20 | Done
| Received | 25.05.2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 953 |  | Y_Lucid_air_pre-compliance xRAY |  | Pre-Comp. | DSIN | 2021 | 20 | 2021 | 20 | Ciocan A. | Oana L. |  |  |  | Done
| Received | 21.04.2021 | Continental-External | Continental-TSR |  | VNI | 939 |  | ARS510TN12 |  | Pre-Comp. | PO | 2021 | 20 | 2021 | 23 | Cioroianu Alina | Oana L. | Radu G. | 21 | 24 | Done
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 438 |  | SAS |  | dPV | PO | 2020 | 20 | 2020 | 24 | Hategan I. | Oana L. | Radu G. | 20 | 25 | Done
| Received | 14.04.2021 | Continental-External | Continental-TSR |  | VNI | 936 |  | John Deere MECA_REAR1 |  | dPV | PO | 2021 | 20 | 2021 | 25 | Cockalo Danijel | Anca M. | Iulia T. | 19 | 27 | Done
| Received | 26.01.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VNI | 817 |  | PSA_MFST_5W |  | dPV | PO | 2021 | 20 | 2021 | 30 | Negrut Sorin | Oana L. | Iulia T. | 23 | 41 | Done
| Received | 25.02.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 877 |  | VED EBS_ER100 Suzuki ABS Entry YSD “Velvety” |  | dPV | PO | 2021 | 20 | 2021 | 31 | Stefan Schmailzl | Anca M. | Dan V. | 19 | 30 | Done
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 586 |  | VDP high |  | dPV | PO | 2021 | 21 | 2021 | 25 | Anghel A. | Mihaela C. | Radu G. | 21 | 26 | Done
| Received | 5.05.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 940 |  | ER100 Suzuki YSA MY19.75 BasePlus |  | dPV | PO | 2021 | 21 | 2021 | 27 | Stefan Schmailzl | Anca M. | Dan V. | 20 | 28 | Done
| Received | 11.02.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 613 |  | emARS |  | dPV | PO | 2020 | 22 | 2020 | 23 | Hategan I. | Oana L. | Ovidiu B. | - | - | Canceled
| New | 18.05.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 950 |  | Renault X82 Short Validation |  | Pre-Comp. | TBD | 2021 | 22 | 2021 | 23 | TBD | Anca M. |  | TBD | TBD | Canceled
| Received | 06.04.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 645 |  | SPCh |  | dPV | PO | 2020 | 22 | 2020 | 23 | Slatineanu I. | Oana L. | Ovidiu B. | 22 | 22 | Done
| Received | 2.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VNI | 837 |  | MakeValves_dPV62 |  | PWR | PO | 2021 | 22 | 2021 | 26 | Ciobanu Aurelian | Oana L. | Iulia T. | TBD | TBD | Canceled
| Received | 25.04.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 474 |  | CHCM1.25 |  | dPV | PO | 2020 | 22 | 2020 | 28 | Ciocan A. | Oana L. | Ovidiu B. | 22 | 28 | Done
| Received | 30.09.2020 | Continental-External | Continental-TSR |  | VNI | 757 |  | TSR_VNI_Iveco HighMux SPR2 MY19 |  | dPV | PO | 2021 | 22 | 2021 | 28 | Cuciureanu Florin | Oana L. | Nick S. | 23 | 32 | Done
| Received | 17.02.2021 | Continental-External | Continental-TSR | TBD | ADAS | 869 |  | DAIPP5_SIB_SHA_UV_unit_change |  | dPV | PO | 2021 | 22 | 2021 | 34 | Zeljko Majstoro | Anca M. | Nick S. | 23 | 36 | Done
| Received | 06.07.2019 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 486 |  | BMW_SP21_21_HSCU_SHZ |  | PV | PO | 2020 | 23 | 2021 | 20 | Burdulea Ionel | Oana L. | Iulia T. | 23 | 23 | Done
| Received | 11.06.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 970 |  | CCN_DQ 200_xRay |  | Pre-Comp. | ESign | 2021 | 23 | 2021 | 23 | Radu Giurgiu | Carmen B. | Carmen B. | 23 | 23 | Done
| Received | 11.06.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 971 |  | CCN_SVC 220_xRay |  | Pre-Comp. | ESign | 2021 | 23 | 2021 | 23 | Munteanu Cristian | Carmen B. | Carmen B. | 23 | 23 | Done
| Received | 2.02.2021 | Non-Continental | External-Schaffler | TBD | N.A | 835 |  | HLStorage |  | Pre-Comp. | PO | 2021 | 23 | 2021 | 23 | Bonini Victoria-Alexandra | Oana L. | Alex M. | 24 | 25 | Done
| Received | 15.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VED | 864 |  | VED CAirs_Nissan QX80 |  | DV | DSIN | 2021 | 23 | 2021 | 24 | Dragos Roman | Anca M. | Tiberiu B. | 22 | 25 | Done
| Received | 18.03.2021 | Continental-External | Continental-SBZ (R&D) |  | PSS | 747 |  | DCC4 |  | Pre-Comp. | PO | 2021 | 23 | 2021 | 27 | Sorin Ghise | Mihaela C. | Radu G. | 23 | 30 | Done
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 439 |  | VDP High |  | dPV | PO | 2020 | 23 | 2020 | 27 | Hategan I. | Oana L. | Radu G. | 23 | 27 | Done
| Received | 12.05.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 947 |  | MakeValves_dPV63 |  | dPV | PO | 2021 | 23 | 2021 | 28 | Aurelian Ciobanu | Oana L. | Iulia T. | 26 | 27 | Done
| Received | 8.06.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 962 |  | CCN_MPS6_xRay |  | Pre-Comp. | ESign | 2021 | 24 | 2021 | 24 | Adina Avram | Carmen B. | Carmen B. | 24 | 24 | Done
| Received | 17.02.2021 | Continental-External | Continental-TSR | TBD | ADAS | 868 |  | CX482 |  | PV | PO | 2021 | 24 | 2021 | 26 | Munk Dieter | Anca M. | Iulia T. | 24 | 27 | Done
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 587 |  | SAS |  | dPV | PO | 2021 | 24 | 2021 | 28 | Mihail Bardasu | Mihaela C. | Radu G. | 24 | 30 | Done
| Received | 24.06.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 980 |  | CAG_XXXX_D_PNEU_xRay |  | Pre-Comp. | DSIN-051798 | 2021 | 25 | 2021 | 25 | Aurelian Ciobanu | Carmen B. | Carmen B. | 26 | 26 | Done
| Received | 24.06.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 981 |  | DQ200 Gen2_xRay |  | Pre-Comp. | ESign | 2021 | 25 | 2021 | 25 | Marius Maracine | Carmen B. | Carmen B. | 26 | 26 | Done
| Received | 19.05.2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 951 |  | AMR |  | dPV 08 | PO | 2021 | 25 | 2021 | 25 | Hategan I. | Mihaela C. | Radu G. | 25 | 25 | Done
| Received | 8.06.2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 960 |  | CVC LOW |  | Pre-Comp. | TBD | 2021 | 25 | 2021 | 25 | Stuparu Catalin | Oana L. | Radu G. |  |  | Canceled
| Received | 3.03.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 883 |  | AUDIXXXX |  | dPV | PO | 2021 | 25 | 2021 | 26 | Costel Cojocaru | Anca M. | Iulia T. | 24 | 26 | Done
| Received | 12.05.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 676 |  | CVC HIGH2 |  | Pre-Comp. | DT-310532 | 2020 | 25 | 2020 | 26 | Ghise S. | Oana L. | Ovidiu B. | 25 | 25 | Done
| Received | 22.06.2021 | Continental-External | Continental-TSR |  | HMI | 977 |  | DAG V297 HUD |  | Pre-Comp. | PO | 2021 | 25 | 2021 | 26 | Pavel Lucian | Anca M. | Radu G. | 25 | 27 | Done
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 437 |  | VDP MID |  | dPV | PO | 2020 | 25 | 2020 | 28 | Hategan I. | Oana L. | Radu G. | 16 | 27 | Done
| New | 15.06.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 974 |  | CCN_Magna |  | Pre-Comp. | TBD | 2021 | 25 | 2021 | 33 | TBD | Oana L. |  |  |  | Canceled
| Received | 28.05.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 954 |  | VW_MQB19_GW |  | dDV | DSIN-030919 | 2021 | 26 | 2021 | 26 | Costel Cojocaru | Oana L. | Iulia T. | 27 | 28 | Done
| Received | 29.01.2021 | Non-Continental | External-Schaffler | TBD | N.A | 826 |  | Schaeffler_Durability_test |  | Pre-Comp. | PO | 2021 | 26 | 2021 | 27 | Bonini Victoria-Alexandra | Oana L. | Nick S. | 27 | 32 | Done
| Received | 1.02.2021 | Non-Continental | External-Schaffler | TBD | N.A | 833 |  | Schaeffler_DampHeat |  | Pre-Comp. | PO | 2021 | 26 | 2021 | 28 | Bonini Victoria-Alexandra | Oana L. | Nick S. | 27 | 30 | Done
| Received | 03.12.2020 | Continental-External | Continental-ING |  | VED | 800 |  | ER100 Ford CD4.2 |  | PV | DT | 2021 | 26 | 2021 | 32 | Schmailzl S. | Anca M. | Dan V. | 26 | 32 | Done
| Received | 10.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 576 |  | emARS |  | dPV 01 | PO | 2020 | 26 | 2020 | 33 | Salcianu M. | Oana L. | Dan V. | 26 | 31 | Done
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 440 |  | SSD |  | dPV | PO | 2020 | 26 | 2020 | 33 | Salcianu M. | Oana L. | Radu G. | 26 | 32 | Done
| Received | 9.03.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 889 |  | ER100 Mitsubishi 5F00 Base |  | DV | DSIN | 2021 | 27 | 2022 | 15 | Stefan Schmailzl | Anca M. | Dan V. | 31 | 20 | Done
| Received | 9.03.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 890 |  | ER100 Mitsubishi 5F00 High Plus |  | DV | DSIN | 2021 | 27 | 2022 | 15 | Stefan Schmailzl | Anca M. | Dan V. | 31 | 20 | Done
| Received | 5.07.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 989 |  | Cairs EVO_xRay |  | Pre-Comp. | DSIN-071041 | 2021 | 27 | 2021 | 27 | Vasi Dumitriu | Carmen B. | Carmen B. | 27 | 28 | Done
| Received | 23.06.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 978 |  | LTT AUDI PPE |  | Pre-Comp. | TBD | 2021 | 27 | 2021 | 27 | Costel Cojocaru | Anca M. | Iulia T. | 27 | 27 | Done
| Received | 2.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VNI | 838 |  | MakeValves_PWR_dPV63 |  | PWR | PO | 2021 | 27 | 2021 | 30 | Ciobanu Aurelian | Oana L. | Iulia T. | TBD | TBD | Canceled
| Received | 29.06.2021 | Continental-Internal | Continental-SBZ (R&D) |  | HMI | 984 |  | Audi 11.6 PPEVPE_Audi 11.9 FID |  | PV | PO | 2021 | 27 | 2021 | 31 | Lisca Bogdan | Oana L. | Nick S. | 28 | 32 | Done
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 588 |  | SSD |  | dPV | PO | 2021 | 27 | 2021 | 31 | Hategan Ion | Mihaela C. | Radu G. | 27 | 29 | Done
| Modified | 20.04.2021 | Non-Continental | External-VITESCO |  | N.A | 937 |  | BMW_48V_DCDC |  | dPV 01 | TBD | 2021 | 27 | 2021 | 33 | TBD | TBD |  |  |  | Canceled
| Received | 9.06.2021 | Continental-External | Continental-TSR |  | TBD | 968 |  | RSA_PTN42146_Schotky_Diode_Onsemi |  | dPV | PO | 2021 | 27 | 2021 | 35 | Popescu Darian | Oana L. | Radu I. | 27 | 37 | Done
| Received | 13.07.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 993 |  | DQ200 Gen1_xRay |  | Pre-Comp. | eSign | 2021 | 28 | 2021 | 28 | Sorin Munteanu | Carmen B. | Carmen B. |  |  | Done
| Received | 15.07.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 997 |  | DQ200_xRay |  | Pre-Comp. | eSign | 2021 | 28 | 2021 | 28 | Marius Maracine | Carmen B. | Carmen B. |  |  | Done
| Received | 15.07.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 996 |  | Prototype shop_Ramses 1.5_xRay |  | Pre-Comp. | DSIN-073814-3301 | 2021 | 28 | 2021 | 28 | Claudiu Popescu | Carmen B. | Carmen B. | 28 | 28 | Done
| Received | 14.07.2020 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 710 |  | BMW_SP21_20_SCU_GBE |  | dPV | PO | 2021 | 28 | 2021 | 39 | Burdulea Ionel | Oana L. | Iulia T. | 28 | 42 | Done
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 441 |  | VDP HIGH |  | dPV | PO | 2020 | 29 | 2020 | 33 | Hategan I. | Oana L. | Ovidiu B. | - | - | Canceled
| Received | 13.11.2018 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 398 |  | CVC HIGH2 |  | PV | PO | 2020 | 30 | 2021 | 8 | Ghise S. | Oana L. | Radu G. | 31 | 7 | Done
| Received | 07.09.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 702 |  | VDP LOW |  | dPV | PO | 2020 | 30 | 2020 | 30 | Bardasu M. | Oana L. | Radu G. | 29 | 29 | Done
| Received | 21.04.2021 | Continental-External | Continental-TSR |  | VNI | 938 |  | KTM_PJ619 |  | Pre-Comp. | PO | 2021 | 30 | 2021 | 31 | Mardare Adrian | Anca M. | Radu G. | 30 | 32 | Done
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 589 |  | VDP HIGH |  | dPV | PO | 2021 | 30 | 2021 | 34 | TBD | Oana L. | Radu G. | TBD | TBD | Canceled
| New | 9.06.2021 | Continental-External | Continental-TSR |  | VNI | 967 |  | CVS_Volvo_TEA2+_DialQualif |  | dPV | PO | 2021 | 30 | 2021 | 38 | Stoiculescu Dorin | Oana L. |  |  |  | Canceled
| New | 23.06.2021 | Continental-External | Continental-TSR |  | ADAS | 979 |  | TSR AMS ADAS_SRR320FT21 |  | PV | TBD | 2021 | 30 | 2021 | 40 | TBD | Anca M. |  |  |  | Canceled
| Received | 7.07.2021 | Continental-External | Continental-TSR |  | VNI | 992 |  | AUD_PPE_SCU |  | PV | PO | 2021 | 30 | 2021 | 43 | Cojocariu Costel | Oana L. | Iulia T. | 30 | 46 | Done
| Received | 10.07.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 500 |  | Nissan CDM |  | DV | PO | 2020 | 30 | 2020 | 49 | Dincu C. | Oana L. | Ovidiu B. | 30 | 49 | Done
| Received | 3.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1012 |  | ESS_D5_ASU_WW_x-ray |  | Pre-Comp. | DSIN-017199 | 2021 | 31 | 2021 | 31 | Trica Daniel | Carmen B. | Carmen B. | 31 | 31 | Done
| Received | 2.08.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1010 |  | Prototype shop_Ramses 1.5_xRay |  | Pre-Comp. | DSIN-073814-3301 | 2021 | 31 | 2021 | 31 | Falaviu Musat | Carmen B. | Carmen B. | 31 | 31 | Done
| Received | 6.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1014 |  | Volvo SP2_x-ray |  | Pre-Comp. | DSIN-057266 | 2021 | 31 | 2021 | 32 | Nicu Stefanoaia | Carmen B. | Carmen B. | 31 | 32 | Done
| Received | 18.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1025 |  | Suzuky ABS Velvety |  | Pre-Comp. | PO | 2021 | 31 | 2021 | 36 | Stefan Schmailzl | Anca M. | Dan V. | 31 | 36 | Done
| Received | 13.04.2021 | Continental-External | External-OSRAM |  | N.A | 930 |  | IAS_Osram_Volvo_HCM |  | PV | PO | 2021 | 31 | 2021 | 44 | Zaharov Adina | Oana L. | Radu I. | 33 | 49 | Done
| Received | 10.08.2021 | Continental-Internal | Continental-TSR |  | VNI | 1017 |  | Traton CM4_x-ray |  | Pre-Comp. | PO | 2021 | 32 | 2021 | 32 | Paul Popute | Carmen B. | Carmen B. | 32 | 32 | Done
| Received | 9.08.2022 | Non-Continental | External-VITESCO |  | N.A | 1016 |  | 48V DCDC BMW_C3_VIB |  | Pre-Comp. | PO | 2021 | 32 | 2021 | 32 | Larion Catalin | Oana L. | Tiberiu B. | 32 | 33 | Done
| Received | 14.07.2021 | Non-Continental | External-Schaffler |  | N.A | 994 |  | VIBtest |  | Pre-Comp. | PO | 2021 | 32 | 2021 | 32 | Bonini Victoria-Alexandra | Oana L. | Tiberiu B. | 32 | 34 | Done
| Received | 1.07.2021 | Non-Continental | External-VITESCO |  | VITESCO | 988 |  | DB35 |  | Pre-Comp. | PO | 2021 | 32 | 2021 | 39 | Cialma Sebastian | Oana L. | Nick S. | 33 | 41 | Done
| Received | 29.07.2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 1001 |  | CVC LOW |  | Pre-Comp. |  | 2021 | 33 | 2021 | 33 | Stuparu Catalin | Carmen B. | Tiberiu B. | 33 | 33 | Done
| Received | 20.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1027 |  | MK120 DV5a x-ray |  | Pre-Comp. | DSIN-022367 | 2021 | 33 | 2021 | 33 | Aurel Neamtu | Carmen B. | Carmen B. | 33 | 33 | Done
| Received | 18.08.2021 | Continental-Internal | Continental-SBZ (Plant) |  | CCN | 1026 |  | SVC220 x-ray |  | Pre-Comp. | PO | 2021 | 33 | 2021 | 33 | Cristian Munteanu | Carmen B. | Carmen B. | 33 | 33 | Done
| Received | 17.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1021 |  | VDP_01 x-ray |  | Pre-Comp. | DSIN-042056 | 2021 | 33 | 2021 | 33 | Radu Rociu | Carmen B. | Carmen B. | 33 | 33 | Done
| Received | 16.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1022 |  | MK100 |  | Pre-Comp. | DSIN | 2021 | 33 | 2021 | 33 | David Mircea | Oana L. | Dan V. | 33 | 33 | Done
| Received | 23.06.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 701 |  | VDP HIGH |  | dPV | PO | 2020 | 33 | 2020 | 33 | Hategan I. | Oana L. | Radu G. | 32 | 32 | Done
| Received | 16.08.2021 | Continental-Internal | Continental-SBZ (Plant) |  | ADAS | 1018 |  | PCN Maxim_SVC10 |  | Pre-Comp. | ESign | 2021 | 33 | 2021 | 34 | Pufu Adelin | Oana L. | Iulia T. | 33 | 36 | Done
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 442 |  | SCCM |  | dPV | PO | 2020 | 33 | 2020 | 36 | Hategan I. | Oana L. | Ovidiu B. | - | - | Canceled
| Received | 29.07.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1002 |  | ER100 Hyundai B-MPV |  | dDV | DSIN | 2021 | 33 | 2021 | 39 | Stefan Schmailzl | Alex I. | Dan V. | 33 | 39 | Done
| Received | 7.06.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 956 |  | Iveco SPR12 |  | PV | PO | 2021 | 33 | 2021 | 39 | Gheorghe Alexandru | Anca M. | Radu G. | 32 | 37 | Done
| Received | 25.01.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | PSS | 815 |  | EFP2V2K |  | Pre-Comp. | PO | 2021 | 33 | 2021 | 41 | Salcianu M. | Carmen B. | Radu G. | 32 | 40 | Done
| Received | 19.03.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 462 |  | CHCM1.25 |  | dPV | PO | 2020 | 33 | 2020 | 43 | Stuparu C. | Oana L. | Radu G. | 33 | 43 | Done
| Received | 7.06.2021 | Non-Continental | External-VITESCO |  | N.A | 958 |  | DKG250_GEN1&2 |  | Pre-Comp. | PO | 2021 | 33 | 2021 | 48 | Salintas Dante | Oana L. | Radu I. | 34 | 3 | Done
| Received | 11.06.2021 | Continental-External | Continental-TSR |  | PSS | 972 |  | ACU PSA P8 |  | dPV | PO | 2021 | 34 | 2022 | 12 | Popa Cristian | Anca M. | Nick S. | 35 | 12 | Done
| Received | 26.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1031 |  | D3_GEELY_x-Ray |  | Pre-Comp. | DSIN-075878 | 2021 | 34 | 2021 | 34 | Nicu Stefanoaia | Carmen B. | Carmen B. | 34 | 34 | Done
| Received | 27.08.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1034 |  | Ramses 1.5 |  | Pre-Comp. | DSIN-073814-3301 | 2021 | 34 | 2021 | 34 | Flaviu Musat | Carmen B. | Carmen B. | 34 | 34 | Done
| Received | 22.09.2020 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 748 |  | DAIMLER BR254 |  | Pre-Comp. | DT | 2021 | 34 | 2021 | 35 | Bratu Cosmin | Anca M. | Tiberiu B. | 29 | 30 | Done
| Received | 4.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VED | 852 |  | Base CAirS CP22 |  | DV | IO | 2021 | 34 | 2021 | 37 | Dragos Roman | Anca M. | Tiberiu B. | 39 | 35 | Done
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 590 |  | PASM |  | dPV | PO | 2021 | 34 | 2021 | 37 | TBD | Oana L. | TBD. | TBD | TBD | Canceled
| Received | 2.08.2021 | Non-Continental | External-OSRAM |  | N.A | 1006 |  | HCM_Blacklabel |  | Pre-Comp. | PO | 2021 | 34 | 2021 | 38 | Zaharov Adina | Oana L. | Radu I. | 35 | 43 | Done
| Received | 29.06.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 983 |  | Mk100 Cl.3.0 & Mk120 Cl 2.0 |  | Pre-Comp. | TBD | 2021 | 34 | 2021 | 38 | Tudor Bozan | Anca M. | Dan V. | 34 | 38 | Done
| Received | 16.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1019 |  | MakeValves_dPV79_dPV80 |  | dPV | PO | 2021 | 34 | 2021 | 42 | Ciobanu Aurelian | Oana L. | Iulia T. | 38 | 41 | Done
| Received | 11.02.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 599 |  | PNEU SCU - MB_213_D5_PSCM_MJ |  | dPV | PO | 2021 | 34 | 2021 | 43 | Adnana Trica | Oana L. | Iulia T. | 33 | 46 | Done
| Received | 17.09.2019 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 529 |  | dP |  | dPV44 | PO | 2021 | 34 | 2021 | TBD | Ciobanu Aurelian | Oana L. | Iulia T. | TBD | TBD | Canceled
| Received | 17.09.2019 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 530 |  | Make_valves |  | dPV45 | PO | 2021 | 34 | 2021 | TBD | Ciobanu Aurelian | Oana L. | Iulia T. | TBD | TBD | Canceled
| Received | 15.07.2020 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 711 |  | CNH VIS3 |  | dPV | PO | 2020 | 35 | 2021 | 4 | Bugarschi Cristian | Anca M. | Alex M. |  |  | Done
| Received | 22.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VNI | 874 |  | AUDIXXXX |  | dPV | PO | 2021 | 35 | 2021 | 36 | Costel Cojocaru | Anca M. | Iulia T. | 35 | 36 | Done
| Received | 9.08.2021 | Continental-External | Continental-TSR |  | TBD | 1015 |  | SAT_HONDA_HRS9_MY23_GSAT |  | dDV | TBD | 2021 | 35 | 2021 | 36 | Novacescu Traian | Anca M. | Radu G. | 35 | 36 | Done
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 591 |  | SCCM |  | dPV | PO | 2021 | 35 | 2021 | 37 | Anghel A. | Carmen B. | Radu G. | 35 | 38 | Done
| Received | 30.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1037 |  | InternalAudit_DampHeatSteadyState |  | Pre-Comp. |  | 2021 | 36 | 2021 | 36 | Cojocariu Costel | Oana L. | Nick S. | 36 | 36 | Done
| Received | 30.08.2021 | Continental-Internal | Continental-SBZ (R&D) | N.A. | N.A | 1036 |  | InternalAudit_IceWaterShock |  | Pre-Comp. |  | 2021 | 36 | 2021 | 36 | Constantinescu Ion Dorin | Anca M. | Dan V. | 36 | 36 | Done
| Received | 30.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1038 |  | InternalAudit_MechanicalShock |  | Pre-Comp. |  | 2021 | 36 | 2021 | 36 | Bardasu Mihail | Oana L. | Tiberiu B. | 36 | 36 | Done
| Received | 17.08.2021 | Continental-External | External-VITESCO |  |  | 1028 |  | BMW_DCDC |  | Pre-Comp. | PO | 2021 | 36 | 2021 | 39 | Larion Catalin | Oana L. | Nick S. | 36 | 40 | Done
| Received | 7.04.2021 | Continental-External | Continental-TSR |  | VNI | 929 |  | TSR VNI CVS_SRR520KC20 |  | Pre-Comp. | TBD | 2021 | 36 | 2021 | 39 | Mardare Adrian | Anca M. | Radu G. | 36 | 40 | Done
| Received | 10.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 577 |  | AMR |  | dPV 06 | PO | 2020 | 36 | 2020 | 40 | Salcianu M. | Oana L. | Radu G. | 35 | 42 | Done
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 443 |  | EFP 1.3 |  | dPV | PO | 2020 | 36 | 2020 | 40 | Hategan I. | Oana L. | Radu G. | 36 | 41 | Done
| Received | 22.02.2021 | Continental-Internal | Continental-SBZ (R&D) |  | ADAS | 873 |  | SVS220VW1 |  | PV | PO | 2021 | 36 | 2021 | 47 | Rehberger Andreas | Oana L. | Iulia T. | 35 | 4 | Done
| Received | 09.06.2020 | Continental-External | Continental-ING |  | VED | 690 |  | ER100 BMW HBE |  | PV | PO | 2020 | 37 | 2021 | 8 | Stefan Schmailzl | Anca M. | Dan V. | 37 | 4 | Done
| Received | 13.09.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1060 |  | DB35 |  | Pre-Comp. | TBD | 2021 | 37 | 2021 | 37 | Florin Prioteasa | Carmen B. | Carmen B. | 37 | 37 | Done
| Received | 16.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1071 |  | SPA2GT |  | Pre-Comp. | DSIN-057266 | 2021 | 37 | 2021 | 37 | Nicu Stefanoaia | Carmen B. | Carmen B. | 37 | 37 | Done
| Received | 29.06.2021 | Continental-External | Continental-TSR |  | QL | 985 |  | QL FT_FCA AR949 AR952 |  | PV | PO | 2021 | 37 | 2021 | 37 | Jurcuta Dan | Anca M. | Tiberiu B. | 37 | 38 | Done
| Received | 13.09.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1059 |  | RAMSES |  | Pre-Comp. | DSIN-073814-3301 | 2021 | 37 | 2021 | 38 | Flaviu Musat | Carmen B. | Carmen B. | 37 | 38 | Done
| Received | 6.09.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1048 |  | CE_BMW 35UP |  | Pre-Comp. | eSign | 2021 | 37 | 2021 | 38 | Feisan Alexandra | Oana L. | Radu I. | 38 | TBD | Done
| Received | 9.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1057 |  | MK100 ESC HCU |  | Pre-Comp. | PO | 2021 | 37 | 2021 | 38 | Pop Dan | Anca M. | Tiberiu B. | 37 | 38 | Done
| Received | 16.09.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1058 |  | SVC22X |  | Pre-Comp. | ESign | 2021 | 37 | 2021 | 39 | Buteata Andrei | Carmen B. | Tiberiu B. | 38 | TBD | Done
| Received | 6.07.2021 | Continental-External | Continental-TSR |  | VNI | 990 |  | MFC525 KB Camera |  | dPV | PO | 2021 | 37 | 2021 | 42 | Mardare Adrian | Anca M. | Iulia T. | 37 | TBD | Done
| Received | 6.07.2021 | Continental-External | Continental-TSR |  | VNI | 991 |  | MFC525 KB System |  | dDV | PO | 2021 | 37 | 2021 | 42 | Mardare Adrian | Anca M. | Iulia T. | TBD | TBD | Canceled
| Received | 16.08.2021 | Continental-External | Continental-TSR |  |  | 1020 |  | FCA_FIAT356MCA |  |  | PO | 2021 | 37 | 2021 | 48 | Jurcuta Dan | Oana L. | Nick S. | 37 | 51 | Done
| Received | 9.06.2021 | Continental-External | Continental-TSR |  | VNI | 965 |  | TEA2+_Renault_Prolong_ReQuali |  | dPV | PO | 2021 | 38 | 2022 | 7 | Bugarschi Cristian | Anca M. | Radu I. | 38 | 5 | Done
| New | 23.09.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1083 |  | SVC220 Daimler |  | Pre-Comp. | PO | 2021 | 38 | 2021 | 38 | Munteanu Cristian | Carmen B. | Carmen B. | 38 | 38 | Done
| Received | 23.09.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1083 |  | SVC220 DAIMLER |  | Pre-Comp. | PO | 2021 | 38 | 2021 | 38 | Munteanu Cristian | Carmen B. | Carmen B. | 38 | 38 | Done
| Received | 21.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1078 |  | GW_LOW |  | Pre-Comp. | DSIN | 2021 | 38 | 2021 | 38 | Cojocariu Costel | Oana L. | Iulia T. | 38 | 38 | Done
| Received | 21.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1082 |  | Volvo HCM Re-Design |  | Pre-Comp. | N.A | 2021 | 38 | 2021 | 38 | Zaharov Adina | Anca M. | Radu I. | 39 | 39 | Done
| New | 21.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1079 |  |  |  | Pre-Comp. | DSIN | 2021 | 38 | 2021 | 38 | Cojocariu Costel | Oana L. | Nick S. | TBD | TBD | Canceled
| New | 21.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1080 |  |  |  | Pre-Comp. | DSIN | 2021 | 38 | 2021 | 38 | Cojocariu Costel | Oana L. | Nick S. | TBD | TBD | Canceled
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 444 |  | DCC3 |  | dPV | PO | 2020 | 38 | 2020 | 42 | Hategan I. | Oana L. | Radu G. | 38 | 42 | Done
| Received | 9.02.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | VNI | 859 |  | AUDI XXXX 16_dPV42 |  | dPV | PO | 2021 | 38 | 2021 | 43 | Cojocariu Costel | Anca M. | TBD. | TBD | TBD | Canceled
| Received | 11.06.2021 | Continental-External | Continental-ING |  | VED | 973 |  | Renault X82 |  | dPV | PO | 2021 | 38 | 2021 | 44 | Dallmeir Wolfgang | Anca M. | Dan V. | 38 | 44 | Done
| Received | 5.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1013 |  | ER120 Hyundai B-MPV |  | dDV | PO | 2021 | 39 | 2022 | 4 | Stefan Schmailzl | Anca M. | Dan V. | 39 | 5 | Done
| Received | 29.07.2021 | Continental-Internal | Continental-SBZ (R&D) |  | ADAS | 1000 |  | SVC_DAIMLER |  | dPV | PO | 2021 | 39 | 2022 | 4 | Zeljko Majstoro | Oana L. | Iulia T. | 42 | 5 | Done
| Received | 28.04.2020 | Continental-External | Continental-ING |  | VED | 661 |  | Mercedes Benz BR547 |  | DV | DSIN | 2020 | 39 | 2021 | 17 | Robert Arnold | Anca M. | Dan V. | 43 | 19 | Done
| New | 23.09.2021 | Continental-External | External-OSRAM |  |  | 1081 |  | HLI3 Daimler |  | Pre-Comp. | PO | 2021 | 39 | 2021 | 39 | Alina Deac | Carmen B. | Carmen B. | 39 | 40 | Done
| Received | 21.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1076 |  | Audit Db - MQB23_GW_BSL |  | Pre-Comp. | N.A | 2021 | 39 | 2021 | 39 | Cojocariu Costel | Oana L. | Nick S. | 39 | 39 | Done
| Received | 21.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1075 |  | Audit Nb: MQB19 GW High |  | Pre-Comp. | N.A | 2021 | 39 | 2021 | 39 | Cojocariu Costel | Oana L. | Nick S. | 39 | 39 | Done
| Received | 16.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1068 |  | AUDIT_Incercarea Ka ceata salina |  | Pre-Comp. | N.A | 2021 | 39 | 2021 | 39 | Cosmin Bratu | Anca M. | Radu G. | 39 | 39 | Done
| Received | 16.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1069 |  | AUDIT_Incercarea Kb_Ceata salina ciclica |  | Pre-Comp. | N.A | 2021 | 39 | 2021 | 39 | Cosmin Bratu | Anca M. | Radu G. | 39 | 39 | Done
| Received | 16.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1066 |  | AUDIT_Incercarea la temep min de depozitare |  | Pre-Comp. | N.A | 2021 | 39 | 2021 | 39 | Cojocariu Costel | Oana L. | Iulia T. | 39 | 39 | Done
| Received | 16.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1067 |  | AUDIT_IncercareaEc_cadere libera |  | Pre-Comp. | N.A | 2021 | 39 | 2021 | 39 | Cojocariu Costel | Oana L. | Iulia T. | 39 | 39 | Done
| Received | 15.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1061 |  | EXT_AUD_REN_IRT |  | Pre-Comp. | N.A | 2021 | 39 | 2021 | 39 | Eduard Saulescu | Anca M. | Dan V. | 39 | 39 | Done
| Received | 15.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1063 |  | EXT_AUD_REN_IWS |  | Pre-Comp. | N.A | 2021 | 39 | 2021 | 39 | Eduard Saulescu | Anca M. | Dan V. | 39 | 39 | Done
| Received | 15.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1062 |  | EXT_AUD_REN_WTS |  | Pre-Comp. | N.A | 2021 | 39 | 2021 | 39 | Eduard Saulescu | Anca M. | Dan V. | 39 | 39 | Done
| Received | 21.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1077 |  | Incercarea Cab -Caldura umeda, stare de echilibru |  | Pre-Comp. | N.A | 2021 | 39 | 2021 | 39 | Cojocariu Costel | Oana L. | Nick S. | 39 | 39 | Done
| Received | 07.09.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 741 |  | VDP High |  | dPV | PO | 2020 | 39 | 2020 | 39 | Hategan I. | Oana L. | Radu G. | 39 | 39 | Done
| Received | 16.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 1070 |  | Volvo HCM Re-Design |  | Pre-Comp. | N.A | 2021 | 39 | 2021 | 39 | Zaharov Adina | Anca M. | Radu I. | 39 | 39 | Done
| Received | 29.06.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 982 |  | GWM D-DE |  | DV | TBD | 2021 | 39 | 2021 | 40 | Dragos Roman | Anca M. | Tiberiu B. | TBD | TBD | Done
| Received | 7.09.2021 | Continental-External | Continental-TSR |  | VNI | 1050 |  | Scania Coo8 |  | dPV | PO | 2021 | 39 | 2021 | 42 | Stoiculescu Dorin | Anca M. | Nick S. | TBD | TBD | Done
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 592 |  | EFP 1.3 |  | dPV | PO | 2021 | 39 | 2021 | 43 | Bardasu Mihail | Carmen B. | Radu G. | 39 | 44 | Done
| Received | 10.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 578 |  | EFP 2.0 |  | dPV 06 | PO | 2020 | 39 | 2020 | 43 | Salcianu M. | Oana L. | Radu G. | 39 | 44 | Done
| Received | 28.05.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 955 |  | VW_MQB19_GW |  | dDV | PO | 2021 | 39 | 2021 | 44 | Costel Cojocaru | Oana L. | Iulia T. | 39 | 44 | Done
| Received | 29.07.2021 | Continental-Internal | Continental-SBZ (R&D) |  | ADAS | 999 |  | VW_SV210 |  | dPV | PO | 2021 | 39 | 2021 | 47 | Rechberger Andreas | Oana L. | Iulia T. | 42 | 1 | Done
| Received | 09.12.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 570 |  | EFP_2V2K |  | DV | DT | 2020 | 39 | 2020 | 51 | Ciocan A. | Oana L. | Ovidiu B. | - | - | Canceled
| Received | 15.07.2020 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 712 |  | PSA Ehud |  | dPV | PO | 2020 | 39 | 2021 | 51 | Burdulea Ionel | Oana L. | TBD. | TBD | TBD | Done
| Received | 27.01.2021 | Continental-Internal | Continental-SBZ (R&D) | TBD | BS | 820 |  | BMW_SP21_21_HSCU_SHZ |  | PV | PO | 2021 | 40 | 2022 | 12 | Burdulea Ionel | Mihaela C. | TBD. | TBD | TBD | Canceled
| Received | 4.10.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1093 |  | DQ200Gen2 |  | Pre-Comp. | eSign | 2021 | 40 | 2021 | 40 | Horia Enciu | Carmen B. | Carmen B. | 40 | 40 | Done
| Received | 4.10.2021 | Continental-Internal | Continental-SBZ (Plant) |  | ADAS | 1087 |  | SVC216TVL |  | Pre-Comp. | eSign | 2021 | 40 | 2021 | 40 | Bogdan Dobra | Carmen B. | Carmen B. | 40 | 40 | Done
| Received | 5.10.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1100 |  | SVC220Daimler |  | Pre-Comp. | eSign | 2021 | 40 | 2021 | 40 | Munteanu Cristian | Carmen B. | Carmen B. | 40 | 40 | Done
| Received | 1.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1088 |  | MK 120 |  | Pre-Comp. | DSIN | 2021 | 40 | 2021 | 40 | Oancea Ciprian | Anca M. | Radu I. | 40 | 41 | Done
| New | 5.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1102 |  | AUD_PPE_SCU |  | dPV | PO | 2021 | 40 | 2021 | 42 | Costel Cojocaru | Oana L. | Iulia T. | 40 | 42 | Done
| New | 27.08.2021 | TBD | TBD |  | TBD | 1033 |  | Volvo IC08 |  | Pre-Comp. | TBD | 2021 | 40 | 2021 | 46 | TBD | TBD | TBD. |  |  | Canceled
| Received | 13.08.2020 | Continental-External | Continental-ULM |  | ADAS | 737 |  | WLCSP_dPV |  | dPV | PO | 2020 | 40 | 2021 | 52 | Stern Johannes | Oana L. | TBD. | TBD | TBD | Done
| New | 30.06.2021 | Continental-External | TBD |  | VNI | 987 |  | IAS_VNI_CE_SP21_21_DCU_TSG |  | PV | PO | 2021 | 41 | 2021 | 4 | Davidescu Madalina | Oana L. | TBD. |  |  | Canceled
| Received | 11.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1109 |  | Cairs GLV |  | Pre-Comp. | DSIN-071041 | 2021 | 41 | 2021 | 41 | Vasi Dumitriu | Carmen B. | Carmen B. | 41 | 41 | Done
| Received | 5.10.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1101 |  | DQ200Gen2 |  | Pre-Comp. | ESign | 2021 | 41 | 2021 | 41 | Capatana Ovidiu | Carmen B. | Carmen B. | 41 | 41 | Done
| Received | 6.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1106 |  | Geely |  | Pre-Comp. |  | 2021 | 41 | 2021 | 41 | Nicu Stefanoaia | Carmen B. | Carmen B. | 41 | 41 | Done
| Received | 13.10.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1114 |  | PLGM Daimler |  | Pre-Comp. | eSign | 2021 | 41 | 2021 | 41 | Grig Ionita | Carmen B. | Carmen B. | 41 | 41 | Done
| Received | 6.10.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1107 |  | SVC220Daimler |  | Pre-Comp. | ESign | 2021 | 41 | 2021 | 41 | Munteanu Cristian | Carmen B. | Carmen B. | 41 | 41 | Done
| Received | 3.02.2021 | Non-Continental | External-Schaffler |  | N.A | 849 |  | Schaeffler_06IPtests |  | Pre-Comp. | PO | 2021 | 41 | 2021 | 41 | Calburean Oliver-Gheorghe | Oana L. | Nick S. | 41 | 44 | Done
| Received | 6.10.2021 | Continental-External | External-VITESCO |  | TBD | 1103 |  | ES PL E_EMS314x |  | dPV | PO | 2021 | 41 | 2021 | 42 | Pistiriga Vlad | Oana L. | Radu G. | 42 | 43 | Done
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 594 |  | VASCO |  | dPV | PO | 2021 | 41 | 2021 | 43 | Anghel A. | Carmen B. | Radu G. | 41 | 44 | Done
| Received | 01.10.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 759 |  | EFP 1.3 Hybrid |  | dPV | PO | 2020 | 41 | 2020 | 43 | Hategan I. | Oana L. | Ovidiu B. | 42 | 43 | Done
| Received | 05.12.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 568 |  | FCA MY23 |  | PV | PO | 2021 | 41 | 2021 | 48 | TBD | Carmen B. | Radu G. | TBD | TBD | Canceled
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 598 |  | MY23_WL_SRT |  | PV | PO | 2021 | 41 | 2021 | 48 | TBD | Oana L. | Radu G. | - | - | Canceled
| Received | 9.06.2021 | Non-Continental | External-VITESCO |  | N.A | 964 |  | QCU3 |  | Pre-Comp. | PO | 2021 | 41 | 2021 | 49 | Tincu Tiberiu | Oana L. | Radu I. | 32 | 5 | Done
| Received | 31.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1040 |  | MiniMAB |  | dPV | PO | 2021 | 42 | 2022 | 2 | Stefan Schmailzl | Anca M. | Dan V. | 43 | 4 | Done
| Received | 07.08.2020 | Non-Continental | External-VITESCO |  | N.A | 722 |  | DKG250 Gen1 |  | PV | PO | 2020 | 42 | 2021 | 2 | Dante Salinas | Anca M. | Radu I. | TBD | TBD | Done
| Received | 24.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 1084 |  | CVC LOW |  | Pre-Comp. | PO | 2021 | 42 | 2021 | 42 | Stuparu Catalin | Carmen B. | TBD. |  |  | Canceled
| New | 14.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1115 |  | CE_VOL_SPA2_22_TCM |  | DV | TBD | 2021 | 42 | 2021 | 43 | Arsene Ionela | Oana L. | Dan V. | TBD | TBD | Canceled
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 445 |  | SCCM |  | dPV | PO | 2020 | 42 | 2020 | 44 | Anghel A. | Oana L. | Ovidiu B. | 43 | 45 | Done
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 593 |  | EFP 2.0 |  | dPV | PO | 2021 | 42 | 2021 | 46 | Salcianu Mihai | Carmen B. | Radu G. | 42 | 47 | Done
| Received | 6.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 1108 |  | SCCU SAF BMW K50 |  | dPV | PO | 2021 | 42 | 2021 | 51 | Bardasu Mihail | Carmen B. | Radu G. | 42 | 1 | Done
| Received | 3.09.2021 | Continental-External | Continental-TSR |  | HMI | 1042 |  | 213 Mopf |  | dPV | PO | 2021 | 43 | 2022 | 3 | Cozmescu Alina Maria | Oana L. | Nick S. | 43 | 5 | Done
| Received | 20.05.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 952 |  | VW_MQB23_FCM_BSL |  | DV | Dsin | 2021 | 43 | 2022 | 9 | Costel Cojocaru | Oana L. | Iulia T. | 43 | 11 | Done
| Received | 29.10.2020 | Continental-External | Continental-ING |  | VED | 774 |  | Hyundai OSPE IPB MNL |  | PV | PO | 2020 | 43 | 2021 | 4 | Schmailzl S. | Anca M. | TBD. | TBD | TBD | Done
| Received | 13.08.2020 | Continental-External | Continental-ING |  | VED | 728 |  | ER100 Hyundai OS HP Plant SHA |  | PV | PO | 2020 | 43 | 2021 | 6 | Schmailzl S. | Anca M. | Dan V. | 44 | 8 | Done
| Received | 13.08.2020 | Continental-External | Continental-ING |  | VED | 727 |  | ER100 Hyundai OS PE IPB Plant CUA |  | PV | PO | 2020 | 43 | 2021 | 6 | Schmailzl S. | Anca M. | Dan V. | 44 | 8 | Done
| Received | 13.08.2020 | Continental-External | Continental-ING |  | VED | 726 |  | ER100 Hyundai OS PE IPB Plant SHA |  | PV | PO | 2020 | 43 | 2021 | 6 | Schmailzl S. | Anca M. | Dan V. | 44 | 8 | Done
| Received | 21.04.2020 | Continental-External | Continental-ING |  | VED | 659 |  | ER100 Hyundai ESC Base B-MPV |  | DV | DT | 2020 | 43 | 2021 | 9 | Schmailzl S. | Anca M. | Dan V. | 43 | 8 | Done
| Received | 21.04.2020 | Continental-External | Continental-ING |  | VED | 658 |  | ER100 Hyundai IPB Su2id |  | DV | DT | 2020 | 43 | 2021 | 9 | Schmailzl S. | Anca M. | Dan V. | 43 | 8 | Done
| Received | 18.05.2020 | Continental-External | Continental-TSR | GM | PSS | 678 |  | gSat_GM_SDM41_SAT |  | DV | PO | 2020 | 43 | 2021 | 10 | Abraham Andreea | Anca M. | Nick S. | 45 | 18 | Done
| Received | 18.05.2020 | Continental-External | Continental-TSR | GM | PSS | 679 |  | pSat_GM_SDM41_SAT |  | DV | PO | 2020 | 43 | 2021 | 10 | Abraham Andreea | Anca M. | Iulia T. | 45 | 18 | Done
| Received | 27.10.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1127 |  | MPS6 |  | Pre-Comp. | eSign | 2021 | 43 | 2021 | 43 | Florin Prioteasa | Carmen B. | Carmen B. | 43 | 43 | Done
| Received | 01.10.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 761 |  | VDP HIGH |  | dPV | PO | 2020 | 43 | 2020 | 43 | Hategan I. | Oana L. | Ovidiu B. | 43 | 43 | Done
| Received | 7.09.2021 | Continental-External | Continental-TSR |  | PSS | 1049 |  | _AMS PSS_BSZ6D GWM |  | Pre-Comp. | PO | 2021 | 43 | 2021 | 47 | Iasmin Stiopu | Anca M. | Radu G. | 44 | 47 | Done
| Received | 26.10.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1126 |  | SVC Daimler |  | Pre-Comp. | e-Sign | 2021 | 44 | 2021 | 44 | Andrei Buteata | Carmen B. | Radu G. | 44 | 45 | Done
| Received | 18.10.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1117 |  | Daimler MFA2 |  | Pre-Comp. | eSign | 2021 | 44 | 2021 | 44 | Andrei Alexandru | Carmen B. | Carmen B. | 42 | 42 | Done
| Received | 15.10.2021 | Non-Continental | TBD |  | N.A | 1116 |  | Kendrion_pre-compliance x-ray |  | Pre-Comp. | O6211147 | 2021 | 44 | 2021 | 44 | Adrian Herciu | Carmen B. | Carmen B. | 42 | 43 | Done
| New | 1.11.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1133 |  | SVC220 Daimler |  | Pre-Comp. | eSign | 2021 | 44 | 2021 | 44 | Munteanu Cristian | Carmen B. | Carmen B. | 44 | 44 | Done
| Received | 07.09.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 740 |  | CVC HIGH2 |  | dPV 01 | PO | 2020 | 44 | 2020 | 44 | Ghise S. | Oana L. | Ovidiu B. | 44 | 45 | Done
| Received | 20.10.2021 | Continental-External | Continental-TSR |  | ADAS | 1120 |  | ICR1XX |  | Pre-Comp. | TBD | 2021 | 44 | 2021 | 44 | Daniel Ioaniciu | Oana L. | Radu G. | 42 | 42 | Done
| New | 1.10.2021 | Non-Continental | External-Schaffler |  | N.A | 1089 |  | P-084362-02-06-24-0-TS100 |  | Pre-Comp. | PO | 2021 | 44 | 2021 | 44 | Soare Ionut Tudor | Oana L. | Nick S. | TBD | TBD | Canceled
| Received | 8.06.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 961 |  | SAIC S11L |  | DV | PO | 2021 | 44 | 2021 | 44 | Dragos Roman | Anca M. | Tiberiu B. | 44 | 45 | Done
| Received | 26.10.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1125 |  | SSG_BMW |  | Pre-Comp. | e-Sign | 2021 | 44 | 2021 | 45 | Alina Deac | Carmen B. | Radu G. | 44 | 46 | Done
| New | 1.10.2021 | Non-Continental | External-Schaffler |  | N.A | 1090 |  | P-084362-02-06-24-06_Heat_humidity_test |  | Pre-Comp. | PO | 2021 | 44 | 2021 | 45 | Soare Ionut Tudor | Oana L. | Nick S. | TBD | TBD | Canceled
| Received | 6.09.2021 | Non-Continental | External-Schaffler |  | N.A | 1043 |  | P-085496-02-06-55 |  | Pre-Comp. | PO | 2021 | 44 | 2021 | 45 | Calburean Oliver-Gheorghe | Oana L. | Nick S. | 44 | 45 | Done
| New | 17.09.2021 | Non-Continental | External-Schaffler |  | N.A | 1073 |  | TS200 |  | Pre-Comp. | N.A | 2021 | 44 | 2021 | 45 | Soare Ionut Tudor | Oana L. | Nick S. | TBD | TBD | Canceled
| New | 17.09.2021 | Non-Continental | External-Schaffler |  | N.A | 1072 |  | Rez-VIB-MS |  | Pre-Comp. | N.A | 2021 | 44 | 2021 | 46 | Soare Ionut Tudor | Oana L. | Tiberiu B. | TBD | TBD | Canceled
| Received | 13.04.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 931 |  | TTTech 2300 |  | DV | DSIN | 2021 | 44 | 2021 | 48 | Tutui Daniel | Anca M. | Iulia T. | TBD | TBD | Canceled
| Received | 30.06.2021 | Continental-External | TBD |  | VNI | 986 |  | IAS_VNI_MAG_X07_13_SRM_RSA_Edison |  | dPV | PO | 2021 | 44 | 2021 | 50 | Madalina Davidescu | Oana L. | Nick S. | 44 | 49 | Done
| Received | 07.05.2020 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 670 |  | Make Valves dPV60 |  | Pre-Comp. | PO | 2020 | 45 | 2021 | 4 | Aurelian Ciobanu | Oana L. | Iulia T. | TBD | TBD | Done
| Received | 16.09.2020 | Continental-External | Continental-TSR |  | VNI | 745 |  | TEA2+RT Prolongation |  | dPV | PO | 2020 | 45 | 2021 | 12 | Bugarschi Cristian | Anca M. | Nick S. | 45 | 13 | Done
| Received | 21.10.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1121 |  | Daimler |  | Pre-Comp. | eSign | 2021 | 45 | 2021 | 45 | Prioteasa Florin | Carmen B. | Carmen B. | 42 | 42 | Done
| Received | 19.10.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 1119 |  | DQ200 |  | Pre-Comp. | eSign | 2021 | 45 | 2021 | 45 | Radu Giurgiu | Carmen B. | Carmen B. | 42 | 42 | Done
| New | 13.10.2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 1113 |  | DCC4 |  | Pre-Comp. | DSIN-070265 | 2021 | 45 | 2021 | 47 | Sorin Ghise | Carmen B. | Radu G. | 45 | 47 | Done
| New | 23.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 1029 |  | EFP 2V2K |  | dDV | DSIN-072665. | 2021 | 45 | 2021 | 49 | Salcianu Mihai | Carmen B. | Radu G. | TBD | TBD | Canceled
| Received | 13.01.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 596 |  | VADA |  | dPV | PO | 2021 | 45 | 2021 | 49 | TBD | Oana L. | TBD. | TBD | TBD | Canceled
| Received | 29.10.2020 | Non-Continental | External-VITESCO |  | N.A | 775 |  | CPC_NG |  | Pre-Comp. | PO | 2020 | 46 | 2021 | 16 | Lazar Monica | Oana L. | Nick S. | 46 | 18 | Done
| Received | 28.10.2019 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 549 |  | HHT VX1 PECU |  | Pre-Comp. | PO | 2020 | 46 | 2021 | 20 | Bratu Cosmin | Anca M. | Radu G. | 49 | 2 | Done
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 446 |  | VASCO |  | dPV | PO | 2020 | 46 | 2020 | 49 | Salcianu M. | Oana L. | Radu G. | 44 | 49 | Done
| Received | 28.10.2020 | Continental-Internal | Continental-SBZ (R&D) |  | N.A | 772 |  | SDT1 |  | Pre-Comp. | DSPN-072327 | 2020 | 47 | 2021 | 9 | Woltz Andrei | Oana L. | Radu G. | 47 | 11 | Done
| Received | 12.08.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 516 |  | CVC_Low |  | dDV | DT | 2020 | 47 | 2021 | 24 | Stuparu C. | Oana L. | Radu G. | - | - | Canceled
| Received | 22.02.2019 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 447 |  | VADA |  | dPV | PO | 2020 | 47 | 2020 | 51 | Bardasu M. | Oana L. | Radu G. | 46 | 51 | Done
| Received | 05.10.2020 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 762 |  | MakeValves_PWR |  | dPV61 | PO | 2020 | 48 | 2021 | 1 | Ciobanu Aurelian | Oana L. | TBD. | TBD | TBD | Done
| Received | 06.11.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 786 |  | SPC+ |  | dPV 03 | PO | 2020 | 48 | 2021 | 2 | Hategan I. | Oana L. | Radu G. | 48 | TBD | Done
| Received | 19.10.2020 | Continental-External | Continental-ING |  | PSS | 766 |  | PSS_DQM |  | dPV | PO | 2020 | 48 | 2021 | 5 | Greb Thomas | Oana L. | Nick S. | 52 | 5 | Done
| Received | 20.11.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 795 |  | CVC Low |  | Pre-Comp. | DSIN-055988 | 2020 | 48 | 2020 | 49 | Stuparu C. | Oana L. | Radu G. | 48 | 48 | Done
| New | 19.03.2021 | Non-Continental | External-VITESCO |  | N.A | 898 |  | EXT_VT_HV_DCDC |  | DV | PO | 2021 | 49 | 2022 | 7 | Chiriac Radu | Oana L. |  |  |  | Canceled
| Received | 23.11.2020 | Continental-External | Continental-TSR |  | VNI | 796 |  | CVAM_TEA2+_SIDH |  | dPV | PO | 2020 | 49 | 2021 | 12 | Bugarschi Cristian | Oana L. | Alex M. | 49 | 22 | Done
| Received | 19.11.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 791 |  | CVC |  | dPV | PO | 2020 | 49 | 2020 | 50 | Ghise S. | Oana L. | Radu G. | 48 | 50 | Done
| Received | 05.11.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 780 |  | SCCM |  | dPV | PO | 2020 | 49 | 2020 | 50 | Anghel A. | Oana L. | Radu G. | 48 | 50 | Done
| Received | 19.10.2020 | Non-Continental | External-OSRAM |  | N.A | 767 |  | Volvo_HCM |  | dDV | PO | 2020 | 51 | 2021 | 10 | Zaharov Adina | Oana L. | Radu I. | 51 | 14 | Done
| Received | 06.11.2020 | Continental-Internal | Continental-SBZ (R&D) |  | PSS | 787 |  | SPCh |  | dPV | PO | 2020 | 52 | 2021 | 2 | Hategan I. | Oana L. | Radu G. | - | - | Canceled
| Received | 16.06.2021 | Continental-Internal | Continental-SBZ (Plant) |  | VNI | 975 |  | MFC430 _xRay |  | Pre-Comp. | TBD | 2021 | TBD | 2021 | TBD | Anca Puscas | Carmen B. | Carmen B. | TBD | TBD | Canceled
| New | 17.09.2021 | Non-Continental | External-Schaffler |  | N.A | 1074 |  | 1000TS |  | Pre-Comp. | N.A | 2021 | TBD | 2021 | TBD | Soare Ionut Tudor | Oana L. | TBD. |  |  | Canceled
| New | 27.08.2021 | Continental-External | Continental-TSR |  | VNI | 1032 |  | CVS_ARS510TN12 |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD. |  |  | Canceled
| New | 15.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1064 |  | MakeValves_dPV75 |  | dPV | PO | TBD | TBD | TBD | TBD | Ciobanu Aurelian | Oana L. | TBD. |  |  | Canceled
| New | 15.09.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VNI | 1065 |  | MakeValves_dPV79 |  | dPV | PO | TBD | TBD | TBD | TBD | Ciobanu Aurelian | Oana L. | TBD. |  |  | Canceled
| New | 27.08.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 1035 |  | MK100 ESC HCU |  | Pre-Comp. | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD. |  |  | Canceled
| New | 18.06.2021 | Continental-Internal | Continental-SBZ (R&D) |  | VED | 976 |  | MK100_granitura etansare |  | Pre-Comp. | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  |  |  | Canceled
| New | 11.03.2021 | Continental-External | Continental-TSR |  | N.A | 894 |  | VT_GPA T85 |  | DV | TBD | TBD | TBD | TBD | TBD |  | Oana L. |  |  |  | Canceled
| New | 19.08.2021 | Continental-Internal |  |  |  | 1024 |  | ER100 |  | dPV | [6 empty] | Anca M. |  |  |  | Canceled
| New | 17.08.2021 | Continental-Internal |  |  | VED | 1023 |  | ER100 Suzuki YXA |  | dPV | [6 empty] | Alex I. |  |  |  | Canceled
| New | 1.09.2021 | Continental-Internal | Continental-SBZ (Plant) |  | ADAS | 1041 |  | Plant_ADAS_SVC_Daimler |  | Pre-Comp. | PO | 2021 |  |  |  |  | Oana L. | TBD. |  |  | Canceled
|  |  | AM | AM
BS
AN
he[a]t-CES
UX
N.A
SAM-PSS
QL
SAM-VED
VITESCO
VNI
AM
BS
AN
he[a]t-CES
UX
N.A
PSA
SAM-PSS
QL
SAM-VED
VITESCO
VNI
Note on B5: Cell "New" = a New Qualification Test is added by the Validation Team; Cell "Modified" = The Validation Team changes something (e.g. ID, Planning, Phase, etc.) to the Qualification Test. Cell "Received" = The REL Team Leader inform the Validation Team that the Qualification Test is taken over by the Reliability Team.
Note on D5: Continental-Internal: -Continental-SBZ (R&D); -Continetal-SBZ (Plant); INFO: It's applies only to Continental Sibiu (R&D and Plant). Continental-External: e.g: - Continental-TSR; - Continental-IAS - Continental-KRB; - Continental-SBA; - Continental-BBU; - Continetal-ULM - Continental-ING - etc.; INFO: It can be eny Continental location. Non-Continental: e.g: - EXTERNAL-Vitesco; - EXTERNAL-Schaffler; - EXTERNAL-Osram; - etc.; INFO: Are customers who aren't part of the Continental Group.
Note on E5: Continental-Internal: -Continental-SBZ (R&D); -Continental-SBZ (Plant); INFO: It's applies only to Continental Sibiu (R&D and Plant). Continental-External: e.g: - Continental-TSR; - Continental-IAS - Continental-KRB; - Continental-SBA; - Continental-BBU; - Continetal-ULM - Continental-ING - etc.; INFO: It can be eny Continental location. Non-Continental: e.g: - EXTERNAL-Vitesco; - EXTERNAL-Schaffler; - EXTERNAL-Osram; - etc.; INFO: Are customers who aren't part of the Continental Group.
Note on Y5: The cell is completed by REL Team Leader involving the Reliability Test Responsible after the Qualification Test ended.
Note on AB5: The cell is completed by Quality Responsible involving the Reliability Test Responsible after the Test Reports were sent to the Project Team.
Note on AC5: The cell is completed by Quality Responsible involving the Reliability Test Responsible after the Test Reports were sent to the Project Team.
Note on AD5: The cell is completed by Quality Responsible involving the Reliability Test Responsible after the Test Reports were sent to the Project Team.
Note on AE5: The cell is completed by Quality Responsible involving the Reliability Test Responsible after the Test Reports were sent to the Project Team.
Note on AF5: The cell is completed by Quality Responsible involving the Reliability Test Responsible after the Test Reports were sent to the Project Team.
Note on AG5: The cell is completed by Quality Responsible involving the Reliability Test Responsible after the Test Reports were sent to the Project Team.
Note on AH5: The cell is completed by Quality Responsible involving the Reliability Test Responsible after the Test Reports were sent to the Project Team.
Note on AI5: The cell is completed by Quality Responsible involving the Reliability Test Responsible after the Test Reports were sent to the Project Team.
Note on AJ5: The cell is completed by Quality Responsible involving the Reliability Test Responsible after the Test Reports were sent to the Project Team.
Note on AK5: The cell is completed by Quality Responsible involving the Reliability Test Responsible after the Test Reports were sent to the Project Team.
Note on AL5: The cell is completed by Quality Responsible involving the Reliability Test Responsible after the Test Reports were sent to the Project Team.
Note on AM5: The cell is completed by Quality Responsible involving the Reliability Test Responsible after the Test Reports were sent to the Project Team.
Note on AN5: The cell is completed by Quality Responsible involving the Reliability Test Responsible after the Test Reports were sent to the Project Team.
Note on O11: Mosteanu, Anca-Maria (uib45904): Initial era CW18 2021
Note on Q11: Mosteanu, Anca-Maria (uib45904): Initial era CW30 2021
Note on O15: Mosteanu, Anca-Maria (uib45904): Initial era CW12 2021
Note on O22: Florea, Adriana-Petronela02 (uic79200): initial: CW25
Note on O47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Initial CW41
Note on O48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Initial CW41 2021
Note on O51: Mosteanu, Anca-Maria (uib45904): Initial CW44
Note on O52: Mosteanu, Anca-Maria (uib45904): Initial CW44
Note on O53: Mosteanu, Anca-Maria (uib45904): Initial CW44
Note on O54: Mosteanu, Anca-Maria (uib45904): Initial CW44
Note on O70: Mosteanu, Anca-Maria (uib45904): Initial era Cw47
Note on O83: Mosteanu, Anca-Maria (uib45904): Initial CW09
Note on E115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GDL
Note on I195: Balan, Carmen02: a fost prima data R02208
Note on I196: Balan, Carmen02: a fost trecut prima data ca si R02209
Note on O236: Mosteanu, Anca-Maria (uib45904): Initial CW09
Note on O237: Mosteanu, Anca-Maria (uib45904): Initial CW44
Note on O238: Mosteanu, Anca-Maria (uib45904): Initial CW44
Note on O239: Mosteanu, Anca-Maria (uib45904): Initial CW44
Note on O240: Mosteanu, Anca-Maria (uib45904): Initial CW44
Note on I245: Balan, Carmen02: R02250 a fost initial
Note on O355: Florea, Adriana-Petronela02 (uic79200): initial CW34
Note on O403: Mosteanu, Anca-Maria (uib45904): Initial era CW06
Note on W410: Mosteanu, Anca-Maria (uib45904): Au fost doar vibratii
Note on Q415: Mosteanu, Anca-Maria (uib45904): Initial era CW28
Note on O431: Mosteanu, Anca-Maria (uib45904): Initial era CW09
Note on Q431: Mosteanu, Anca-Maria (uib45904): Initial era CW34
Note on O457: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: planificat initial in cw39
Note on O459: Mosteanu, Anca-Maria (uib45904): Initial era CW10
Note on Q459: Mosteanu, Anca-Maria (uib45904): Initial era CW29
Note on O460: Mosteanu, Anca-Maria (uib45904): Initial era CW10
Note on Q460: Mosteanu, Anca-Maria (uib45904): Initial era CW29
Note on O469: Florea, Adriana-Petronela02 (uic79200): Initial: CW11
Note on O471: Mosteanu, Anca-Maria (uib45904): Initial CW15
Note on Q471: Mosteanu, Anca-Maria (uib45904): Initial CW17
Note on O473: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CW 14 initial
Note on O474: Mosteanu, Anca-Maria (uib45904): Initial : CW14
Note on Q474: Mosteanu, Anca-Maria (uib45904): Initial CW23
Note on O490: Florea, Adriana-Petronela02 (uic79200): Initial a fost CW17
Note on O491: Mosteanu, Anca-Maria (uib45904): Initial era CW14
Note on O492: Mosteanu, Anca-Maria (uib45904): Initial era CW14
Note on O502: Mosteanu, Anca-Maria (uib45904): Initial era CW16
Note on O510: Florea, Adriana-Petronela02 (uic79200): Initial era CW18
Note on O511: Mosteanu, Anca-Maria (uib45904): Initial CW15
Note on Q511: Mosteanu, Anca-Maria (uib45904): Initial CW25
Note on O515: Florea, Adriana-Petronela02 (uic79200): Initial: CW14
Note on Q515: Florea, Adriana-Petronela02 (uic79200): Initial: CW14
Note on O517: Cernatescu, Mihaela-Nicoleta (uib54238): Initial: CW13
Note on O533: Florea, Adriana-Petronela02 (uic79200): Initial: cw14
Note on Q533: Florea, Adriana-Petronela02 (uic79200): initial CW16
Note on O534: Florea, Adriana-Petronela02 (uic79200): Initial CW14
Note on Q534: Florea, Adriana-Petronela02 (uic79200): Initial CW16
Note on O535: Mosteanu, Anca-Maria (uib45904): Initial CW05
Note on G546: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IID
Note on O564: Florea, Adriana-Petronela02 (uic79200): Initial CW29
Note on O585: Mosteanu, Anca-Maria (uib45904): Initial CW20
Note on Q585: Mosteanu, Anca-Maria (uib45904): Initial CW21
Note on O589: Mosteanu, Anca-Maria (uib45904): Initial CW31
Note on O602: Mosteanu, Anca-Maria (uib45904): Initial CW31
Note on Q602: Mosteanu, Anca-Maria (uib45904): Initial CW34
Note on O605: Florea, Adriana-Petronela02 (uic79200): initial CW31
Note on Q671: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: initial CW37
Note on O705: Mosteanu, Anca-Maria (uib45904): Initial CW23
Note on Q705: Mosteanu, Anca-Maria (uib45904): Initial CW35
Note on E706: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IAS

## QL SBZ REL Tests Tracking
|  |  | ● | REL Team |  | CA 1014449-A13-01
QL SBZ REL Tests Tracking
● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ●
No | BA Name | Unique Identification No. | Project Name | Test Order/ Report No. | Type of qualification | Test method/name | QL Test Responsible | Test Schedule (CW - CW) | Test Start (dd.mm.yyyy) | Test Start (CW) | Test End (dd.mm.yyyy) | Test End (CW) | Test Status | Functional Test Responsible | Result of the Functional Check | Comments
1 | AN | R02164 | Vol_SPA2_22_TCM_TRM | R02164-SBZ–01 | Pre-compliance | Rapid change of temperature | Radu I. | - | 2022-05-10 | 19 | 2022-05-31 | 22 | Done | Arsene Catalina | N/A
2 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -01 | PV | High temperature storage | Radu I. | CW14-16 | 2022-04-08 | 14 | 2022-04-29 | 17 | Done | Srdjan Struharik | N/A
3 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ-02 | PV | Temperature cycling with specified temperature change rate | Radu I. | CW17-18 | 2022-05-02 | 18 | 2022-05-12 | 19 | Done | Srdjan Struharik | N/A
4 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -03 | PV | Rapid change of temperature with specified transition duration | Radu I. | CW19-20 | 2022-05-13 | 19 | 2022-06-03 | 22 | Done | Srdjan Struharik | N/A
5 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -04 | PV | Random and sinusoidal vibrations and temperature cycling | Ion C. | CW21 | 2022-06-22 | 25 | 2022-06-27 | 26 | Done | Srdjan Struharik | N/A
6 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -05 | PV | Composite temperature/ humidity cycle test | Radu I. | CW22-23 | 2022-07-01 | 26 | N.A | TBD | Ongoing | Srdjan Struharik | N/A
7 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -06 | PV | Damp heat, steady state | Radu I. | CW24-26 | N.A | TBD | N.A | TBD | Next | Srdjan Struharik | N/A
8 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -07 | PV | Low temperature storage | Radu I. | CW27 | N.A | TBD | N.A | TBD | Next | Srdjan Struharik | N/A
9 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -08 | PV | Low temperature operation | Radu I. | CW14 | 2022-04-14 | 15 | 2022-04-15 | 15 | Done | Srdjan Struharik | N/A
10 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -09 | PV | High temperature operation | Radu I. | CW14 | 2022-04-15 | 15 | 2022-04-16 | 15 | Done | Srdjan Struharik | N/A
11 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -10 | PV | Temperature steps test | Radu I. | CW15 | 2022-04-18 | 16 | 2022-04-19 | 16 | Done | Srdjan Struharik | N/A
12 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -11 | PV | Mechanical shock test | Ion C. | CW16 | 06/17/202 | 24 | 2022-06-17 | 24 | Done | Srdjan Struharik | N/A
13 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -12 | PV | Drop test | Radu I. | CW16 | 2022-06-21 | 25 | 2022-06-21 | 25 | Done | Srdjan Struharik | N/A
14 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -13 | PV | Connector pins push/pull | Daniel I. | CW16 | 2022-06-21 | 25 | 2022-06-27 | 26 | Done | Srdjan Struharik | N/A
15 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -14 | PV | Chemical loads | Radu I. | CW17 | N.A | TBD | N.A | TBD | Next | Srdjan Struharik | N/A
16 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -15 | PV | IP -Protection Against Foreign Objects | Radu I. | CW18 | N.A | TBD | N.A | TBD | Next | Srdjan Struharik | N/A
17 | AN | R02074 | CCN S2 Asia_VOL_SPA2_22_TCM_TRM | R02074 – SBZ -16 | PV | IP -Water intrusion | Radu I. | CW18 | N.A | TBD | N.A | TBD | Next | Srdjan Struharik | N/A
18 | AN | R02188 | AUD_PPE21 | R02188-SBZ 01 | PV | L-02 High-temperature durability testing | Iulia T. | CW15 | 2022-04-13 | 15 | 2022-05-01 | 17 | Done | Schmailzl Marco
19 | AN | R02188 | AUD_PPE21 | R02188-SBZ 02 | PV | L-03 Temperature cycle durability testing | Iulia T. | CW21 | 2022-05-26 | 21 | 2022-06-07 | 23 | Done | Schmailzl Marco
20 | AN | R02188 | AUD_PPE21 | R02188-SBZ 03 | PV | K-02 Incremental temperature test | Iulia T. | CW21 | 2022-06-10 | 23 | 2022-06-13 | 24 | Done | Schmailzl Marco
21 | External | R02038 | PCU48_ IWS_DCDC | R02038-SBZ–01 | Pre-compliance | Test A: Cold, Test B: Dry Heat | Nick S. | CW14 | 2022-04-06 | 14 | 2022-04-08 | 14 | Done | Pantiru Radu
22 | External | R02038 | PCU48_ IWS_DCDC | R02038-SBZ–02 | Pre-compliance | Temperature step test | Nick S. | CW15 | 2022-04-11 | 15 | 2022-04-13 | 15 | Done | Pantiru Radu
23 | External | R02038 | PCU48_ IWS_DCDC | R02038-SBZ–03 | Pre-compliance | Test Ea: Shock | Daniel I. | CW15 | 2022-04-03 | 13 | 2022-04-21 | 16 | Done | Pantiru Radu | Pass
24 | External | R02038 | PCU48_ IWS_DCDC | R02038-SBZ–04 | Pre-compliance | Test Fh: Random | Daniel I. | CW15 | 2022-04-03 | 13 | 2022-04-21 | 16 | Done | Pantiru Radu | Pass
25 | External | R02038 | PCU48_ IWS_DCDC | R02038-SBZ–05 | Pre-compliance | Temperature step test | Nick S. | CW17 | 2022-04-27 | 17 | 2022-04-29 | 17 | Done | Pantiru Radu
26 | SAM-VED | R02211 | Chrysler JT | R02211-SBZ-01 | PV | I9 Entry | Catalin S. | CW15 | 2022-04-12 | 15 | 2022-04-13 | 15 | Done | George Cebuc
27 | SAM-VED | R02211 | Chrysler JT | R02211-SBZ-02 | PV | HTHE | Catalin S. | CW15 | 2022-04-13 | 15 | 2022-05-26 | 21 | Done | George Cebuc
28 | SAM-VED | R02211 | Chrysler JT | R02211-SBZ-03 | PV | I9 Exit | Catalin S. | CW15 - CW21 | 2022-05-26 | 21 | 2022-05-27 | 21 | Done | George Cebuc
29 | SAM-VED | R02141 | ER100 Chrysler MP MY21 Base Pace 6_PV | R02141-SBZ-01 | PV | I9 Entry, Leg A | Catalin S. | CW 17 | 2022-04-26 | 17 | 2022-04-27 | 17 | Done | Alexandru Comsa
30 | SAM-VED | R02141 | ER100 Chrysler MP MY21 Base Pace 6_PV | R02141-SBZ-02 | PV | TS | Catalin S. | CW 17 - CW | 2022-04-27 | 17 | 2022-06-24 | 25 | Done | Alexandru Comsa
31 | SAM-VED | R02141 | ER100 Chrysler MP MY21 Base Pace 6_PV | R02141-SBZ-03 | PV | I9 Exit, Leg A | Catalin S. |  | 2022-06-24 | 25 | 2022-06-25 | 25 | Done | Alexandru Comsa
32 | SAM-VED | R02141 | ER100 Chrysler MP MY21 Base Pace 6_PV | R02141-SBZ-04 | PV | I9 Entry, Leg B | Catalin S. | CW 17 | 2022-04-27 | 17 | 2022-04-28 | 17 | Done | Alexandru Comsa
33 | SAM-VED | R02141 | ER100 Chrysler MP MY21 Base Pace 6_PV | R02141-SBZ-05 | PV | RAN, Leg B | Daniel I. | CW18 | 2022-05-11 | 19 | 2022-05-18 | 20 | Done | Alexandru Comsa | Pass
34 | SAM-VED | R02141 | ER100 Chrysler MP MY21 Base Pace 6_PV | R02141-SBZ-06 | PV | Mechanical shock test, Leg B | Daniel I. | CW18 | 2022-05-18 | 20 | 2022-05-18 | 20 | Done | Alexandru Comsa | Pass
35 | SAM-VED | R02141 | ER100 Chrysler MP MY21 Base Pace 6_PV | R02141-SBZ-07 | PV | I9 Exit, Leg B | Catalin S. | CW20 | 2022-05-19 | 20 | 2022-05-19 | 20 | Done | Alexandru Comsa
36 | AM | R02019 | SVS220VW27 | R02019-SBZ-01 | PV | Parameter Test Large | Rodean C |  | 2022-03-17 | 11 | 2022-03-17 | 11 | Done | Rehberger Andreas
37 | AM | R02019 | SVS220VW27 | R02019-SBZ-02 | PV | K-01 High/low temperature storage | Rodean C |  | 2022-03-19 | 11 | 2022-03-21 | 12 | Done | Rehberger Andreas
38 | AM | R02019 | SVS220VW27 | R02019-SBZ-03 | PV | M-04 Vibration test | Ion C. | CW10 | 2022-03-23 | 12 | 2022-03-25 | 12 | Done | Rehberger Andreas
39 | AM | R02019 | SVS220VW27 | R02019-SBZ-04 | PV | Parameter test small | Rodean C | CW11 | 2022-03-10 | 10 | 2022-03-29 | 13 | Done | Rehberger Andreas
40 | AM | R02019 | SVS220VW27 | R02019-SBZ-05 | PV | M-05 Mechanical shock | Ion C. |  | 2022-04-06 | 14 | 2022-04-06 | 14 | Done | Rehberger Andreas
41 | AM | R02019 | SVS220VW27 | R02019-SBZ-06 | PV | Parameter test small | Rodean C |  | 2022-04-07 | 14 | 2022-04-07 | 14 | Done | Rehberger Andreas
42 | AM | R02019 | SVS220VW27 | R02019-SBZ-07 | PV | M-06 Mechanical shock endurance | Ion C. |  | 2022-04-09 | 14 | 2022-04-10 | 14 | Done | Rehberger Andreas
43 | AM | R02019 | SVS220VW27 | R02019-SBZ-08 | PV | Parameter Test small | Rodean C |  | 2022-04-15 | 15 | 2022-04-15 | 15 | Done | Rehberger Andreas
44 | AM | R02019 | SVS220VW27 | R02019-SBZ-09 | PV | K-01 High/low temperature storage | Rodean C |  | 2022-03-19 | 11 | 2022-03-21 | 12 | Done | Rehberger Andreas
45 | AM | R02019 | SVS220VW27 | R02019-SBZ-10 | PV | Parameter Test Large | Rodean C |  | 2022-03-23 | 12 | 2022-03-23 | 12 | Done | Rehberger Andreas
46 | AM | R02019 | SVS220VW27 | R02019-SBZ-11 | PV | K-05 Thermal shock | Rodean C |  | 2022-03-25 | 12 |  | TBD | Done | Rehberger Andreas
47 | AM | R02019 | SVS220VW27 | R02019-SBZ-12 | PV | Parameter test small | Rodean C |  | 2022-04-04 | 14 | 2022-04-04 | 14 | Done | Rehberger Andreas
48 | AM | R02019 | SVS220VW27 | R02019-SBZ-13 | PV | K-10 Water protection – IPX6K | Rodean C |  | 2022-04-13 | 15 | 2022-04-28 | 17 | Done | Rehberger Andreas
49 | AM | R02019 | SVS220VW27 | R02019-SBZ-14 | PV | Parameter test small | Rodean C |  | 2022-04-28 | 17 | 2022-04-28 | 17 | Done | Rehberger Andreas
50 | AM | R02019 | SVS220VW27 | R02019-SBZ-15 | PV | K-01 High/low temperature storage | Rodean C |  | 2022-03-19 | 11 | 2022-03-21 | 12 | Done | Rehberger Andreas
51 | AM | R02019 | SVS220VW27 | R02019-SBZ-16 | PV | Parameter Test Large | Rodean C |  | 2022-03-24 | 12 | 2022-03-24 | 12 | Done | Rehberger Andreas
52 | AM | R02019 | SVS220VW27 | R02019-SBZ-17 | PV | Parameter Test Large | Rodean C |  |  | TBD | 2022-04-19 | 16 | Done | Rehberger Andreas
53 | AM | R02019 | SVS220VW27 | R02019-SBZ-18 | PV | M-01 Shake for loose parts | Rodean C |  | 2022-04-19 | 16 | 2022-04-19 | 16 | Done | Rehberger Andreas
54 | AM | R02019 | SVS220VW27 | R02019-SBZ-19 | PV | Parameter test small | Rodean C |  |  | TBD |  | TBD | Done | Rehberger Andreas
55 | AM | R02019 | SVS220VW27 | R02019-SBZ-20 | PV | K-01 High/low temperature storage | Rodean C |  |  | TBD |  | TBD | Done | Rehberger Andreas
56 | AM | R02019 | SVS220VW27 | R02019-SBZ-21 | PV | Parameter Test Large | Rodean C |  |  | TBD |  | TBD | Done | Rehberger Andreas
57 | AM | R02019 | SVS220VW27 | R02019-SBZ-22 | PV | K-02 Incremental temperature test | Rodean C |  | 2022-03-19 | 11 | 2022-03-21 | 12 | Done | Rehberger Andreas
58 | AM | R02019 | SVS220VW27 | R02019-SBZ-23 | PV | Parameter Test Large | Rodean C |  | 2022-03-21 | 12 | 2022-03-21 | 12 | Done | Rehberger Andreas
59 | AM | R02019 | SVS220VW27 | R02019-SBZ-24 | PV | K-05 Thermal shock | Rodean C |  | 2022-03-21 | 12 | 2022-03-29 | 13 | Done | Rehberger Andreas
60 | AM | R02019 | SVS220VW27 | R02019-SBZ-25 | PV | Parameter test small | Rodean C |  | 2022-03-29 | 13 | 2022-03-29 | 13 | Done | Rehberger Andreas
61 | AM | R02019 | SVS220VW27 | R02019-SBZ-26 | PV | K-09 Damp heat, cyclic | Rodean C |  | 2022-04-07 | 14 | 2022-04-18 | 16 | Done | Rehberger Andreas
62 | AM | R02019 | SVS220VW27 | R02019-SBZ-27 | PV | Parameter test small | Rodean C |  | 2022-04-27 | 17 | 2022-04-27 | 17 | Done | Rehberger Andreas
63 | AM | R02019 | SVS220VW27 | R02019-SBZ-28 | PV | M-04 Vibration test | Daniel I. |  | 2022-05-06 | 18 | 2022-05-12 | 19 | Done | Rehberger Andreas
64 | AM | R02019 | SVS220VW27 | R02019-SBZ-29 | PV | Parameter test small | Rodean C |  | 2022-03-22 | 12 |  | TBD | Next | Rehberger Andreas
65 | AM | R02019 | SVS220VW27 | R02019-SBZ-30 | PV | K-12 Thermal shock with splash water | Rodean C |  |  | TBD |  | TBD | Next | Rehberger Andreas
66 | AM | R02019 | SVS220VW27 | R02019-SBZ-31 | PV | Parameter Test Large | Rodean C |  |  | TBD |  | TBD | Done | Rehberger Andreas
67 | AM | R02019 | SVS220VW27 | R02019-SBZ-32 | PV | K-01 High/low temperature storage | Rodean C |  |  | TBD |  | TBD | Done | Rehberger Andreas
68 | AM | R02019 | SVS220VW27 | R02019-SBZ-33 | PV | Parameter Test Large | Rodean C |  |  | TBD |  | TBD | Done | Rehberger Andreas
69 | AM | R02019 | SVS220VW27 | R02019-SBZ-34 | PV | L-03 temperature cycle endurance test | Rodean C |  | 2022-03-28 | 13 |  | TBD | Ongoing | Rehberger Andreas
70 | AM | R02019 | SVS220VW27 | R02019-SBZ-35 | PV | Parameter Test Large | Rodean C |  |  | TBD |  | TBD | Ongoing | Rehberger Andreas
71 | Heat CE | R02126 | MAGNA CTS SRM | R02126-SBZ–01 | PV | Test Na: Rapid change of temperature with prescribed time of transfer - Thermal shock test | Nick S. | CW17 | 2022-04-29 | 17 | 2022-05-16 | 20 | Done | Davidescu Madalina
72 | Heat CE | R02126 | MAGNA CTS SRM | R02126-SBZ–02 | PV | VIBRATION TEST | Ion C. | CW 20 | 2022-04-28 | 20 |  | TBD | Ongoing | Davidescu Madalina
73 | Heat CE | R02126 | MAGNA CTS SRM | R02126-SBZ–03 | PV |  | Ion C. |  |  | TBD |  | TBD | Next | Davidescu Madalina
74 | Heat CE | R02126 | MAGNA CTS SRM | R02126-SBZ–04 | PV | Test A: Cold – Low temperature storage test | Nick S. |  |  | TBD |  | TBD | Done | Davidescu Madalina
75 | Heat CE | R02126 | MAGNA CTS SRM | R02126-SBZ–05 | PV | Test B: Dry heat - High temperature storage test | Nick S. |  |  | TBD |  | TBD | Done | Davidescu Madalina
76 | Heat CE | R02126 | MAGNA CTS SRM | R02126-SBZ–06 | PV | Dew Condensation | Nick S. |  | 2022-05-18 | 20 | 2022-05-20 | 20 | Done | Davidescu Madalina
77 | Heat CE | R02126 | MAGNA CTS SRM | R02126-SBZ–07 | PV | Test Z/AD: Composite temperature and humidity test | Nick S. |  |  | TBD | 2022-06-20 | 25 | Done | Davidescu Madalina
78 | Heat CE | R02126 | MAGNA CTS SRM | R02126-SBZ–08 | PV | Solder evaluation |  |  |  | TBD |  | TBD | Next | Davidescu Madalina
79 | VNI-CCN | R02135 | VOL-F-LCU_-D-HCM1-RE-DESIGN |  |  | 4.3 MECHANICAL SHOCK | Ion C. |  |  | TBD |  | TBD
80 | VNI-CCN | R02135 | VOL-F-LCU_-D-HCM1-RE-DESIGN |  |  | 3.7 TEMPERATURE STEP TEST | Radu I. |  |  | TBD |  | TBD
81 | AN | R02259 | DQ200 TCU | R02259-SBZ-01 | Pre-compliance | Test Fc:Sinusoidal | Ion C. | CW17 | 2022-04-28 | 17 | 2022-04-29 | 17 | Done | Ovidiu Capatana
82 | AN | R02144 | MQB 21 DCU DV | R02144-SBZ–03 | DV | Test Fh: Random | Ion C. | CW14 | 2022-04-04 | 14 | 2022-04-07 | 14 | Done | Marius Carp | Pass
83 | AN | R02144 | MQB 21 DCU DV | R02144-SBZ–04 | DV | Test Ea: Shock | Ion C. | CW13 | 2022-04-01 | 13 | 2022-04-01 | 13 | Done | Marius Carp | Pass
84 | AN | R02144 | MQB 21 DCU DV | R02144-SBZ–05 | DV | Test Ea: Shock | Ion C. | CW10 | 2022-03-08 | 10 | 2022-03-09 | 10 | Done | Marius Carp | Pass
85 | AN | R02192 | MQB 21 DCU dPV | R02192-SBZ–03 | dPV | Test Fh: Random | Ion C. | CW16 | 2022-04-19 | 16 | 2022-04-21 | 16 | Done | Marius Carp | Pass
86 | AN | R02193 | MQB 21 DCU dPV | R02192-SBZ–04 | dPV | Test Ea: Shock | Ion C. | CW16 | 2022-04-19 | 16 | 2022-04-19 | 16 | Done | Marius Carp | Pass
87 | AN | R02194 | MQB 21 DCU dPV | R02192-SBZ–05 | dPV | Test Ea: Shock | Ion C. | CW17 | 2022-04-26 | 17 | 2022-04-27 | 17 | Done | Marius Carp | Pass
88 | SAM-PSS | R02045 | SPC+ | R02045-SBZ–02 | PV | Test Fh: Random | Ion C. | CW17 | 2022-04-28 | 17 | 2022-04-30 | 17 | Done | Mihai Bardasu
89 | SAM-VED | R02271 | Hyundai B-MPV | R02271-SBZ-01 | Pre-compliance | Test Fh: Random | Ion C. | CW18 | 2022-05-06 | 18 | 2022-05-20 | 20 | Done | Acatrinei Alina
90 | SAM-PSS | R03476 | AK1 gSat | R03476-SBZ–01 | PV | Test Fh: Random | Ion C. | CW15 | 2022-04-11 | 15 | 2022-04-18 | 16 | Done | Varna Bogdan | Pass
91 | AM | R02153 | RVS22xGM12 2.1MP | R02153-SBZ–12 | PV | Test Fh: Random | Ion C. | CW17 | 2022-04-28 | 17 | 2022-05-05 | 18 | Done | Santiago Miguel
92 | he[a]t-CE | R02036 | MQB 23 BSL | R0 2036-SBZ–06 | DV | Test Ea: Shock | Daniel I. | CW 16 | 2022-04-28 | 17 | 2022-04-29 | 17 | Done | Sebi Basil
93 | he[a]t-CE | R02036 | MQB 23 BSL | R0 2036-SBZ–07 | DV | Test Fh: Random | Daniel I. | CW16 | 2022-04-29 | 17 | 2022-05-18 | 20 | Done | Sebi Basil
94 | UX | R03871 | PSA eHUD | R03781 -TSR–02 | PV | CL07a | Radu I. |  | 2022-05-13 | 19 | 2022-06-03 | 22 | Done | Petru Suveti
95 | SAM-PSS | R02046 | SCCU VDP BMW 35up LOW | R02046-SBZ-01 | dPV | K-05: Temperature shock test | Radu G. | CW19 | 2022-05-13 | 19 | 2022-05-19 | 20 | Done | Bardasu Mihail
95 | SAM-PSS | R02046 | SCCU VDP BMW 35up LOW | R02046-SBZ-02 | dPV | K-08: Humid heat, cyclic test | Radu G. | CW20 | 2022-05-20 | 20 | 2022-05-30 | 22 | Done | Bardasu Mihail
95 | SAM-PSS | R02046 | SCCU VDP BMW 35up LOW | R02046-SBZ-04 | dPV | K-02: Temperature Step test | Radu G. | CW22 | 2022-06-08 | 23 | 2022-06-10 | 23 | Done | Bardasu Mihail
96 | SAM-PSS | R02043 | Volvo_CCU37 | R02043-SBZ-01 | dPV | High Temperature Storage | Radu G. | CW12 | 2022-03-25 | 12 | 2022-04-16 | 15 | Done | Hategan Ion
97 | SAM-PSS | R02043 | Volvo_CCU37 | R02043-SBZ-02 | dPV | Low Temperature Storage | Radu G. | CW15 | 2022-04-19 | 16 | 2022-04-20 | 16 | Done | Hategan Ion
98 | SAM-PSS | R02043 | Volvo_CCU37 | R02043-SBZ-03 | dPV | Temperature Cycling | Radu G. | CW 16 | 2022-04-21 | 16 | 2022-05-02 | 18 | Done | Hategan Ion
99 | SAM-PSS | R02043 | Volvo_CCU37 | R02043-SBZ-04 | dPV | Rapid change of temperature | Radu G. | CW18 | 2022-05-05 | 18 | TBD | TBD | Done | Hategan Ion
100 | SAM-PSS | R02043 | Volvo_CCU37 | R02043-SBZ-05 | dPV | Temperature Step Test | Radu G. | CW21 | 2022-05-27 | 21 | 2022-05-30 | 22 | Done | Hategan Ion
101 | SAM-PSS | R02043 | Volvo_CCU37 | R02043-SBZ-06 | dPV | Composite Temperature/Humidity Cyclic Test | Radu G. | CW22 | 2022-06-02 | 22 | 2022-06-10 | 23 | Done | Hategan Ion
102 | SAM-PSS | R02043 | Volvo_CCU37 | R02043-SBZ-07 | dPV | Damp Heat Steady State | Radu G. | CW24 | 2022-06-15 | 24 | 2022-07-06 | 27 | Ongoing | Hategan Ion
103 | PSS-ECC | R02190 | VW DCC4 MQB37AW_2023_DACC | R02190-SBZ–07 | DV | M-05 Mechanical Shock | Daniel I. | CW20 | 2022-05-11 | 19 | 2022-05-13 | 19 | Done | Sorin Ghise
104 | PSS-ECC | R02190 | VW DCC4 MQB37AW_2023_DACC | R02190-SBZ–07 | DV | Test Fh: Random | Daniel I. | CW20 | 2022-05-16 | 20 | 2022-05-18 | 20 | Done | Sorin Ghise
105 | VED | R02291 | Hyundai_B-MPV_MK 100_ESC_MY22.00_Base_KS | R02291-SBZ–01 | Pre-compliance | Test Fh: Random | Daniel I. | 21 | 2022-05-22 | 20 | 2022-05-31 | 22 | Done | Alina Acatrinei
106 | VED | R02248 | Sum of motor forces at interface |  | Pre-compliance | Push Pull | Daniel I. | CW15 | 2022-04-18 | 16 | 2022-04-19 | 16 | Done | Balc Daniel
107 | VED | R02249 | MK100_Broken knob at customer |  | Pre-compliance | Push Pull | Daniel I. | CW15 | 2022-04-27 | 17 | 2022-04-27 | 17 | Done | Sergiu Lazăr
108 | AN | R02282 | DQ200TCU | R02282-SBZ–01 | Pre-compliance | Thermal shock | Radu I. | CW21 | 2022-05-25 | 21 | 2022-06-15 | 24 | Done | Capatina Ovidiu
109 | SAM-PSS | R02047 | EFP 2.0 | R02047-SBZ–01 | dPV | K-01 High/Low Temperature Storage | Radu G. | CW21 | 2022-05-26 | 21 | 2022-05-29 | 21 | Done | Hategan Ion
110 | SAM-PSS | R02047 | EFP 2.0 | R02047-SBZ–02 | dPV | K-02 Incremental Temperature Test | Radu G. | CW22 | 2022-06-06 | 23 | 2022-06-10 | 23 | Done | Hategan Ion
111 | SAM-PSS | R02047 | EFP 2.0 | R02047-SBZ–05 | dPV | K-09 Moist heat (Damp heat), cyclic (with frost) | Radu G. | CW25 | 2022-06-21 | 25 | 2022-07-04 | 27 | Done | Hategan Ion
112 | SAM-PSS | R02047 | EFP 2.0 | R02047-SBZ–06 | dPV | K-16 Thermal shock (without housing) | Radu G. | CW21 | 31.05.2022 | 22 | 2022-06-10 | 23 | Done | Hategan Ion
113 | Heat CE | R02095 | MakeValves | R02095–SBZ–01 | dPV | K-01 High/Low Temperature Storage | Iulia T. |  | 2022-06-06 | 23 | 2022-06-09 | 23 | Done | Ciobanu Aurelian
114 | Heat CE | R02095 | MakeValves | R02095–SBZ–02 | dPV | Stand alone parameter test | Iulia T. |  | 2022-06-15 | 24 |  | TBD | Ongoing | Ciobanu Aurelian
115 | Heat CE | R02095 | MakeValves | R02095–SBZ–03 | dPV | Service life low temp | Iulia T. |  |  | TBD |  | TBD | Next | Ciobanu Aurelian
116 | Heat CE | R02095 | MakeValves | R02095–SBZ–04 | dPV | Temperature shock | Iulia T. |  |  | TBD |  | TBD | Next | Ciobanu Aurelian
117 | Heat CE | R02272 | BMW_35UP_SCU_MYC | R02272-SBZ–01 | dPV | K-01 High/Low Temperature Storage | Iulia T. | CW20 | 2022-05-16 | 20 | 2022-05-19 | 20 | Done | Vasile Maria Adina
118 | Heat CE | R02272 | BMW_35UP_SCU_MYC | R02272-SBZ–02 | dPV | Temperature shock without housing | Iulia T. | CW22 | 2022-05-20 | 20 | 2022-06-13 | 24 | Done | Vasile Maria Adina
119 | Heat CE | R02168 | AUD_XXXX_16_PNEU_BK | R02168-SBZ–01 | PV | K-01 High/Low Temperature Storage | Iulia T. | CW21 | 2022-05-20 | 20 | 2022-05-23 | 21 | Done | David Cristina
120 | Heat CE | R02168 | AUD_XXXX_16_PNEU_BK | R02168-SBZ–02 | PV | K-02 Incremental Temperature Test | Iulia T. | CW21 | 2022-05-25 | 21 | 2022-06-03 | 22 | Done | David Cristina
121 | Heat CE | R02189 | MB_213_D5_PSCM_MJ | R02189-SBZ–01 | dPV | K-01 High/Low Temperature Storage | Iulia T. | CW21 | 2022-05-23 | 21 | 2022-05-26 | 21 | Done | Vestemean Marius
122 | Heat CE | R02189 | MB_213_D5_PSCM_MJ | R02189-SBZ–02 | dPV | K-02 Incremental Temperature Test | Iulia T. | CW22 | 2022-06-08 | 23 | 2022-06-20 | 25 | Done | Vestemean Marius
123 | Heat CE | R02189 | MB_213_D5_PSCM_MJ | R02189-SBZ–03 | dPV | M01- Free Fall | Iulia T. | CW25 | 2022-06-22 | 25 | 2022-06-22 | 25 | Done | Vestemean Marius
124 | Heat CE | R02189 | MB_213_D5_PSCM_MJ | R02189-SBZ–04 | dPV | M-05 - Mechanical Shock Test | Ion C. | CW26 | 2022-06-29 | 26 |  | TBD | Ongoing | Vestemean Marius
125 | Heat CE | R02189 | MB_213_D5_PSCM_MJ | R02189-SBZ–05 | dPV | M-04 - Vibration Test | Ion C. | CW26 | 2022-06-30 | 26 |  | TBD | Ongoing | Vestemean Marius
126 | Heat CE | R02189 | MB_213_D5_PSCM_MJ | R02189-SBZ–06 | dPV | K-02 - Temperature Step Test | Iulia T. |  |  | TBD |  | TBD | Next | Vestemean Marius
127 | Heat CE | R02189 | MB_213_D5_PSCM_MJ | R02189-SBZ–07 | dPV | K-09 - Humidity Heat, Cyclic (with Frost) | Iulia T. |  | 2022-06-28 | 26 |  | TBD | Ongoing | Vestemean Marius
128 | Heat CE | R02189 | MB_213_D5_PSCM_MJ | R02189-SBZ–08 | dPV | K-14 - Humidity Heat, const/ | Iulia T. | CW25 | 2022-06-16 | 24 |  | TBD | Ongoing | Vestemean Marius
129 | Heat CE | R02189 | MB_213_D5_PSCM_MJ | R02189-SBZ–09 | dPV | K-02 - Temperature Step Test | Iulia T. | CW22 | 2022-06-08 | 23 | 2022-06-13 | 24 | Done | Vestemean Marius
130 | Heat CE | R02189 | MB_213_D5_PSCM_MJ | R02189-SBZ–10 | dPV | L-03 - Life Test: Temperature Cycle Endurance Test for Components with reduced performance at low and high temperatures | Iulia T. | CW25 | 2022-06-16 | 24 |  | TBD | Ongoing | Vestemean Marius
131 | Heat CE | R02189 | MB_213_D5_PSCM_MJ | R02189-SBZ–11 | dPV | K-02 - Temperature Step Test | Iulia T. |  |  | TBD |  | TBD | Next | Vestemean Marius
132 | Heat CE | R02189 | MB_213_D5_PSCM_MJ | R02189-SBZ–12 | dPV | K-02 - Temperature Step Test | Iulia T. |  |  | TBD |  | TBD | Next | Vestemean Marius
133 | Heat CE | R02203 | MB_213_D5_PSCM_MJ | R02203-SBZ-01 | dPV | K-01 High/Low Temperature Storage | Iulia T. | CW21 | 2022-05-26 | 21 | 2022-05-28 | 21 | Done | Vestemean Marius
134 | Heat CE | R02203 | MB_213_D5_PSCM_MJ | R02203-SBZ-02 | dPV | K-02 Incremental Temperature Test | Iulia T. | CW21 | 2022-06-14 | 24 |  | TBD | Ongoing | Vestemean Marius
135 | AM | R02210 | SVC22XDP | R02210-SBZ–01 | dPV | K-01 High/Low Temperature Storage | Iulia T. |  |  | TBD |  | TBD | Next | Zeljko Majstoro
136 | AM | R02210 | SVC22XDP | R02210-SBZ–02 | dPV | K-09 Damp heat cyclic (with frost) | Iulia T. |  |  | TBD |  | TBD | Next | Zeljko Majstoro
137 | AM | R02210 | SVC22XDP | R02210-SBZ–03 | dPV | M-04 Vibration test | Ion C. |  |  | TBD |  | TBD | Next | Zeljko Majstoro
138 | AM | R02210 | SVC22XDP | R02210-SBZ–04 | dPV | K-10 Water protection | Iulia T. |  |  | TBD |  | TBD | Next | Zeljko Majstoro
139 | AM | R02210 | SVC22XDP | R02210-SBZ–05 | dPV | K-02 Incremental Temperature Test | Iulia T. |  |  | TBD |  | TBD | Next | Zeljko Majstoro
140 | AM | R02210 | SVC22XDP | R02210-SBZ–06 | dPV | L-03 Temp. cyclic endurance test | Iulia T. |  |  | TBD |  | TBD | Next | Zeljko Majstoro
141 | AM | R02210 | SVC22XDP | R02210-SBZ–07 | dPV | L-02 High temp. endurance test | Iulia T. |  |  | TBD |  | TBD | Next | Zeljko Majstoro
142 | Heat CE | R02186 | MakeValves | R02186–SBZ–01 | dPV | K-01 High/Low Temperature Storage | Iulia T. |  | 2022-06-21 | 25 |  | TBD | Ongoing | Ciobanu Aurelian
143 | Heat CE | R02186 | MakeValves | R02186–SBZ–02 | dPV | Stand alone parameter test | Iulia T. |  |  | TBD |  | TBD | Next | Ciobanu Aurelian
144 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–01 | DV | CL/13 Check of Saturation Temperature | Nick S. | CW22 | 2022-05-31 | 22 | 2022-06-03 | 22 | Done | Madalina Davidescu
145 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–02 | DV | LT/00 Self heating temperature measurement | Nick S. | CW22 | 2022-06-03 | 22 | 2022-06-06 | 23 | Done | Madalina Davidescu
146 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–03 | DV | CL/00 Thermal inertia characterization test | Nick S. | CW22 | 2022-05-31 | 22 | 2022-06-01 | 22 | Done | Madalina Davidescu
147 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–04 | DV | CH/01 Solid tightness | Nick S. | CW22 | 2022-06-02 | 22 | 2022-06-02 | 22 | Done | Madalina Davidescu
148 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–05 | DV | CL/02 Thermal shock pre-ageing test (50 cycles) | Nick S. | CW22 | 2022-05-31 | 22 | 2022-06-06 | 23 | Done | Madalina Davidescu
149 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–06 | DV | CH/08 Fluid corrosion | Nick S. | CW23 | 2022-06-16 | 24 | 2022-06-21 | 25 | Done | Madalina Davidescu
150 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–07 | DV | CH/12 Corrosive atmosphere | Nick S. |  |  | TBD |  | TBD | Next | Madalina Davidescu
151 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–08 | DV | VI/01 Resonance investigation-resonance point detecting test | Ion C. | CW22 | 2022-06-02 | 22 | 2022-06-07 | 23 | Done | Madalina Davidescu
152 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–09 | DV | VI/05 Resonance point 1h oscillation test | Ion C. | CW24 | 2022-06-16 | 24 | 2022-06-17 | 24 | Done | Madalina Davidescu
153 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–10 | DV | CL/08 Warm operation test | Nick S. | CW23 | 2022-06-03 | 22 | 2022-06-05 | 22 | Done | Madalina Davidescu
154 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–11 | DV | CL/09 Cold operation test | Nick S. | CW23 | 2022-06-07 | 23 | 2022-06-08 | 23 | Done | Madalina Davidescu
155 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–12 | DV | CL/07 a Temperature Range (steps)test | Nick S. | CW23 | 2022-06-09 | 23 | 2022-06-10 | 23 | Done | Madalina Davidescu
156 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–13 | DV | CL/07 b Temperature Range (steps)test | Nick S. | CW25 | 2022-06-15 | 24 | 2022-06-15 | 24 | Done | Madalina Davidescu
157 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–14 | DV | CL/15 Continuous humidity test | Nick S. | CW23 | 2022-06-07 | 23 |  | TBD | Ongoing | Madalina Davidescu
158 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–15 | DV | CL/03 Warm storage test | Nick S. | CW23 | 2022-06-03 | 22 | 2022-06-05 | 22 | Done | Madalina Davidescu
159 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–16 | DV | CL/04 cold storage test | Nick S. | CW23 | 2022-06-09 | 23 | 2022-06-10 | 23 | Done | Madalina Davidescu
160 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–17 | DV | MS/01 Free fall test | Nick S. | CW24 | 2022-06-16 | 24 | 2022-06-16 | 24 | Done | Madalina Davidescu
161 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–18 | DV | MS/10 Brackets and fasteners strength test | Daniel I. | CW24 | 2022-06-20 | 25 | 2022-06-21 | 25 | Done | Madalina Davidescu
162 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–19 | DV | MS/11 Terminal strength test | Nick S. |  |  | TBD |  | TBD | Next | Madalina Davidescu
163 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–20 | DV | CL/01 Thermal shock endurance test | Nick S. | CW22 | 2022-06-02 | 22 | 2022-06-15 | 24 | Done | Madalina Davidescu
164 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–21 | DV | CH/02 Liquid tightness (Water test) | Nick S. |  |  | TBD |  | TBD | Next | Madalina Davidescu
165 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–22 | DV | LT/01 Thermal cycling life test | Nick S. |  |  | TBD |  | TBD | Next | Madalina Davidescu
166 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–23 | DV | VI/07 Random vibration endurance test -Real vibration | Ion C. |  |  | TBD |  | TBD | Next | Madalina Davidescu
167 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–24 | DV | CH/02 Liquid tightness (Water test) | Nick S. |  |  | TBD |  | TBD | Next | Madalina Davidescu
168 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–25 | DV | LT/02 Constant humid heat life test | Nick S. |  |  | TBD |  | TBD | Next | Madalina Davidescu
169 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–26 | DV | LT/03 Thermal life test | Nick S. |  |  | TBD |  | TBD | Next | Madalina Davidescu
170 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–27 | DV | CL/03 Warm storage test | Nick S. | CW22 | 2022-06-02 | 22 | 2022-06-04 | 22 | Done | Madalina Davidescu
171 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–28 | DV | CL/04 Cold storage test | Nick S. | CW22 | 2022-06-07 | 23 | 2022-06-08 | 23 | Done | Madalina Davidescu
172 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–29 | DV | CL/02 Thermal shock pre-ageing test | Nick S. | CW23 | 2022-06-09 | 23 | 2022-06-13 | 24 | Done | Madalina Davidescu
173 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–30 | DV | CL/10 Cold and low-pressure storage test | Nick S. |  |  | TBD |  | TBD | Next | Madalina Davidescu
174 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–31 | DV | MS/02 Mechanical shocks-resistance to impact during assembly | Daniel I. | CW26 | 2022-06-30 | 26 |  | TBD | Ongoing | Madalina Davidescu
175 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–32 | DV | MS/03 Mechanical shocks- resistance to collision impact | Ion C. |  |  | TBD |  | TBD | Next | Madalina Davidescu
176 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–33 | DV | MS/07 Mechanical shocks- shocks from the road | Ion C. |  |  | TBD |  | TBD | Next | Madalina Davidescu
177 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–34 | DV | VI/07 Random vibration endurance test (CP1 phase) | Ion C. |  |  | TBD |  | TBD | Next | Madalina Davidescu
178 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–35 | DV | VI/07 Random vibration endurance test (CP2 phase) | Ion C. |  |  | TBD |  | TBD | Next | Madalina Davidescu
179 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–36 | DV | CL/06 Climatic sequence test | Nick S. |  |  | TBD |  | TBD | Next | Madalina Davidescu
180 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–37 | DV | CH/09 Salt spray with humidity functional endurance test | Nick S. |  |  | TBD |  | TBD | Next | Madalina Davidescu
181 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–38 | DV | CH/02 Liquid tightness test | Nick S. |  |  | TBD |  | TBD | Next | Madalina Davidescu
182 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–39 | DV | Cross section test | Nick S. |  |  | TBD |  | TBD | Next | Madalina Davidescu
183 | AN | R02165 | REN_EZ1_23_IVS_PCU | R02165–SBZ–40 | DV | (Internal inspection) Disassembly examinations | Nick S. |  |  | TBD |  | TBD | Next | Madalina Davidescu
184 | External | R02187 | BMW_PCU48_DCDC | R02187-SBZ–12 | Pre-compliance | M-05 Mechanical | Daniel I. | CW21 | 2022-06-02 | 22 | 2022-06-16 | 24 | Done | Ganea Ovidiu
185 | External | R02187 | BMW_PCU48_DCDC | R02187-SBZ–13 | Pre-compliance | M-04 Vibration Test – Profile D | Daniel I. | CW21 | 2022-06-02 | 22 | 2022-06-16 | 24 | Done | Ganea Ovidiu
186 | VED | R02061 | BMW_G2x_MY19MK100HP-High Plus ESC | RID943-SBZ-24 | PV | Vibration test | Daniel I. | CW22 | 05/30.2022 | TBD | 2022-06-05 | 22 | Done | Alexandru Spatar
187 | VED | R02061 | BMW_G2x_MY19MK100HP-High Plus ESC | RID943SBZ-25 | PV | Mechanical Shock | Daniel I. | CW22 | 2022-05-30 | 22 | 2022-06-07 | 23 | Done | Alexandru Spatar
188 | AM | R02153 | RVS22xGM12 2.1MP | R02153-SBZ-01 | PV | 5-Point Functional/Parametric Check | Rodean C | CW15 | 2022-04-15 | 15 | 2022-04-19 | 16 | Done | Santiago Miguel
189 | AM | R02153 | RVS22xGM12 2.1MP | R02153-SBZ-02 | PV | Thermal Shock Air-To-Air (TS) | Rodean C | CW16 | 2022-04-19 | 16 |  | TBD | Done | Santiago Miguel
190 | AM | R02153 | RVS22xGM12 2.1MP | R02153-SBZ-03 | PV | Power Temperature Cycle (PTC) | Rodean C | CW16 | 2022-04-19 | 16 |  | TBD | Done | Santiago Miguel
191 | AM | R02153 | RVS22xGM12 2.1MP | R02153-SBZ-04 | PV | Seal | Rodean C | CW18 | 2022-05-05 | 18 | 2022-05-20 | 20 | Done | Santiago Miguel
192 | AM | R02153 | RVS22xGM12 2.1MP | R02153-SBZ-05 | PV | Humid Heat Cyclic (HHC) | Rodean C | CW16 | 2022-04-20 | 16 | 2022-05-01 | 17 | Done | Santiago Miguel
193 | AM | R02153 | RVS22xGM12 2.1MP | R02153-SBZ-06 | PV | Humid Heat Constant (HHCO) | Rodean C | CW16 | 2022-04-20 | 16 | 2022-04-30 | 17 | Done | Santiago Miguel
194 | AM | R02153 | RVS22xGM12 2.1MP | R02153-SBZ-07 | PV | Low Temperature Wakeup | Rodean C | CW16 | 2022-04-20 | 16 | 2022-04-22 | 16 | Done | Santiago Miguel
195 | AM | R02153 | RVS22xGM12 2.1MP | R02153-SBZ-08 | PV | Minimum Non-Operating Temperature | Rodean C | CW16 | 2022-04-22 | 16 |  | TBD | Done | Santiago Miguel
196 | AM | R02153 | RVS22xGM12 2.1MP | R02153-SBZ-09 | PV | Dust | Rodean C | CW18 | 2022-05-04 | 18 | 2022-05-05 | 18 | Done | Santiago Miguel
197 | AM | R02153 | RVS22xGM12 2.1MP | R02153-SBZ-10 | PV | Water | Rodean C | CW19 | 2022-05-11 | 19 | 2022-05-12 | 19 | Done | Santiago Miguel
198 | AM | R02153 | RVS22xGM12 2.1MP | R02153-SBZ-11 | PV | High Temperature Degradation | Rodean C | CW16 | 2022-04-22 | 16 | 2022-05-17 | 20 | Done | Santiago Miguel
199 | AM | R02153 | RVS22xGM12 2.1MP | R02153-SBZ-12 | PV | Shipping Vibration | Ion C. |  |  | TBD |  | TBD | Done | Santiago Miguel
200 | SAM-PSS | R02046 | SCCU VDP BMW 35up LOW | R02046-SBZ-03 | PV | M-04 Vibration Test – Profile D | Daniel I. | CW22 | 2022-06-03 | 22 | 2022-06-05 | 22 | Done
201 | AN | R02317 | BMW GBE | R02317-SBZ-01 | Pre-compliance | K15a: Dewing Test | Radu I. |  | 2022-05-31 | 22 | 2022-06-02 | 22 | Done
203 | AM | R02201 | MFL420, CP03 TA | R02201-SBZ-01 | PV | Temperature/Voltage Composite Characteristics | Rodean C | CW20 | 2022-05-20 | 20 | 2022-05-21 | 20 | Done
204 | AM | R02201 | MFL420, CP03 TA | R02201-SBZ-02 | PV | Operation Durability of Temperature cycle | Rodean C | CW20 | 2022-05-20 | 20 |  | TBD | Ongoing
205 | AM | R02201 | MFL420, CP03 TA | R02201-SBZ-03 | PV | Operation Durability at High Temperature High Humidity | Rodean C | CW20 | 2022-05-21 | 20 |  | TBD | Ongoing
206 | AM | R02201 | MFL420, CP03 TA | R02201-SBZ-04 | PV | Temperature/Humidity cycle test | Rodean C | CW30 |  |  |  |  | Next
207 | SAM-PSS | R02137 | JTEKT | R02137-SBZ-01 | DV | Step temperature test (Group 1A) | Radu G. | CW23 | 2022-06-08 | 23 |  | TBD | Ongoing
208 | SAM-PSS | R02137 | JTEKT | R02137-SBZ-02 | DV | Step temperature beyond the limits (Group 1B) | Radu G. |  |  | TBD |  | TBD | Next
209 | SAM-PSS | R02137 | JTEKT | R02137-SBZ-03 | DV | Climatic sequence test (Group 1A) | Radu G. |  |  | TBD |  | TBD | Next
210 | SAM-PSS | R02137 | JTEKT | R02137-SBZ-04 | DV | High temperature operational life test (Group 2) | Radu G. | CW24 | 2022-07-01 | 26 |  | TBD | Ongoing
211 | SAM-VED | R02066 | BMW_CAirS_CB1_MY18 - pulse cube | R02066-SBZ-01 | PV | I9 Entry - B | Dan V. |  | 2022-03-07 | 10 | 2022-03-08 | 10 | Done | Bucse Bogdan
212 | SAM-VED | R02066 | BMW_CAirS_CB1_MY18 - pulse cube | R02066-SBZ-02 | PV | PTC - B | Dan V. |  | 2022-03-10 | 10 |  | TBD | Ongoing | Bucse Bogdan
213 | SAM-VED | R02066 | BMW_CAirS_CB1_MY18 - pulse cube | R02066-SBZ-03 | PV | I9 Exit - B | Dan V. |  |  | TBD |  | TBD | Next | Bucse Bogdan
214 | SAM-VED | R02066 | BMW_CAirS_CB1_MY18 - pulse cube | R02066-SBZ-04 | PV | I9 Entry - D | Dan V. |  | 2022-03-10 | 10 | 2022-03-11 | 10 | Done | Bucse Bogdan
215 | SAM-VED | R02066 | BMW_CAirS_CB1_MY18 - pulse cube | R02066-SBZ-05 | PV | LTS- D | Dan V. |  | 2022-03-11 | 10 | 2022-03-12 | 10 | Done | Bucse Bogdan
216 | SAM-VED | R02066 | BMW_CAirS_CB1_MY18 - pulse cube | R02066-SBZ-06 | PV | HTS - D | Dan V. |  | 2022-03-14 | 11 | 2022-03-15 | 11 | Done | Bucse Bogdan
217 | SAM-VED | R02066 | BMW_CAirS_CB1_MY18 - pulse cube | R02066-SBZ-07 | PV | TSE - D | Dan V. |  | 2022-03-15 | 11 | 2022-03-26 | 12 | Done | Bucse Bogdan
218 | SAM-VED | R02066 | BMW_CAirS_CB1_MY18 - pulse cube | R02066-SBZ-08 | PV | I9 Exit - D | Dan V. |  | 2022-03-29 | 13 | 2022-03-30 | 13 | Done | Bucse Bogdan
219 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-01 | dPV | A - I9 Entry | Dan V. |  | 2022-04-26 | 17 | 2022-04-28 | 17 | Done | Andrei Cimpean
220 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-02 | dPV | A - Thermal cycling life test/PTC | Dan V. |  | 2022-05-06 | 18 |  | TBD | Ongoing | Andrei Cimpean
221 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-03 | dPV | A - Immersion | Dan V. |  |  | TBD |  | TBD | Next | Andrei Cimpean
222 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-04 | dPV | A - Splash water | Dan V. |  |  | TBD |  | TBD | Next | Andrei Cimpean
223 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-05 | dPV | A - Ice water | Dan V. |  |  | TBD |  | TBD | Next | Andrei Cimpean
224 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-06 | dPV | A - bubble test | Dan V. |  |  | TBD |  | TBD | Next | Andrei Cimpean
225 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-07 | dPV | A - High pressure test | Dan V. |  |  | TBD |  | TBD | Next | Andrei Cimpean
226 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-08 | dPV | A - I9 Exit | Dan V. |  |  | TBD |  | TBD | Next | Andrei Cimpean
227 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-09 | dPV | B - I9 Entry | Dan V. |  | 2022-04-21 | 16 | 2022-04-22 | 16 | Done | Andrei Cimpean
228 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-10 | dPV | B - Withstand voltage | Dan V. |  | 2022-05-10 | 19 | 2022-05-10 | 19 | Done | Andrei Cimpean
229 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-11 | dPV | B - Insulation resistance | Dan V. |  | 2022-05-11 | 19 | 2022-05-11 | 19 | Done | Andrei Cimpean
230 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-12 | dPV | B - Constant Humid Heat | Dan V. |  | 2022-05-11 | 19 | 2022-06-24 | 25 | Done | Andrei Cimpean
231 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-13 | dPV | B - Withstand voltage | Dan V. |  | 2022-06-24 | 25 | 2022-06-24 | 25 | Done | Andrei Cimpean
232 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-14 | dPV | B - Insulation resistance | Dan V. |  | 2022-06-24 | 25 | 2022-06-24 | 25 | Done | Andrei Cimpean
233 | SAM-VED | R02150 | ER100 Nissan L21B High Plus | R02150-SBZ-15 | dPV | B - I9 Exit | Dan V. |  | 2022-06-24 | 25 | 2022-06-25 | 25 | Done | Andrei Cimpean
234 | SAM-VED | R02070 | ER100 PSA CMP ECO MY23.50_IPB High | R02070-SBZ-01 | dPV | A - I9 Entry | Dan V. |  | 2022-05-13 | 19 | 2022-05-14 | 19 | Done | Andrei Cimpean
235 | SAM-VED | R02070 | ER100 PSA CMP ECO MY23.50_IPB High | R02070-SBZ-02 | dPV | A - PTC | Dan V. |  | 2022-05-14 | 19 |  | TBD | Ongoing | Andrei Cimpean
236 | SAM-VED | R02070 | ER100 PSA CMP ECO MY23.50_IPB High | R02070-SBZ-03 | dPV | A - I9 Exit | Dan V. |  |  | TBD |  | TBD | Next | Andrei Cimpean
237 | SAM-VED | R02070 | ER100 PSA CMP ECO MY23.50_IPB High | R02070-SBZ-04 | dPV | B - I9 Entry | Dan V. |  | 2022-05-14 | 19 | 2022-05-15 | 19 | Done | Andrei Cimpean
238 | SAM-VED | R02070 | ER100 PSA CMP ECO MY23.50_IPB High | R02070-SBZ-05 | dPV | B - STT | Dan V. |  | 2022-05-17 | 20 | 2022-05-18 | 20 | Done | Andrei Cimpean
239 | SAM-VED | R02070 | ER100 PSA CMP ECO MY23.50_IPB High | R02070-SBZ-06 | dPV | B - TSE | Dan V. |  | 2022-05-20 | 20 |  | TBD | Ongoing | Andrei Cimpean
240 | SAM-VED | R02070 | ER100 PSA CMP ECO MY23.50_IPB High | R02070-SBZ-07 | dPV | B - I9 Exit | Dan V. |  |  | TBD |  | TBD | Next | Andrei Cimpean
241 | SAM-VED | R02071 | ER100 PSA CMP ECO MY23.50_IPB Base | R02071-SBZ-01 | dPV | A - I9 Entry | Dan V. |  | 2022-05-13 | 19 | 2022-05-14 | 19 | Done | Andrei Cimpean
242 | SAM-VED | R02071 | ER100 PSA CMP ECO MY23.50_IPB Base | R02071-SBZ-02 | dPV | A - PTC | Dan V. |  | 2022-05-14 | 19 |  | TBD | Ongoing | Andrei Cimpean
243 | SAM-VED | R02071 | ER100 PSA CMP ECO MY23.50_IPB Base | R02071-SBZ-03 | dPV | A - I9 Exit | Dan V. |  |  | TBD |  | TBD | Next | Andrei Cimpean
244 | SAM-VED | R02071 | ER100 PSA CMP ECO MY23.50_IPB Base | R02071-SBZ-04 | dPV | B - I9 Entry | Dan V. |  | 2022-05-14 | 19 | 2022-05-15 | 19 | Done | Andrei Cimpean
245 | SAM-VED | R02071 | ER100 PSA CMP ECO MY23.50_IPB Base | R02071-SBZ-05 | dPV | B - STT | Dan V. |  | 2022-05-17 | 20 | 2022-05-18 | 20 | Done | Andrei Cimpean
246 | SAM-VED | R02071 | ER100 PSA CMP ECO MY23.50_IPB Base | R02071-SBZ-06 | dPV | B - TSE | Dan V. |  | 2022-05-20 | 20 |  | TBD | Ongoing | Andrei Cimpean
247 | SAM-VED | R02071 | ER100 PSA CMP ECO MY23.50_IPB Base | R02071-SBZ-07 | dPV | B - I9 Exit | Dan V. |  |  | TBD |  | TBD | Next | Andrei Cimpean
248 | SAM-VED | R02072 | ER100 PSA CMP ECO MY23.50_ESC Base | R02072-SBZ-01 | dPV | A - I9 Entry | Dan V. |  | 2022-05-13 | 19 | 2022-05-14 | 19 | Done | Andrei Cimpean
249 | SAM-VED | R02072 | ER100 PSA CMP ECO MY23.50_ESC Base | R02072-SBZ-02 | dPV | A - PTC | Dan V. |  | 2022-05-14 | 19 |  | TBD | Ongoing | Andrei Cimpean
250 | SAM-VED | R02072 | ER100 PSA CMP ECO MY23.50_ESC Base | R02072-SBZ-03 | dPV | A - I9 Exit | Dan V. |  |  | TBD |  | TBD | Next | Andrei Cimpean
251 | SAM-VED | R02072 | ER100 PSA CMP ECO MY23.50_ESC Base | R02072-SBZ-04 | dPV | B - I9 Entry | Dan V. |  | 2022-05-14 | 19 | 2022-05-15 | 19 | Done | Andrei Cimpean
252 | SAM-VED | R02072 | ER100 PSA CMP ECO MY23.50_ESC Base | R02072-SBZ-05 | dPV | B - STT | Dan V. |  | 2022-05-17 | 20 | 2022-05-18 | 20 | Done | Andrei Cimpean
253 | SAM-VED | R02072 | ER100 PSA CMP ECO MY23.50_ESC Base | R02072-SBZ-06 | dPV | B - TSE | Dan V. |  | 2022-05-20 | 20 |  | TBD | Ongoing | Andrei Cimpean
254 | SAM-VED | R02072 | ER100 PSA CMP ECO MY23.50_ESC Base | R02072-SBZ-07 | dPV | B - I9 Exit | Dan V. |  |  | TBD |  | TBD | Next | Andrei Cimpean
255 | SAM-VED | R02330 | Hero_MiniMAB_ABS_MY18.25_ABWB | R02330-SBZ-01 | Pre-compliance | TSE ( T.I. characterization) | Dan V. | CW24 | 2022-06-10 | 23 | 2022-06-13 | 24 | Done | Vlad Rotaru
256 | SAM-VED | R02293 | ER100_B-MPV | R02293-SBZ-01 | PV | C - I9 Entry | Catalin S. | CW 21 | 2022-05-23 | 21 | 2022-05-24 | 21 | Done | George Cebuc
257 | SAM-VED | R02293 | ER100_B-MPV | R02293-SBZ-02 | PV | C - TS | Catalin S. |  | 2022-05-24 | 21 |  | TBD | Ongoing | George Cebuc
258 | SAM-VED | R02293 | ER100_B-MPV | R02293-SBZ-03 | PV | C - PTC | Catalin S. |  |  | TBD |  | TBD | Next | George Cebuc
259 | SAM-VED | R02293 | ER100_B-MPV | R02293-SBZ-04 | PV | C - Vibration Endurance |  |  |  | TBD |  | TBD | Next | George Cebuc
260 | SAM-VED | R02293 | ER100_B-MPV | R02293-SBZ-05 | PV | C - I9 Exit | Catalin S. |  |  | TBD |  | TBD | Next | George Cebuc
261 | heat-CE | R02185 | AUD_XXXX_16_PNEU_BK | R02185-SBZ-01 | PV | High / low temperature storage | Rodean C | CW 23 | 2022-06-03 | 22 | 2022-06-05 | 22 | Done | David Cristina Elena
262 | heat-CE | R02185 | AUD_XXXX_16_PNEU_BK | R02185-SBZ-02 | PV | Mechanical Shock | Tiberiu B. | CW25 | 2022-06-17 | 24 | 2022-06-17 | 24 | Done | David Cristina Elena
263 | heat-CE | R02185 | AUD_XXXX_16_PNEU_BK | R02185-SBZ-03 | PV | Vibration test | Tiberiu B. | CW25 | 2022-06-23 | 25 |  | TBD | Ongoing | David Cristina Elena
264 | heat-CE | R02185 | AUD_XXXX_16_PNEU_BK | R02185-SBZ-04 | PV | Temperature cycle endurance | Rodean C | CW26-27 |  | TBD |  | TBD | Next | David Cristina Elena
265 | heat-CE | R02185 | AUD_XXXX_16_PNEU_BK | R02185-SBZ-05 | PV | Free Fall | Rodean C | CW24 | 2022-06-14 | 24 | 2022-06-14 | 24 | Done | David Cristina Elena
266 | heat-CE | R02185 | AUD_XXXX_16_PNEU_BK | R02185-SBZ-06 | PV | Temperature Shock (Component) | Rodean C | CW24 | 2022-06-20 | 25 | 2022-06-27 | 26 | Done | David Cristina Elena
267 | heat-CE | R02185 | AUD_XXXX_16_PNEU_BK | R02185-SBZ-07 | PV | Mechanical Shock | Tiberiu B. | CW25 |  | TBD |  | TBD | Next | David Cristina Elena
268 | heat-CE | R02185 | AUD_XXXX_16_PNEU_BK | R02185-SBZ-08 | PV | Dust Test | Rodean C | CW25 | 2022-06-22 | 25 | 2022-06-23 | 25 | Done | David Cristina Elena
269 | heat-CE | R02185 | AUD_XXXX_16_PNEU_BK | R02185-SBZ-09 | PV | Moist Heat Cyclic | Rodean C | CW26-27 |  | TBD |  | TBD | Next | David Cristina Elena
270 | AM | R02327 | SVC DAIMLER | R02327-SBZ–01 | Pre-compliance | High/low temperature storage (SAT+AR+RVS) | Rodean C | CW24 | 2022-06-14 | 24 | 2022-06-16 | 24 | Done | Buteata Marian-Andrei
271 | AM | R02327 | SVC DAIMLER | R02327-SBZ–02 | Pre-compliance | Damp heat cyclic with frost (SAT+AR+RVS) | Rodean C | CW24 | 2022-06-17 | 24 | 2022-06-28 | 26 | Done | Buteata Marian-Andrei
272 | Vitesco | R03908 | Nissan MAPC61T TMAPC65T BAP05T | R03908-SBZ-02 | External request | Thermal shock | Radu I. | CW24 | 2022-06-16 | 24 |  | TBD | Ongoing
273 | SAM-PSS | R02323 | SCCU SAF | R02323-SBZ-01 | dPV | H/L Storage | Radu G. | CW25 | 2022-06-22 | 25 | 2022-06-24 | 25 | Done
274 | SAM-PSS | R02323 | SCCU SAF | R02323-SBZ-02 | dPV | Step Test | Radu G. | CW26 | 2022-06-27 | 26 | 2022-06-28 | 26 | Done
275 |  | R02224 | NISSAN | R02224-SBZ–01 | PV | Thermal Shocks Pre-Aging Test | Radu I. | CW | 2022-06-20 | 25 | 2022-06-21 | 25 | Done | Gabriel Paslaru
276 |  | R02224 | NISSAN | R02224-SBZ–02 | PV | Mounting operation shock test | Ion C. | CW | 2022-06-27 | 26 | 2022-06-27 | 26 | Done | Gabriel Paslaru
277 |  | R02224 | NISSAN | R02224-SBZ–03 | PV | Collision Impact | Ion C. | CW | 2022-06-28 | 26 | 2022-06-28 | 26 | Done | Gabriel Paslaru
278 |  | R02224 | NISSAN | R02224-SBZ–04 | PV | Shocks from the road test | Ion C. | CW | 2022-06-29 | 26 | 2022-06-29 | 26 | Done | Gabriel Paslaru
279 |  | R02224 | NISSAN | R02224-SBZ–05 | PV | Random Vibration Endurance Test | Ion C. | CW | 2022-06-30 | 26 |  | TBD | Ongoing | Gabriel Paslaru
280 | AN | R02326 | DCU SP 21 BMW | R02326-SBZ–01 | dPV | H/L Storage | Iulia T. | CW25 | 2022-06-21 | 25 |  | TBD | Ongoing | Silvana Popovici
281 | AN | R02326 | DCU SP 21 BMW | R02326-SBZ–02 | dPV | K-05 Temperature shock | Iulia T. | CW25 |  | TBD |  | TBD | Done | Silvana Popovici
282 | AN | R02326 | DCU SP 21 BMW | R02326-SBZ–03 | dPV | Free Fall | Iulia T. | CW26 | 2022-07-01 | 26 | 2022-07-01 | 26 | Done | Silvana Popovici
283 | AN | R02326 | DCU SP 21 BMW | R02326-SBZ–04 | dPV | M-04 Vibration test | Ion C. | CW26 |  | TBD |  | TBD | Next | Silvana Popovici
284 | AN | R02326 | DCU SP 21 BMW | R02326-SBZ–05 | dPV | M-05 Mechanical shock | Ion C. | CW27 |  | TBD |  | TBD | Next | Silvana Popovici
285 | SAM-PSS | R02047 | EFP 2.0 | R02047-SBZ–05 | dPV | M-04 Vibration Test | Ion C. | CW24 | 2022-06-14 | 24 | 06/17//2022 | TBD | Done | Ion Hategan
286 | SAM-VED | R02331 | MK100 Panasonic CRP Light | R02331-SBZ–02 | Pre-compliance | Thermal Cycling/ Thermal Shock | Catalin S. | CW25 | 2022-06-21 | 25 |  | TBD | Ongoing | Tudor Bozan
287 | SAM-VED | R02331 | MK100 Panasonic CRP Light | R02331-SBZ–01 | Pre-compliance | Vibration Test | Daniel I. | CW25 | 2022-06-21 | 25 | 2022-06-24 | 25 | Done | Tudor Bozan
288 | SAM-VED | R02331 | MK100 Panasonic CRP Light | R02331-SBZ–03 | Pre-compliance | Vibration Test | Daniel I. |  |  | TBD |  | TBD | Next | Tudor Bozan
289 | SAM-PSS | R02049 | EFP 1.3 | R02049-SBZ-01 | dPV | H/L Storage | Marius B.. | CW26 | 2022-07-01 | 26 | 2022-07-03 | 26 | Done | Ion Hategan
290 | SAM-PSS | R02049 | EFP 1.3 | R02049-SBZ-02 | dPV | Incremental temperature step - 1 | Marius B.. | CW27 | 2022-07-04 | 27 |  | TBD | Ongoing | Ion Hategan
291 | SAM-PSS | R02049 | EFP 1.3 | R02049-SBZ-03 | dPV | Incremental temperature step - 2 | Marius B.. | CW27 |  | TBD |  | TBD | Next | Ion Hategan
292 | SAM-PSS | R02049 | EFP 1.3 | R02049-SBZ-05 | dPV | Temperature shock test | Marius B.. | CW29 |  | TBD |  | TBD | Next | Ion Hategan
293 | SAM-PSS | R02049 | EFP 1.3 | R02049-SBZ-06 | dPV | Moist heat cclic (with frost) | Marius B.. | C230-31 |  | TBD |  | TBD | Next | Ion Hategan
294 | SAM-PSS | R02049 | EFP 1.3 | R02049-SBZ-07 | dPV | Thermal shock (without housing) | Marius B.. | CW28 |  | TBD |  | TBD | Next | Ion Hategan
295 | SAM-PSS | R02322 | SCCU SPCh+ | R02322-SBZ-01 |  | H/L Storage | Marius B.. | CW26 | 2022-07-01 | 26 | 2022-07-03 | 26 | Done
296 | SAM-PSS | R02322 | SCCU SPCh+ | R02322-SBZ-02 |  | Temperature step test | Marius B.. | CW27 | 2022-07-04 | 27 | 2022-07-06 | 27 | Done
297 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-01 | PV | D - I9 Entry | Dan V. | CW31 | 2022-06-29 | 26 | 2022-06-30 | 26 | Done | Sirbu Adrian
298 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-02 | PV | D - STT | Dan V. | CW31 |  | TBD |  | TBD | Next | Sirbu Adrian
299 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-03 | PV | D - Warm op | Dan V. | CW32 |  | TBD |  | TBD | Next | Sirbu Adrian
300 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-04 | PV | D - Cold op | Dan V. | CW32 |  | TBD |  | TBD | Next | Sirbu Adrian
301 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-05 | PV | D - I9 Exit | Dan V. | CW33 |  | TBD |  | TBD | Next | Sirbu Adrian
302 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-06 | PV | G - I9 Entry | Dan V. | CW26 | 2022-06-24 | 25 | 2022-06-25 | 25 | Done | Sirbu Adrian
303 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-07 | PV | G - TSE | Dan V. | CW26-39 | 2022-06-27 | 26 |  | TBD | Ongoing | Sirbu Adrian
304 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-08 | PV | G - IWS | Dan V. | CW40 |  | TBD |  | TBD | Next | Sirbu Adrian
305 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-09 | PV | G - HPC | Dan V. | CW41 |  | TBD |  | TBD | Next | Sirbu Adrian
306 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-10 | PV | G - I9 Exit | Dan V. | CW41 |  | TBD |  | TBD | Next | Sirbu Adrian
307 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-11 | PV | H - I9 Entry | Dan V. | CW26 | 2022-06-28 | 26 | 2022-06-29 | 26 | Done | Sirbu Adrian
308 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-12 | PV | H - LT/01_Thermal cycling | Dan V. | CW26-40 |  | TBD |  | TBD | Next | Sirbu Adrian
309 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-13 | PV | H - IWS | Dan V. | CW43 |  | TBD |  | TBD | Next | Sirbu Adrian
310 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-14 | PV | H - HPC | Dan V. | CW44 |  | TBD |  | TBD | Next | Sirbu Adrian
311 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-15 | PV | H - I9 Exit | Dan V. | CW44 |  | TBD |  | TBD | Next | Sirbu Adrian
312 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-16 | PV | I - I9 Entry | Dan V. | CW26 | 2022-06-28 | 26 | 2022-06-29 | 26 | Done | Sirbu Adrian
313 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-17 | PV | I - WST | Dan V. | CW26 | 2022-06-29 | 26 | 2022-06-29 | 26 | Done | Sirbu Adrian
314 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-18 | PV | I - IRT | Dan V. | CW26 | 2022-06-29 | 26 | 2022-06-29 | 26 | Done | Sirbu Adrian
315 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-19 | PV | I - DHC | Dan V. | CW26-32 | 2022-06-30 | 26 |  | TBD | Ongoing | Sirbu Adrian
316 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-20 | PV | I - WST | Dan V. | CW33 |  | TBD |  | TBD | Next | Sirbu Adrian
317 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-21 | PV | I - IRT | Dan V. | CW33 |  | TBD |  | TBD | Next | Sirbu Adrian
318 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-22 | PV | I - I9 Exit | Dan V. | CW33 |  | TBD |  | TBD | Next | Sirbu Adrian
319 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-23 | PV | J - I9 Entry | Dan V. | CW37 |  | TBD |  | TBD | Next | Sirbu Adrian
320 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-24 | PV | J - LT/03_THE | Dan V. | CW37-51 |  | TBD |  | TBD | Next | Sirbu Adrian
321 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-25 | PV | J - I9 Exit | Dan V. | CW02 |  | TBD |  | TBD | Next | Sirbu Adrian
322 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-26 | PV | K - I9 Entry | Dan V. | CW26 | 2022-06-24 | 25 | 2022-06-25 | 25 | Done | Sirbu Adrian
323 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-27 | PV | K - Tspa | Dan V. | CW27 | 2022-06-28 | 26 | 2022-06-30 | 26 | Done | Sirbu Adrian
324 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-28 | PV | K - LAP | Dan V. | CW28 |  | TBD |  | TBD | Next | Sirbu Adrian
325 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-29 | PV | K - Warm st | Dan V. | CW28 |  | TBD |  | TBD | Next | Sirbu Adrian
326 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-30 | PV | K - Cold st | Dan V. | CW29 |  | TBD |  | TBD | Next | Sirbu Adrian
327 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-34 | PV | K - CL/06_ climatic seq | Dan V. | CW35-36 |  | TBD |  | TBD | Next | Sirbu Adrian
328 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-35 | PV | K - IWS | Dan V. | CW40 |  | TBD |  | TBD | Next | Sirbu Adrian
329 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-36 | PV | K - HPC | Dan V. | CW41 |  | TBD |  | TBD | Next | Sirbu Adrian
330 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-37 | PV | K - I9 Exit | Dan V. | CW41 |  | TBD |  | TBD | Next | Sirbu Adrian
331 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-38 | PV | L - I9 Entry | Dan V. | CW25 | 2022-06-21 | 25 | 2022-06-22 | 25 | Done | Sirbu Adrian
332 | SAM-VED | R02145 | CAirs_Nissan QX80 | R02145-SBZ-40 | PV | L - I9 Exit | Dan V. | CW40 |  | TBD |  | TBD | Next | Sirbu Adrian
333 | SAM-VED | R02270 | Hyundai_K3_MK120_IPB_MY23.00_Base_SX2 SX2 | R02270-SBZ-01 | PV | C - I9 Entry | Dan V. | CW26 |  | TBD |  | TBD | Next | Andrei Cimpean
334 | SAM-VED | R02270 | Hyundai_K3_MK120_IPB_MY23.00_Base_SX2 SX2 | R02270-SBZ-01 | PV | C - TSE | Dan V. | CW27-31 |  | TBD |  | TBD | Next | Andrei Cimpean
335 | SAM-VED | R02270 | Hyundai_K3_MK120_IPB_MY23.00_Base_SX2 SX2 | R02270-SBZ-01 | PV | C - Thermal cycle test | Dan V. | CW33-34 |  | TBD |  | TBD | Next | Andrei Cimpean
336 | SAM-VED | R02270 | Hyundai_K3_MK120_IPB_MY23.00_Base_SX2 SX2 | R02270-SBZ-01 | PV | C - I9 Exit | Dan V. | CW37 |  | TBD |  | TBD | Next | Andrei Cimpean
337 | SAM-VED | R02270 | Hyundai_K3_MK120_IPB_MY23.00_Base_SX2 SX2 | R02270-SBZ-01 | PV | E - I9 Entry | Dan V. | CW26 |  | TBD |  | TBD | Next | Andrei Cimpean
338 | SAM-VED | R02270 | Hyundai_K3_MK120_IPB_MY23.00_Base_SX2 SX2 | R02270-SBZ-01 | PV | E - HTHE | Dan V. | CW34-39 |  | TBD |  | TBD | Next | Andrei Cimpean
339 | SAM-VED | R02270 | Hyundai_K3_MK120_IPB_MY23.00_Base_SX2 SX2 | R02270-SBZ-01 | PV | E - I9 Exit | Dan V. | CW40 |  | TBD |  | TBD | Next | Andrei Cimpean
340 | heat-CE | R02217 | MB_167_22_TRAN_FRE_SIP | R02217-SBZ-01 | PV | K-01 High/Low Temperature Storage | Rodean C | CW25 | 2022-06-22 | 25 | 2022-06-24 | 25 | Done
341 | heat-CE | R02217 | MB_167_22_TRAN_FRE_SIP | R02217-SBZ-02 | PV | K-02 Temperature step test | Rodean C | CW26 | 2022-06-27 | 26 | 2022-06-29 | 26 | Done
342 | heat-CE | R02217 | MB_167_22_TRAN_FRE_SIP | R02217-SBZ-03 | PV | M-01 Free Fall | Rodean C | CW26 | 2022-07-01 | 26 | 2022-07-01 | 26 | Done
343 | heat-CE | R02217 | MB_167_22_TRAN_FRE_SIP | R02217-SBZ-04 | PV | K-05 Thermal Shock | Rodean C | CW27 | 2022-06-30 | 26 |  |  | Next
344 | heat-CE | R02217 | MB_167_22_TRAN_FRE_SIP | R02217-SBZ-05 | PV | M-05 Mechanical Shock | Rodean C | CW27 |  |  |  |  | Next
345 | heat-CE | R02217 | MB_167_22_TRAN_FRE_SIP | R02217-SBZ-06 | PV | K-02 Temperature step test | Rodean C | CW27-28 |  |  |  |  | Next
357 | SAM-VED | R02366 | RVS22xGM12 2.1MP | R02362-SBZ-01 | Pre-comp. | Degrees of protection against water (IPx9K) | Dan V. | CW21 | 2022-05-24 | 21 | 2022-05-24 | 21 | Done | Dayana Montenegro | N/A
346 | SAM-VED | R02061 / ID 943 | BMW G2x (3 series) MY'19 MK 100 HP-High Plus 2 ESC | RID943-SBZ-26 | PV | A - I9 Exit | Catalin S. | CW24 | 2022-06-14 | 24 | 2022-06-15 | 24 | Done | Bucse Bogdan
347 | SAM-VED | R02099 | ER100 Honda 30AA ESC 8M6 MY23 Base IPB HEV | R02099-SBZ-32 | PV | E - I9 Exit | Catalin S. | CW24 | 2022-06-14 | 24 | 2022-06-15 | 24 | Done | Cebuc G. //Bucse
348 | SAM-VED | R02329 | CAirS INA 201 broker parts | R02329-SBZ-01 | PV | A - I9 Entry | Catalin S. | CW26 | 2022-06-29 | 26 | 2022-06-30 | 26 | Done | Daniel Filimon
349 | SAM-VED | R02329 | CAirS INA 201 broker parts | R02329-SBZ-02 | PV | K-05 Thermal Shock (Component) | Catalin S. | CW26 | 2022-06-30 | 26 |  |  | Ongoing | Daniel Filimon
350 | SAM-VED | R02329 | CAirS INA 201 broker parts | R02329-SBZ-03 | PV | K-02 Temperature Step Test | Catalin S. | [5 empty] | Next | Daniel Filimon
351 | SAM-PSS | R02339 | I-CMV | R02339-SBZ-01 | dPV | K-05 Temperature Shock Test | Marius B.. | CW27 | 2022-07-05 | 27 |  | TBD | Ongoing | Mihail Bardasu
352 | heat-CE | R02202 | MB_MRA2_20_PNEU_CC | R02202-SBZ-01 | dPV | L-01_Pneumatic /Electric Endurance Test | Rodean C | CW27-40 | 2022-07-05 | 27 |  |  | Ongoing
353 | VNI | R02363 | MQB19 GW LOW | R02363-SBZ-01 | Pre-comp. | Test Ec: Free fall | Radu G. | CW27 | 2022-07-05 | 27 | 2022-07-05 | 27 | Done | Robert Lazar | N/A
354 | VNI | R02360 | MQB19 GW LOW | R02360-SBZ-01 | Pre-comp. | Temperature step test | Iulia T. | CW27 | 2022-07-09 |  |  |  | Next | Cojocariu Costel | N/A
355 | SAM-VED | R02359 | Renault ESC | R02359-SBZ-01 | Pre-comp. | Test B: Dry heat | Catalin S. | CW27 | 2022-07-08 | 27 |  | 27 | Next
356 | VNI | R02361 | MQB19 GW FCM | R02361-SBZ-01 | Pre-comp. | Cy: Caldura umeda, stare de echilibru | Nick S. | CW27 |  |  |  |  | Next |  | N/A
357 | SAM-VED | R02362 | EXT_AUD_REN_IPX9K | R02362-SBZ-01 | Pre-comp. | Degrees of protection against water (IPx9K) | Dan V. | CW27 | TBD | TBD | TBD | TBD | Next | Andrei Cimpean | N/A
358 | SAM-VED | R03830 | SRR620 | R03830-SBZ-01 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
359 | SAM-VED | R03830 | SRR620 | R03830-SBZ-02 |  | Dry heat | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
360 | SAM-VED | R03830 | SRR620 | R03830-SBZ-03 |  | Cold test | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
361 | SAM-VED | R03830 | SRR620 | R03830-SBZ-04 |  | Damp heat | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
362 | SAM-VED | R03830 | SRR620 | R03830-SBZ-05 |  | Random vibration | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
363 | SAM-VED | R03830 | SRR620 | R03830-SBZ-06 |  | Mechanical shock | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
364 | SAM-VED | R03830 | SRR620 | R03830-TSR-07 |  | Thermal Shock in Splash Water | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
365 | SAM-VED | R03830 | SRR620 | R03830-SBZ-08 |  | Ingress protection (IPx7) | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
366 | SAM-VED | R03830 | SRR620 | R03830-SBZ-09 |  | Free fall | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
367 | SAM-VED | R03830 | SRR620 | R03830-SBZ-10 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
368 | SAM-VED | R03830 | SRR620 | R03830-SBZ-01 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
369 | SAM-VED | R03830 | SRR620 | R03830-SBZ-10 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
369 | SAM-VED | R03830 | SRR620 | R03830-SBZ-10 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
369 | SAM-VED | R03830 | SRR620 | R03830-SBZ-10 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-10 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-09 |  | Free fall | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-08 |  | Ingress protection (IPx7) | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-TSR-07 |  | Thermal Shock in Splash Water | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-06 |  | Mechanical shock | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-05 |  | Random vibration | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-04 |  | Damp heat | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-03 |  | Cold test | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-02 |  | Dry heat | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
369 | SAM-VED | R03830 | SRR620 | R03830-SBZ-01 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
369 | SAM-VED | R03830 | SRR620 | R03830-SBZ-10 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-01 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-02 |  | Dry heat | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-03 |  | Cold test | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-04 |  | Damp heat | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-05 |  | Random vibration | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-06 |  | Mechanical shock | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
369 | SAM-VED | R03830 | SRR620 | R03830-TSR-07 |  | Thermal Shock in Splash Water | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
369 | SAM-VED | R03830 | SRR620 | R03830-SBZ-08 |  | Ingress protection (IPx7) | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
369 | SAM-VED | R03830 | SRR620 | R03830-SBZ-09 |  | Free fall | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
369 | SAM-VED | R03830 | SRR620 | R03830-SBZ-10 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
369 | SAM-VED | R03830 | SRR620 | R03830-SBZ-01 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-02 |  | Dry heat | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-03 |  | Cold test | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-04 |  | Damp heat | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-05 |  | Random vibration | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-06 |  | Mechanical shock | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-TSR-07 |  | Thermal Shock in Splash Water | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-08 |  | Ingress protection (IPx7) | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-09 |  | Free fall | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-10 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-01 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-02 |  | Dry heat | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-03 |  | Cold test | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-04 |  | Damp heat | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-05 |  | Random vibration | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-06 |  | Mechanical shock | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-TSR-07 |  | Thermal Shock in Splash Water | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-08 |  | Ingress protection (IPx7) | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-09 |  | Free fall | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-10 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-01 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-02 |  | Dry heat | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-03 |  | Cold test | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-04 |  | Damp heat | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-05 |  | Random vibration | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-06 |  | Mechanical shock | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-TSR-07 |  | Thermal Shock in Splash Water | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-08 |  | Ingress protection (IPx7) | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-09 |  | Free fall | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
| SAM-VED | R03830 | SRR620 | R03830-SBZ-10 |  | 9 Points Parameters | Catalin S. | TBD | TBD |  | TBD |  | Next | Adrian Mardare
|  | R02224 | NISSAN LDM | -SBZ-01 |  | Thermal Shocks Pre-Aging Test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | -SBZ-02 |  | Mounting operation shock test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | -SBZ-03 |  | Collision Impact | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | -SBZ-04 |  | Shocks from the road test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | -SBZ-05 |  | Random Vibration Endurance Test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM
369 |  | R02224 | NISSAN LDM |  |  | Thermal Shocks Pre-Aging Test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM |  |  | Mounting operation shock test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM |  |  | Collision Impact | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM |  |  | Shocks from the road test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM |  |  | Random Vibration Endurance Test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-01 |  | Thermal Shocks Pre-Aging Test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-02 |  | Mounting operation shock test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-03 |  | Collision Impact | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-04 |  | Shocks from the road test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-05 |  | Random Vibration Endurance Test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-01 |  | Thermal Shocks Pre-Aging Test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-02 |  | Mounting operation shock test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-03 |  | Collision Impact | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-04 |  | Shocks from the road test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-05 |  | Random Vibration Endurance Test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-01 |  | Thermal Shocks Pre-Aging Test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
369 |  | R02224 | NISSAN LDM | R02224-SBZ-02 |  | Mounting operation shock test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
369 |  | R02224 | NISSAN LDM | R02224-SBZ-03 |  | Collision Impact | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-04 |  | Shocks from the road test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-05 |  | Random Vibration Endurance Test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-01 | PV | Thermal Shocks Pre-Aging Test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-02 | PV | Mounting operation shock test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-03 | PV | Collision Impact | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-04 | PV | Shocks from the road test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
|  | R02224 | NISSAN LDM | R02224-SBZ-05 | PV | Random Vibration Endurance Test | Radu I. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
| N.A | R02110 | VOLVO RE-DESIGN | R02110-SBZ-01 | dPV | MECHANICAL SHOCK | TBD. | TBD | TBD |  | TBD |  | Next | Vlad Florea
| N.A | R02110 | VOLVO RE-DESIGN | R02110-SBZ-02 | dPV | TEMPERATURE STEP TEST | TBD. | TBD | TBD |  | TBD |  | Next | Vlad Florea
dsa | sda | asd | sda | sda | dsa | asd
369 | SAM-VED | R02221 | NISSAN LDM | R02221-SBZ-01 | DV | Thermal Shocks Pre-Aging Test | Robert T. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
| SAM-VED | R02221 | NISSAN LDM | R02221-SBZ-02 | DV | Mounting operation shock test | Robert T. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
| SAM-VED | R02221 | NISSAN LDM | R02221-SBZ-03 | DV | Collision Impact | Robert T. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
| SAM-VED | R02221 | NISSAN LDM | R02221-SBZ-04 | DV | Shocks from the road test | Robert T. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
| SAM-VED | R02221 | NISSAN LDM | R02221-SBZ-05 | DV | Random Vibration Endurance Test | Robert T. | TBD | TBD |  | TBD |  | Next | Gabriel Paslaru
369
369
369
369
369
369
369
369
369
369
369
369
369
369
369
369
369
Internal
Formulas:
Test Start (CW) = IF(ISBLANK([Test Start (dd.mm.yyyy)]),"TBD",IF(ISTEXT([Test Start (dd.mm.yyyy)]),"TBD",ISOWEEKNUM([Test Start (dd.mm.yyyy)])))
Test Start (CW) = IF(ISBLANK([Test Start (dd.mm.yyyy)]),"TBD",IF(ISTEXT([Test Start (dd.mm.yyyy)]),"TBD",(ISOWEEKNUM([Test Start (dd.mm.yyyy)]))))
Test End (CW) = IF(ISBLANK([Test End (dd.mm.yyyy)]),"TBD",IF(ISTEXT([Test End (dd.mm.yyyy)]),"TBD",ISOWEEKNUM([Test End (dd.mm.yyyy)])))
Test End (CW) = IF(ISBLANK([Test End (dd.mm.yyyy)]),"TBD",IF(ISTEXT([Test End (dd.mm.yyyy)]),"TBD",(ISOWEEKNUM([Test End (dd.mm.yyyy)]))))
Test Start (dd.mm.yyyy) = IF(ISBLANK([Test Schedule (CW - CW)]),"TBD",IF(ISTEXT([Test Schedule (CW - CW)]),"TBD",(ISOWEEKNUM([Test Schedule (CW - CW)]))))
Test End (dd.mm.yyyy) = IF(ISBLANK([Test Start (CW)]),"TBD",IF(ISTEXT([Test Start (CW)]),"TBD",(ISOWEEKNUM([Test Start (CW)]))))